## Diagramme PAY@MCO (FTE)
Sprintverschiebung
-1 | Sprint 1_3+4 | Sprint 1_5+6 | Sprint 2_1+2 | Sprint 2_3/4 | Sprint 2_5/6 | Sprint 3_1/2 | SODA | Stacked & Ordered Development-Accomplished
| 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  | Sprint 1_3+4 | Sprint 1_5+6 | Sprint 2_1+2 | Sprint 2_3/4 | Sprint 2_5/6 | Sprint 3_1/2
| IDL Sprint Velocity | Payment | 18 | 23 | 30 | 27 | [8 empty] | 30 | 27
1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [6 empty] | 30 | 27 | 31
| Payment | 18 | 23 | 30 | 27 | 31 | [6 empty] | 30 | 27 | 31 | 34
2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  |  |  | 30 | 27 | 31 | 34 | 20
| 18 | 23 | 30 | 27 | 31 | 34 |  |  |  |  | 30 | 27 | 31 | 34 | 20 | 26
3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  |  |  | 27 | 31 | 34 | 20 | 26 | 26
| 23 | 30 | 27 | 31 | 34 | 20 |  |  |  |  | 2 | 1 | 1 | 5 | 5 | 4
4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| 30 | 27 | 31 | 34 | 20 | 26
5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| 27 | 31 | 34 | 20 | 26 | 26
6 | 7 | 7 | 7 | 7 | 7 | 7 | 1
| Butterfly | MCO | Vlinder | Vlinder | BTF@MCO |  | AC
| Butterfly | SCO | Papillon | Papillon | BTF@SCO |  | AI
| Payment | MCO | The Pay-Team | Payment | PAY@MCO |  | AA
| Payment | SCO | Two Fingered Sloth | TFS | PAY@SCO |  | AF
| Value | MCO | Synergy | Synergy | VLU@MCO |  | AH
| Value | SCO | TNT | TNT | VLU@SCO |  | AE
| Sales | MCO | Team S | Sales | SLS@MCO |  | AB
| Sales | SCO | The Till Titans | TTT | SLS@SCO |  | AD
| Engineering | CHO | Engineering | Engineering | ENG@CHO |  | Z
| IDL | Interleaved, Differentiating, Levelled
A | VALE | Velocity Attribution with Logical Explanations
D | Standardabweichung | Average Velocity (4 Sprints prior) | IDL Sprint Velocity | Alarming | Concerning | Healthy | Spot-On | Lively | Bloated | Target
30 |  |  | Payment | 1 |  |  |  |  | 57 | 1
Sprint 4_4+5 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 39 | 18
Sprint 4_6/7+8 | 0 | 18 | 23 | 18 | 0 | 0 | 0 | 0 | 39 | 18
Sprint 1_1+2 | 2.5 | 20.5 | 30 | 15.5 | 2.5 | 2.5 | 2.5 | 2.5 | 31.5 | 18
Sprint 1_3+4 | 4.9216 | 23.6667 | 27 | 13.8235 | 4.9216 | 4.9216 | 4.9216 | 4.9216 | 23.4901 | 19
Sprint 1_5+6 | 4.5 | 24.5 | 31 | 15.5 | 4.5 | 4.5 | 4.5 | 4.5 | 23.5 | 20
Sprint 2_1+2 | 3.1125 | 27.75 | 34 | 21.5251 | 3.1125 | 3.1125 | 3.1125 | 3.1125 | 23.0251 | 25
Sprint 2_3/4 | 2.5 | 30.5 | 20 | 25.5 | 2.5 | 2.5 | 2.5 | 2.5 | 21.5 | 28
Sprint 2_5/6 | 5.244 | 28 | 26 | 17.5119 | 5.244 | 5.244 | 5.244 | 5.244 | 18.5119 | 23
Sprint 3_1/2 | 5.3092 | 27.75 | 26 | 17.1316 | 5.3092 | 5.3092 | 5.3092 | 5.3092 | 18.6316 | 22
Sprint 3_3/4 | 4.9749 | 26.5 | 23.9333 | 16.5501 | 4.9749 | 4.9749 | 4.9749 | 4.9749 | 20.5501 | 22
Sprint 3_5/6 | 2.4497 | 23.9833 | 21.4889 | 19.084 | 2.4497 | 2.4497 | 2.4497 | 2.4497 | 28.1173 | 22
| HIL | Hieratic, Incremental, Librating
| Standard Deviation | 95% factor | 95% VELOCITY | Mean Velocity (Current + 5) | HIL Sprint Velocity | FTE corrected | Median | FTE | Special Effects
|  | 2 |  |  | Payment
Sprint 4_4+5 | 0 | 100% | 17 | 17 | 17 | 17 | 17 | 1 | 0
Sprint 4_6/7+8 | 6 | 85.97% | 19.7737 | 23 | 29 | 21.5685 | 23 | 0.89637 | 9.6667
Sprint 1_1+2 | 9.3927 | 82% | 23.5058 | 28.6667 | 40 | 29.1944 | 29 | 1.2331 | 4
Sprint 1_3+4 | 8.1356 | 84.68% | 24.3447 | 28.75 | 29 | 24.4363 | 29 | 1.1868 | 0
Sprint 1_5+6 | 11.8085 | 80.4% | 26.8544 | 33.4 | 52 | 33.3369 | 40 | 1.1699 | 13
Sprint 2_1+2 | 10.8167 | 81.99% | 27.0564 | 33 | 31 | 26.4464 | 31 | 0.98312 | 5
Sprint 2_3/4 | 9.8939 | 84.03% | 28.2905 | 33.6667 | 21 | 27.0791 | 31 | 0.7755 | 0
Sprint 2_5/6 | 10.3118 | 82.92% | 27.3626 | 33 | 25 | 29.0739 | 25 | 0.85988 | 0
Sprint 3_1/2 | 9.9163 | 82.47% | 25.5655 | 31 | 28 | 27.0837 | 25 | 1.0338
Sprint 3_3/4 | 9.9233 | 82.96% | 26.4096 | 31.8333 | 34 | 24.4541 | 28 | 1.3904
Sprint 3_5/6 | 7.946 | 86.16% | 26.5649 | 30.8333 | 46 | 33.085 | 34 | 1.3904

## Diagramme PAY@MCO
Sprintverschiebung
-1 | Sprint 1_3+4 | Sprint 1_5+6 | Sprint 2_1+2 | Sprint 2_3/4 | Sprint 2_5/6 | Sprint 3_1/2 | SODA | Stacked & Ordered Development-Accomplished
| 1 | 2 | 3 | 4 | 5 | 6 | [12 empty] | Sprint 1_3+4 | Sprint 1_5+6 | Sprint 2_1+2 | Sprint 2_3/4 | Sprint 2_5/6 | Sprint 3_1/2
| IDL Sprint Velocity | Payment | 18 | 23 | 30 | 27 | [12 empty] | IDL Sprint Velocity | Payment | 18 | 23 | 30 | 27
1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [11 empty] | Payment | 18 | 23 | 30 | 27 | 31
| Payment | 18 | 23 | 30 | 27 | 31 | [12 empty] | 18 | 23 | 30 | 27 | 31 | 34
2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | [11 empty] | 23 | 30 | 27 | 31 | 34 | 20
| 18 | 23 | 30 | 27 | 31 | 34 | [12 empty] | 30 | 27 | 31 | 34 | 20 | 26
3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | [11 empty] | 27 | 31 | 34 | 20 | 26 | 26
| 23 | 30 | 27 | 31 | 34 | 20 | [12 empty] | 2 | 1 | 1 | 6 | 5 | 4
4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| 30 | 27 | 31 | 34 | 20 | 26
5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| 27 | 31 | 34 | 20 | 26 | 26
6 | 7 | 7 | 7 | 7 | 7 | 7 | 1
| Butterfly | MCO | Vlinder | Vlinder | BTF@MCO |  | AC
| Butterfly | SCO | Papillon | Papillon | BTF@SCO |  | AI
| Payment | MCO | The Pay-Team | Payment | PAY@MCO |  | AA
| Payment | SCO | Two Fingered Sloth | TFS | PAY@SCO |  | AF
| Value | MCO | Synergy | Synergy | VLU@MCO |  | AH
| Value | SCO | TNT | TNT | VLU@SCO |  | AE
| Sales | MCO | Team S | Sales | SLS@MCO |  | AB
| Sales | SCO | The Till Titans | TTT | SLS@SCO |  | AD
| Engineering | CHO | Engineering | Engineering | ENG@CHO |  | Z
A | IDL | Interleaved, Differentiating, Levelled
D | VALE | Velocity Attribution with Logical Explanations
30 | Standardabweichung | Average Velocity | IDL Sprint Velocity | RZ: Alarming | RZ: Concerning | RZ: Healthy | RZ: Spot-On | RZ: Lively | RZ: Bloated | Target Trajectory | tt | tt | Target Velocity | calc range | zone | target zone |  | 0.3
| 1 | 2 | Payment | 1 |  |  |  |  | 200 |  |  |  | 1 | 4
Sprint 4_4+5 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 182 | 18 |  |  | 18 | 29 |  | 4 |  | 0.31765 | [7 empty] | RAINBOW | Ratingzone Adjustment Into Normalized Bands Of Unambiguous Understanding | [11 empty] | 10
Sprint 4_6/7+8 | 0 | 18 | 23 | 18 | 0 | 0 | 0 | 0 | 182 | 18 | 23 |  | 18 | 30 |  | 4 |  | 0.46028 | [6 empty] | -4 | 1 | Velocity | [6 empty] | 32 | 1 | 2 | Payment | Alarming | 10
Sprint 1_1+2 | 2.5 | 20.5 | 30 | 15.5 | 2.5 | 2.5 | 2.5 | 2.5 | 174.5 |  | 22 | 30 | 22 | 31 | 6 | 4 | 6 | 0.5472 | [6 empty] | 0 | Sprint 1_3+4 | 36.7729 | 1 | [5 empty] | Sprint 1_3+4 | 4.9216 | 23.6667 | 27 | Concerning | 20
Sprint 1_3+4 | 4.9216 | 23.6667 | 27 | 13.8235 | 4.9216 | 4.9216 | 4.9216 | 4.9216 | 166.4901 | 27 |  | 31 | 31 | 32 | 4 | 5 | 10 | 0.66235 | [6 empty] | 1 | Sprint 1_5+6 | 44.4444 |  | 1 |  |  |  |  | Sprint 1_5+6 | 4.5 | 24.5 | 31 | Healthy | 30
Sprint 1_5+6 | 4.5 | 24.5 | 31 | 15.5 | 4.5 | 4.5 | 4.5 | 4.5 | 166.5 | 27 | 31 |  | 27 | 33 | 5 | 4 | 9 | 0.64249 | [6 empty] | 2 | Sprint 2_1+2 | 50.0805 |  |  | 1 |  |  |  | Sprint 2_1+2 | 3.1125 | 27.75 | 34 | Spot-On | 40
Sprint 2_1+2 | 3.1125 | 27.75 | 34 | 21.5251 | 3.1125 | 3.1125 | 3.1125 | 3.1125 | 166.0251 |  | 29 | 34 | 29 | 34 | 6 | 4 | 6 | 0.77878 | [6 empty] | 3 | Sprint 2_3/4 | -12 |  |  |  | 1 |  |  | Sprint 2_3/4 | 2.5 | 30.5 | 20 | Lively | 50
Sprint 2_3/4 | 2.5 | 30.5 | 20 | 25.5 | 2.5 | 2.5 | 2.5 | 2.5 | 164.5 | 20 |  | 34 | 34 | 35 | 1 | 5 | 1 | 0.83086 | [6 empty] | 4 | Sprint 2_5/6 | 26.1861 |  |  |  |  | 1 |  | Sprint 2_5/6 | 5.244 | 28 | 26 | Bloated | 60
Sprint 2_5/6 | 5.244 | 28 | 26 | 17.5119 | 5.244 | 5.244 | 5.244 | 5.244 | 161.5119 | 20 | 26 |  | 20 | 36 | 3 | 2 | 9 | 0.8936 | [6 empty] | 5 | Sprint 3_1/2 | 26.7038 | [5 empty] | 1 | Sprint 3_1/2 | 5.3092 | 27.75 | 26
Sprint 3_1/2 | 5.3092 | 27.75 | 26 | 17.1316 | 5.3092 | 5.3092 | 5.3092 | 5.3092 | 161.6316 |  | 30 | 26 | 30 | 37 | 3 | 4 | 9 | 0.90409
Sprint 3_3/4 | 4.9749 | 26.5 | 31 | 16.5501 | 4.9749 | 4.9749 | 4.9749 | 4.9749 | 163.5501 | 31 |  | 29 | 29 | 38 | 4 | 4 | 10 | 0.90639
Sprint 3_5/6 | 3.8971 | 25.75 | 42 | 17.9558 | 3.8971 | 3.8971 | 3.8971 | 3.8971 | 166.4558 | 28 | 42 |  | 28 | 39 | 6 | 4 | 6 | 0.90839
[11 empty] | 0 | 0
[10 empty] | 0 |  | 0 | [13 empty] | REAL | Relative Excess, Absolute Location
[10 empty] | 0 | 0 | [15 empty] | Delta 2 Ideal | Delta 2 Target | Real KPI
[11 empty] | 0 | 0 | [13 empty] | Sprint 1_1+2 | -2 | 2 | 100%
[10 empty] | 0 |  | 0 | [13 empty] | Sprint 1_3+4 | 0 | -1 | 85.71%
[26 empty] | Sprint 1_5+6 | -1 | 1 | 100%
[26 empty] | Sprint 2_1+2 | -2 | 2 | 100%
[26 empty] | Sprint 2_3/4 | -3 | -4 | 0%
[26 empty] | Sprint 2_5/6 | -1 | 1 | 100%
[26 empty] | Sprint 3_1/2 | -1 | -1 | 71.43%
[26 empty] | Sprint 3_3/4 | 0 | 0 | 100%
| HIL | Hieratic, Incremental, Librating | [23 empty] | Sprint 3_5/6 | -2 | 2 | 100%
| Standard Deviation | HIL Sprint Velocity | Mean Velocity (Current + 5) | 95%-Success VELOCITY | 99% VELOCITY | Median
|  | Payment |  | 2 | 1.5
Sprint 4_4+5 | 0 | 17 | 17 | 17 | 17 | 17
Sprint 4_6/7+8 | 6 | 29 | 23 | 19.7737 | 18.8022 | 23
Sprint 1_1+2 | 9.3927 | 40 | 28.6667 | 23.5058 | 22.0009 | 29
Sprint 1_3+4 | 8.1356 | 29 | 28.75 | 24.3447 | 23.0317 | 29
Sprint 1_5+6 | 11.8085 | 52 | 33.4 | 26.8544 | 24.9711 | 29
Sprint 2_1+2 | 10.8167 | 31 | 33 | 27.0564 | 25.3234 | 30
Sprint 2_3/4 | 9.8939 | 21 | 33.6667 | 28.2905 | 26.6964 | 30
Sprint 2_5/6 | 10.3118 | 25 | 33 | 27.3626 | 25.7062 | 30
Sprint 3_1/2 | 9.9163 | 28 | 31 | 25.5655 | 23.9746 | 28.5
Sprint 3_3/4 | 9.9233 | 34 | 31.8333 | 26.4096 | 24.8155 | 29.5
Sprint 3_5/6 | 7.946 | 46 | 30.8333 | 26.5649 | 25.2777 | 29.5

## KPIs HIL
| Initially Planned | [10 empty] | Pulled after Start
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 | 79 | 21 | 56 | 59 | 56 | 50 | 40 | 38 |  | 21 | Sprint_4_4 | 6 | 1 | 5 | 1 | 6 | 10 | 7 | 5 |  | 2
Sprint_4_5 | 57 | 13 | 39 | 51 | 76 | 40 | 46 | 34 | 29 | 28 | Sprint_4_5 | 6 | 11 | 19 | 0 | 3 | 11 | 8 | 8 | 6 | 2
Sprint_4_6 | 46 | 17 | 26 | 39 | 63 | 47 | 27 | 29 | 71 | 24.5 | Sprint_4_6 | 19 | 3 | 15 | 4 | 14 | 16 | 11 | 24 | 2 | 31.5
Sprint_4_8 | 65 | 17 | 29 | 34 | 49 | 42 | 22 | 27 | 53 | 28 | Sprint_4_8 | 37 | 3 | 3 | 14 | 0 | 15 | 4 | 0 | 1 | 7
Sprint_1_1 | 53 | 27 | 34 | 49 | 32 | 48 | 23 |  | 37 | 36 | Sprint_1_1 | 38 | 9 | 20 | 0 | 5 | 8 | 10 |  | 4 | 12
Sprint_1_2 | 48 | 28 | 54 | 38 | 35 | 45 | 40 |  | 31 | 37 | Sprint_1_2 | 5 | 19 | 4 | 5 | 6 | 5 | 0 |  | 9 | 19.5
Sprint_1_3 | 74 | 34 | 37 | 44 | 41 | 36 | 25 |  | 19 | 35 | Sprint_1_3 | 10 | 3 | 18 | 0 | 0 | 13 | 8 |  | 8 | 52
Sprint_1_4 | 58 | 26 | 52 | 36 | 36 | 35 | 34 |  | 32 | 38 | Sprint_1_4 | 6 | 11 | 4 | 21 | 6 | 4 | 8 |  | 8 | 27.5
Sprint_1_5 | 77 | 24 | 29 | 50 | 38 | 35 | 32 |  | 28 | 46 | Sprint_1_5 | 6 | 6 | 7 | 3 | 2 | 13 | 6 |  | 13 | 38
Sprint_1_6 | 66 | 36 | 37 | 40 | 46 | 36 | 23 |  | 37 | 31 | Sprint_1_6 | 16 | 9 | 19 | 6 | 6 | 20 | 3 |  | 5 | 28.5
Sprint_2_1 | 38 | 15 | 39 | 47 | 26 | 33 | 26 |  | 47 | 48 | Sprint_2_1 | 14 | 5 | 8 | 15 | 8 | 7 | 7 |  | 0 | 15
Sprint_2_2 | 41 | 13 | 46 | 39 | 36 | 36 | 21 |  | 50 | 60 | Sprint_2_2 | 2 | 13 | 11 | 9 | 1 | 8 | 2 |  | 9 | 16
Sprint_2_3u4 | 96 | 21 | 36 | 22 | 38 | 33 | 45 |  | 98 | 58 | Sprint_2_3u4 | 10 | 10 | 42 | 91 | 20 | 42 | 0 |  | 0 | 45
Sprint_2_5u6 | 104 | 20 | 68 | 52 | 52 | 59 | 43 |  | 81 | 77 | Sprint_2_5u6 | 20 | 10 | 56 | 24 | 19 | 28 | 19 |  | 91 | 33
Sprint_3_1u2 | 0 | 44 | 78 | 0 | 47 | 0 | 72 |  | 0 | 0 | Sprint_3_1u2 | 0 | 11 | 73 | 0 | 33 | 0 | 0 |  | 0 | 0
Sprint_3_3u4 | [10 empty] | Sprint_3_3u4
Sprint_3_5u6 | [10 empty] | Sprint_3_5u6
| Completed | [10 empty] | Removed | [10 empty] | Not Completed | [10 empty] | Completed Items
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 | 70 | 5 | 23 | 33 | 29 | 41 | 16 | 17 |  | 13 | Sprint_4_4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Sprint_4_4 | 13 | 14 | 38 | 27 | 33 | 19 | 31 | 26 |  | 10 | Sprint_4_4 | 18 | 4 | 5 | 7 | 9 | 16 | 5 |  | 0 | 5
Sprint_4_5 | 59 | 12 | 50 | 40 | 36 | 35 | 30 | 16 | 23 | 17 | Sprint_4_5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | Sprint_4_5 | 4 | 12 | 8 | 11 | 40 | 13 | 24 | 26 | 12 | 10 | Sprint_4_5 | 21 | 4 | 11 | 9 | 11 | 12 | 9 |  | 9 | 7
Sprint_4_6 | 37 | 20 | 33 | 18 | 51 | 38 | 30 | 32 | 30 | 37 | Sprint_4_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Sprint_4_6 | 28 | 0 | 8 | 25 | 26 | 25 | 8 | 21 | 43 | 17 | Sprint_4_6 | 15 | 11 | 13 | 5 | 18 | 12 | 14 |  | 7 | 15
Sprint_4_8 | 74 | 9 | 24 | 29 | 38 | 52 | 18 | 11 | 23 | 24 | Sprint_4_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Sprint_4_8 | 28 | 11 | 8 | 19 | 11 | 5 | 8 | 16 | 31 | 11 | Sprint_4_8 | 22 | 3 | 5 | 7 | 10 | 17 | 9 |  | 8 | 10
Sprint_1_1 | 75 | 10 | 37 | 27 | 29 | 37 | 22 |  | 17 | 23 | Sprint_1_1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 11 | 3 | Sprint_1_1 | 16 | 26 | 17 | 22 | 3 | 19 | 11 |  | 13 | 22 | Sprint_1_1 | 28 | 6 | 9 | 5 | 11 | 15 | 10 |  | 5 | 7
Sprint_1_2 | 38 | 30 | 45 | 35 | 26 | 47 | 29 |  | 29 | 41.5 | Sprint_1_2 | 0 | 5 | 5 | 0 | 0 | 0 | 0 |  | 0 | 1 | Sprint_1_2 | 15 | 12 | 8 | 8 | 15 | 3 | 11 |  | 11 | 15 | Sprint_1_2 | 17 | 15 | 11 | 11 | 9 | 16 | 6 |  | 7 | 15
Sprint_1_3 | 54 | 16 | 34 | 26 | 29 | 27 | 25 |  | 16 | 61 | Sprint_1_3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | Sprint_1_3 | 24 | 21 | 21 | 18 | 12 | 22 | 8 |  | 11 | 18 | Sprint_1_3 | 20 | 7 | 11 | 6 | 11 | 10 | 9 |  | 4 | 22
Sprint_1_4 | 27 | 13 | 56 | 38 | 33 | 23 | 34 |  | 29 | 44.5 | Sprint_1_4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | Sprint_1_4 | 37 | 16 | 0 | 19 | 9 | 16 | 8 |  | 11 | 16 | Sprint_1_4 | 8 | 6 | 10 | 9 | 9 | 9 | 10 |  | 7 | 18
Sprint_1_5 | 72 | 13 | 31 | 37 | 28 | 46 | 35 |  | 36 | 55.5 | Sprint_1_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | Sprint_1_5 | 11 | 17 | 5 | 16 | 12 | 2 | 3 |  | 5 | 26 | Sprint_1_5 | 15 | 6 | 8 | 12 | 10 | 12 | 11 |  | 12 | 17
Sprint_1_6 | 68 | 39 | 48 | 32 | 26 | 31 | 18 |  | 36 | 51 | Sprint_1_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint_1_6 | 14 | 6 | 8 | 14 | 26 | 25 | 8 |  | 6 | 21 | Sprint_1_6 | 19 | 11 | 15 | 8 | 9 | 10 | 8 |  | 12 | 16
Sprint_2_1 | 40 | 13 | 26 | 44 | 25 | 32 | 17 |  | 34 | 29 | Sprint_2_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint_2_1 | 12 | 7 | 21 | 18 | 9 | 8 | 16 |  | 13 | 34 | Sprint_2_1 | 17 | 7 | 8 | 11 | 7 | 9 | 6 |  | 11 | 10
Sprint_2_2 | 21 | 18 | 39 | 21 | 25 | 30 | 20 |  | 49 | 43 | Sprint_2_2 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint_2_2 | 22 | 8 | 10 | 27 | 12 | 14 | 3 |  | 10 | 33 | Sprint_2_2 | 8 | 8 | 10 | 6 | 10 | 9 | 7 |  | 18 | 16
Sprint_2_3u4 | 61 | 21 | 60 | 94 | 51 | 55 | 40 |  | 79 | 67 | Sprint_2_3u4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint_2_3u4 | 45 | 9 | 18 | 19 | 7 | 0 | 5 |  | 0 | 36 | Sprint_2_3u4 | 21 | 11 | 20 | 19 | 15 | 18 | 14 |  | 24 | 18
Sprint_2_5u6 | 83 | 25 | 81 | 52 | 47 | 63 | 43 |  | 151 | 59 | Sprint_2_5u6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint_2_5u6 | 41 | 3 | 43 | 24 | 24 | 24 | 19 |  | 21 | 51 | Sprint_2_5u6 | 23 | 11 | 27 | 13 | 17 | 20 | 20 |  | 79 | 17
Sprint_3_1u2 | 0 | 28 | 132 | 0 | 66 | 0 | 51 |  | 0 | 0 | Sprint_3_1u2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint_3_1u2 | 0 | 17 | 19 | 0 | 14 | 0 | 21 |  | 0 | 0 | Sprint_3_1u2 | 0 | 9 | 39 | 0 | 19 | 0 | 13 |  | 0 | 0
Sprint_3_3u4 | [10 empty] | Sprint_3_3u4 | [10 empty] | Sprint_3_3u4 | [10 empty] | Sprint_3_3u4
Sprint_3_5u6 | [10 empty] | Sprint_3_5u6 | [10 empty] | Sprint_3_5u6 | [10 empty] | Sprint_3_5u6
| Mittelwert | [10 empty] | Standardabweichung | [10 empty] | Mittlere Abweichung vom Mittelwert
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 - Sprint_4_6 | 55.3333 | 12.3333 | 35.3333 | 30.3333 | 38.6667 | 38 | 25.3333 | 21.6667 |  | 22.3333 | Sprint_4_4 - Sprint_4_6 | 13.7194 | 6.1283 | 11.1455 | 9.1773 | 9.1773 | 2.4495 | 6.5997 | 7.3182 |  | 10.4987 | Sprint_4_4 - Sprint_4_6 | 12.2222 | 5.1111 | 9.7778 | 8.2222 | 8.2222 | 2 | 6.2222 | 6.8889 |  | 9.7778
Sprint_4_5 - Sprint_4_8 | 60 | 11.5 | 32.5 | 30 | 38.5 | 41.5 | 23.5 |  | 25.3333 | 22.75 | Sprint_4_5 - Sprint_4_8 | 14.3701 | 5.5 | 10.8282 | 7.9687 | 7.953 | 6.4226 | 6.5383 | 7.8422 | 3.2998 | 9.1207 | Sprint_4_5 - Sprint_4_8 | 12 | 4.5 | 9 | 6.5 | 6.25 | 5.25 | 6.5 | 6.5 | 3.1111 | 7.75
Sprint_4_6 - Sprint_1_1 | 63 | 11.2 | 33.4 | 29.4 | 36.6 | 40.6 | 23.2 |  | 23.25 | 22.8 | Sprint_4_6 - Sprint_1_1 | 14.1845 | 4.9558 | 9.8509 | 7.2277 | 8.0647 | 6.02 | 5.8788 |  | 4.603 | 8.1584 | Sprint_4_6 - Sprint_1_1 | 12 | 3.84 | 8.08 | 5.68 | 6.32 | 4.72 | 5.44 |  | 3.375 | 6.24
Sprint_4_8 - Sprint_1_2 | 58.8333 | 14.3333 | 35.3333 | 30.3333 | 34.8333 | 41.6667 | 24.1667 |  | 24.4 | 25.9167 | Sprint_4_8 - Sprint_1_2 | 15.9522 | 8.34 | 9.9778 | 6.9202 | 8.355 | 5.9907 | 5.7855 |  | 4.7159 | 10.1997 | Sprint_4_8 - Sprint_1_2 | 14.2222 | 7.1111 | 8.6667 | 5.6667 | 6.8333 | 5.2222 | 5.5 |  | 4.08 | 8.8889
Sprint_1_1 - Sprint_1_3 | 56.1667 | 16.1667 | 37.1667 | 29.1667 | 34.8333 | 39.3333 | 25.6667 |  | 23 | 33.9167 | Sprint_1_1 - Sprint_1_3 | 15.1813 | 7.2207 | 8.4344 | 6.9622 | 8.355 | 8.1377 | 4.4969 |  | 5.3229 | 14.7434 | Sprint_1_1 - Sprint_1_3 | 13.1667 | 5.8889 | 6.8889 | 5.5556 | 6.8333 | 6.7778 | 4 |  | 4.3333 | 12.5833
Sprint_1_2 - Sprint_1_4 | 50.8333 | 16.3333 | 38.1667 | 28.8333 | 34.3333 | 37.3333 | 26.3333 |  | 24 | 38.5 | Sprint_1_2 - Sprint_1_4 | 18.506 | 7.1336 | 10.0899 | 6.4657 | 8.36 | 10.1762 | 5.3125 |  | 5.7735 | 12.9357 | Sprint_1_2 - Sprint_1_4 | 16.8333 | 5.7778 | 8.2222 | 5.1667 | 6.7778 | 8.3333 | 4.6667 |  | 5.3333 | 10.5
Sprint_1_3 - Sprint_1_5 | 56.6667 | 15.1667 | 37.8333 | 32 | 30.5 | 38.6667 | 27.1667 |  | 25 | 41.5833 | Sprint_1_3 - Sprint_1_5 | 18.7409 | 7.0099 | 10.2862 | 4.8305 | 3.9476 | 10.6875 | 6.1486 |  | 7.0946 | 14.3394 | Sprint_1_3 - Sprint_1_5 | 17 | 5.2222 | 8.4444 | 4.6667 | 3.3333 | 9.6667 | 5.5 |  | 6.3333 | 12.0833
Sprint_1_4 - Sprint_1_6 | 55.6667 | 20.1667 | 41.8333 | 32.5 | 28.5 | 35.1667 | 27.1667 |  | 27.1667 | 46.0833 | Sprint_1_4 - Sprint_1_6 | 17.932 | 10.6053 | 8.6683 | 4.6458 | 2.3629 | 9.0631 | 6.1486 |  | 8.0709 | 12.1909 | Sprint_1_4 - Sprint_1_6 | 16 | 9.5556 | 7.8333 | 4.1667 | 1.8333 | 8.1667 | 5.5 |  | 7.1111 | 9.75
Sprint_1_5 - Sprint_2_1 | 49.8333 | 20.6667 | 40 | 35.3333 | 27.8333 | 34.3333 | 26.3333 |  | 30 | 47.0833 | Sprint_1_5 - Sprint_2_1 | 16.3138 | 10.1762 | 10.4722 | 5.5277 | 2.6719 | 9.086 | 7.0632 |  | 6.9041 | 10.3659 | Sprint_1_5 - Sprint_2_1 | 14.8333 | 9.2222 | 9.6667 | 4.3333 | 2.1667 | 8.1111 | 6.3333 |  | 5.3333 | 8.75
Sprint_1_6 - Sprint_2_2 | 47 | 18.6667 | 39 | 33 | 27.6667 | 31.5 | 24.8333 |  | 33.3333 | 47.3333 | Sprint_1_6 - Sprint_2_2 | 19.3218 | 9.2856 | 10.2307 | 7.7028 | 2.8087 | 7.1356 | 7.2896 |  | 9.8263 | 10.2456 | Sprint_1_6 - Sprint_2_2 | 17.6667 | 6.7778 | 8.6667 | 6.6667 | 2.3333 | 5 | 6.5 |  | 7.2222 | 8.5
Sprint_2_1 - Sprint_2_3u4 | 48.1667 | 19.5 | 43.3333 | 44.3333 | 31.3333 | 36.1667 | 27.3333 |  | 43.8333 | 48.3333 | Sprint_2_1 - Sprint_2_3u4 | 19.9116 | 9.2331 | 12.4588 | 23.3 | 9.2135 | 10.8538 | 9.2316 |  | 16.8465 | 11.7177 | Sprint_2_1 - Sprint_2_3u4 | 18.8333 | 7 | 11.3333 | 16.5556 | 7.1111 | 9.5556 | 9 |  | 13.4444 | 9.5
Sprint_2_2 - Sprint_2_5u6 | 57.5 | 21.5 | 47.5 | 46.6667 | 33.6667 | 42.8333 | 28.8333 |  | 64.1667 | 50.75 | Sprint_2_2 - Sprint_2_5u6 | 20.9026 | 8.9022 | 18.6436 | 23.2499 | 10.9494 | 12.8247 | 10.7922 |  | 41.8068 | 12.1647 | Sprint_2_2 - Sprint_2_5u6 | 18 | 7 | 15.5 | 17.5556 | 10.2222 | 11.8333 | 10.5 |  | 33.8889 | 9.8333
Sprint_2_3u4 - Sprint_3_1u2 | 45.5 | 24 | 64.3333 | 40.5 | 40 | 35.1667 | 31.5 |  | 58.1667 | 41.5 | Sprint_2_3u4 - Sprint_3_1u2 | 28.4415 | 8.2462 | 34.7691 | 29.1533 | 15.7692 | 20.2437 | 13.5984 |  | 47.6005 | 22.0888 | Sprint_2_3u4 - Sprint_3_1u2 | 25.1667 | 6.6667 | 28.1111 | 22.8333 | 14.6667 | 15.8889 | 13.1667 |  | 37.8889 | 18
Sprint_2_5u6 - Sprint_3_3u4 | [10 empty] | Sprint_2_5u6 - Sprint_3_3u4 | [10 empty] | Sprint_2_5u6 - Sprint_3_3u4
Sprint_3_1u2 - Sprint_3_5u6 | [10 empty] | Sprint_3_1u2 - Sprint_3_5u6 | [10 empty] | Sprint_3_1u2 - Sprint_3_5u6
| TRULY AGILE Scope (Initially Planned + Pulled after Start - Removed) | [10 empty] | FAIRLY AGILE Scope (Initially Planned - Removed)
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 | 83 | 19 | 61 | 60 | 62 | 60 | 47 | 43 |  | 23 | Sprint_4_4 | 77 | 18 | 56 | 59 | 56 | 50 | 40 | 38 |  | 21
Sprint_4_5 | 63 | 24 | 58 | 51 | 76 | 48 | 54 | 42 | 35 | 30 | Sprint_4_5 | 57 | 13 | 39 | 51 | 73 | 37 | 46 | 34 | 29 | 28
Sprint_4_6 | 65 | 20 | 41 | 43 | 77 | 63 | 38 | 53 | 73 | 55 | Sprint_4_6 | 46 | 17 | 26 | 39 | 63 | 47 | 27 | 29 | 71 | 23.5
Sprint_4_8 | 102 | 20 | 32 | 48 | 49 | 57 | 26 | 27 | 54 | 34 | Sprint_4_8 | 65 | 17 | 29 | 34 | 49 | 42 | 22 | 27 | 53 | 27
Sprint_1_1 | 91 | 36 | 54 | 49 | 32 | 56 | 33 |  | 30 | 45 | Sprint_1_1 | 53 | 27 | 34 | 49 | 27 | 48 | 23 |  | 26 | 33
Sprint_1_2 | 53 | 42 | 53 | 43 | 41 | 50 | 40 |  | 40 | 55.5 | Sprint_1_2 | 48 | 23 | 49 | 38 | 35 | 45 | 40 |  | 31 | 36
Sprint_1_3 | 78 | 37 | 55 | 44 | 41 | 49 | 33 |  | 27 | 86 | Sprint_1_3 | 68 | 34 | 37 | 44 | 41 | 36 | 25 |  | 19 | 34
Sprint_1_4 | 64 | 29 | 56 | 57 | 42 | 39 | 42 |  | 40 | 64.5 | Sprint_1_4 | 58 | 18 | 52 | 36 | 36 | 35 | 34 |  | 32 | 37
Sprint_1_5 | 83 | 30 | 36 | 53 | 40 | 48 | 38 |  | 41 | 83 | Sprint_1_5 | 77 | 24 | 29 | 50 | 38 | 35 | 32 |  | 28 | 45
Sprint_1_6 | 82 | 45 | 56 | 46 | 52 | 56 | 26 |  | 42 | 59.5 | Sprint_1_6 | 66 | 36 | 37 | 40 | 46 | 36 | 23 |  | 37 | 31
Sprint_2_1 | 52 | 20 | 47 | 62 | 34 | 40 | 33 |  | 47 | 63 | Sprint_2_1 | 38 | 15 | 39 | 47 | 26 | 33 | 26 |  | 47 | 48
Sprint_2_2 | 43 | 26 | 49 | 48 | 37 | 44 | 23 |  | 59 | 76 | Sprint_2_2 | 41 | 13 | 38 | 39 | 36 | 36 | 21 |  | 50 | 60
Sprint_2_3u4 | 106 | 30 | 78 | 113 | 58 | 75 | 45 |  | 98 | 103 | Sprint_2_3u4 | 96 | 20 | 36 | 22 | 38 | 33 | 45 |  | 98 | 58
Sprint_2_5u6 | 124 | 28 | 124 | 76 | 71 | 87 | 62 |  | 172 | 110 | Sprint_2_5u6 | 104 | 18 | 68 | 52 | 52 | 59 | 43 |  | 81 | 77
Sprint_3_1u2 | 0 | 45 | 151 | 0 | 80 | 0 | 72 |  | 0 | 0 | Sprint_3_1u2 | 0 | 34 | 78 | 0 | 47 | 0 | 72 |  | 0 | 0
Sprint_3_3u4 | [10 empty] | Sprint_3_3u4
Sprint_3_5u6 | [10 empty] | Sprint_3_5u6
| SP Completed PSEUDO-4-weeks Sprints | [10 empty] | Mittelwert | [10 empty] | Standardabweichung
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint 2024-4-4+5 | 129 | 17 | 73 | 73 | 65 | 76 | 46 | 33 | 46 | 30 | Sprint 2024-4-4+5 | 129 | 17 | 73 | 73 | 65 | 76 | 46 | 33 | 46 | 30 | Sprint 2024-4-4+5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 2024-4-6/7+8 | 111 | 29 | 57 | 47 | 89 | 90 | 48 | 43 | 53 | 61 | Sprint 2024-4-6/7+8 | 120 | 23 | 65 | 60 | 77 | 83 | 47 | 38 | 49.5 | 45.5 | Sprint 2024-4-6/7+8 | 9 | 6 | 8 | 13 | 12 | 7 | 1 | 5 | 3.5 | 15.5
Sprint 2025-1-1+2 | 113 | 40 | 82 | 62 | 55 | 84 | 51 |  | 46 | 64.5 | Sprint 2025-1-1+2 | 117.6667 | 28.6667 | 70.6667 | 60.6667 | 69.6667 | 83.3333 | 48.3333 |  | 48.3333 | 51.8333 | Sprint 2025-1-1+2 | 8.0554 | 9.3927 | 10.3387 | 10.6562 | 14.2673 | 5.7349 | 2.0548 |  | 3.2998 | 15.5045
Sprint 2025-1-3+4 | 81 | 29 | 90 | 64 | 62 | 50 | 59 |  | 45 | 105.5 | Sprint 2025-1-3+4 | 108.5 | 28.75 | 75.5 | 61.5 | 67.75 | 75 | 51 |  | 47.5 | 65.25 | Sprint 2025-1-3+4 | 17.3421 | 8.1356 | 12.2577 | 9.3408 | 12.794 | 15.2643 | 4.9497 |  | 3.2016 | 26.8386
Sprint 2025-1-5+6 | 140 | 52 | 79 | 69 | 54 | 77 | 53 |  | 72 | 106.5 | Sprint 2025-1-5+6 | 114.8 | 33.4 | 76.2 | 63 | 65 | 75.4 | 51.4 |  | 52.4 | 73.5 | Sprint 2025-1-5+6 | 19.984 | 11.8085 | 11.0526 | 8.8769 | 12.6965 | 13.6763 | 4.4989 |  | 10.2098 | 29.129
Sprint 2025-2-1+2 | 61 | 31 | 65 | 65 | 50 | 62 | 37 |  | 83 | 72 | Sprint 2025-2-1+2 | 105.8333 | 33 | 74.3333 | 63.3333 | 62.5 | 73.1667 | 49 |  | 57.5 | 73.25 | Sprint 2025-2-1+2 | 27.1073 | 10.8167 | 10.9189 | 8.1377 | 12.8679 | 13.4464 | 6.7577 |  | 14.7281 | 26.5969
Sprint 2025-2-3/4 | 61 | 21 | 60 | 94 | 51 | 55 | 40 |  | 79 | 67 | Sprint 2025-2-3/4 | 94.5 | 33.6667 | 72.1667 | 66.8333 | 60.1667 | 69.6667 | 48 |  | 63 | 79.4167 | Sprint 2025-2-3/4 | 29.1876 | 9.8939 | 12.1849 | 13.9692 | 13.4588 | 14.9071 | 7.5277 |  | 15.5456 | 19.0819
Sprint 2025-2-5/6 | 83 | 25 | 81 | 52 | 47 | 63 | 43 |  | 151 | 59 | Sprint 2025-2-5/6 | 89.8333 | 33 | 76.1667 | 67.6667 | 53.1667 | 65.1667 | 47.1667 |  | 79.3333 | 79.0833 | Sprint 2025-2-5/6 | 28.4043 | 10.3118 | 10.3508 | 12.8668 | 4.7405 | 11.8521 | 7.7549 |  | 35.3396 | 19.4152
Sprint 2025-3-1/2 | 0 | 28 | 132 | 0 | 66 | 0 | 51 |  | 0 | 0 | Sprint 2025-3-1/2 | 71 | 31 | 84.5 | 57.3333 | 55 | 51.1667 | 47.1667 |  | 71.6667 | 68.3333 | Sprint 2025-3-1/2 | 41.3239 | 9.9163 | 23.4858 | 28.5754 | 6.7823 | 24.3544 | 7.7549 |  | 45.3199 | 35.6133
Sprint 2025-3-3/4 | 71 | 31 | 84.5 | 57.3333 | 55 | 51.1667 | 47.1667 |  | 71.6667 | 68.3333 | Sprint 2025-3-3/4 | 97.4111 | 32.1361 | 76.4778 | 63.2778 | 60.5972 | 68.2611 | 48.9556 |  | 61.9 | 73.1389 | Sprint 2025-3-3/4 | 27.2249 | 10.1471 | 13.3751 | 13.6278 | 10.5567 | 15.5834 | 6.5407 |  | 20.7241 | 26.1125
Sprint 2025-3-5/6 | 69.3333 | 31.3333 | 83.5833 | 56.2222 | 53.8333 | 51.3611 | 45.1944 |  | 76.1111 | 62.1389 | Sprint 2025-3-5/6 | 95.563 | 32.7005 | 76.6407 | 63.5741 | 59.4051 | 67.138 | 48.6148 |  | 64.3 | 74.4537 | Sprint 2025-3-5/6 | 28.872 | 10.4824 | 13.5614 | 14.3423 | 10.1838 | 15.6366 | 6.8058 |  | 23.6445 | 25.9915
| Items Completed PSEUDO-4-weeks Sprints | [10 empty] | Mittelwert | [10 empty] | Standardabweichung | [10 empty] | Durchschnittliche Komplexität
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint 2024-4-4+5 | 39 | 8 | 16 | 16 | 20 | 28 | 14 |  | 9 | 12 | Sprint 2024-4-4+5 | 39 | 8 | 16 | 16 | 20 | 28 | 14 |  | 9 | 12 | Sprint 2024-4-4+5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Sprint 2024-4-4+5 | 3.3077 | 2.125 | 4.5625 | 4.5625 | 3.25 | 2.7143 | 3.2857 |  | 5.1111 | 2.5
Sprint 2024-4-6/7+8 | 37 | 14 | 18 | 12 | 28 | 29 | 23 |  | 15 | 25 | Sprint 2024-4-6/7+8 | 38 | 11 | 17 | 14 | 24 | 28.5 | 18.5 |  | 12 | 18.5 | Sprint 2024-4-6/7+8 | 1 | 3 | 1 | 2 | 4 | 0.5 | 4.5 |  | 3 | 6.5 | Sprint 2024-4-6/7+8 | 3 | 2.0714 | 3.1667 | 3.9167 | 3.1786 | 3.1034 | 2.087 |  | 3.5333 | 2.44
Sprint 2025-1-1+2 | 45 | 21 | 20 | 16 | 20 | 31 | 16 |  | 12 | 22 | Sprint 2025-1-1+2 | 40.3333 | 14.3333 | 18 | 14.6667 | 22.6667 | 29.3333 | 17.6667 |  | 12 | 19.6667 | Sprint 2025-1-1+2 | 3.3993 | 5.3125 | 1.633 | 1.8856 | 3.7712 | 1.2472 | 3.8586 |  | 2.4495 | 5.5578 | Sprint 2025-1-1+2 | 2.5111 | 1.9048 | 4.1 | 3.875 | 2.75 | 2.7097 | 3.1875 |  | 3.8333 | 2.9318
Sprint 2025-1-3+4 | 28 | 13 | 21 | 15 | 20 | 19 | 19 |  | 11 | 40 | Sprint 2025-1-3+4 | 37.25 | 14 | 18.75 | 14.75 | 22 | 26.75 | 18 |  | 11.75 | 24.75 | Sprint 2025-1-3+4 | 6.0982 | 4.6368 | 1.9203 | 1.6394 | 3.4641 | 4.603 | 3.3912 |  | 2.1651 | 10.0343 | Sprint 2025-1-3+4 | 2.8929 | 2.2308 | 4.2857 | 4.2667 | 3.1 | 2.6316 | 3.1053 |  | 4.0909 | 2.6375
Sprint 2025-1-5+6 | 34 | 17 | 23 | 20 | 19 | 22 | 19 |  | 24 | 33 | Sprint 2025-1-5+6 | 36.6 | 14.6 | 19.6 | 15.8 | 21.4 | 25.8 | 18.2 |  | 14.2 | 26.4 | Sprint 2025-1-5+6 | 5.6071 | 4.3174 | 2.4166 | 2.5612 | 3.3226 | 4.5343 | 3.0594 |  | 5.2688 | 9.5624 | Sprint 2025-1-5+6 | 4.1176 | 3.0588 | 3.4348 | 3.45 | 2.8421 | 3.5 | 2.7895 |  | 3 | 3.2273
Sprint 2025-2-1+2 | 25 | 15 | 18 | 17 | 17 | 18 | 13 |  | 29 | 26 | Sprint 2025-2-1+2 | 34.6667 | 14.6667 | 19.3333 | 16 | 20.6667 | 24.5 | 17.3333 |  | 16.6667 | 26.3333 | Sprint 2025-2-1+2 | 6.6999 | 3.9441 | 2.2852 | 2.3805 | 3.448 | 5.058 | 3.3993 |  | 7.3182 | 8.7305 | Sprint 2025-2-1+2 | 2.44 | 2.0667 | 3.6111 | 3.8235 | 2.9412 | 3.4444 | 2.8462 |  | 2.8621 | 2.7692
Sprint 2025-2-3/4 | 21 | 11 | 20 | 19 | 15 | 18 | 14 |  | 24 | 18 | Sprint 2025-2-3/4 | 31.6667 | 15.1667 | 20 | 16.5 | 19.8333 | 22.8333 | 17.3333 |  | 19.1667 | 27.3333 | Sprint 2025-2-3/4 | 7.9931 | 3.1842 | 1.7321 | 2.63 | 4.0586 | 5.2731 | 3.3993 |  | 6.8171 | 7.2495 | Sprint 2025-2-3/4 | 2.9048 | 1.9091 | 3 | 4.9474 | 3.4 | 3.0556 | 2.8571 |  | 3.2917 | 3.7222
Sprint 2025-2-5/6 | 23 | 11 | 27 | 13 | 17 | 20 | 20 |  | 79 | 17 | Sprint 2025-2-5/6 | 29.3333 | 14.6667 | 21.5 | 16.6667 | 18 | 21.3333 | 16.8333 |  | 29.8333 | 26 | Sprint 2025-2-5/6 | 8.1377 | 3.5434 | 2.8723 | 2.357 | 1.8257 | 4.5338 | 2.6719 |  | 22.945 | 8.226 | Sprint 2025-2-5/6 | 3.6087 | 2.2727 | 3 | 4 | 2.7647 | 3.15 | 2.15 |  | 1.9114 | 3.4706
Sprint 2025-3-1/2 | 0 | 9 | 39 | 0 | 19 | 0 | 13 |  | 0 | 0 | Sprint 2025-3-1/2 | 21.8333 | 12.6667 | 24.6667 | 14 | 17.8333 | 16.1667 | 16.3333 |  | 27.8333 | 22.3333 | Sprint 2025-3-1/2 | 10.6053 | 2.6874 | 6.9921 | 6.6833 | 1.675 | 7.3579 | 3.0368 |  | 24.8557 | 12.8149 | Sprint 2025-3-1/2 | #DIV/0! | 3.1111 | 3.3846 | #DIV/0! | 3.4737 | #DIV/0! | 3.9231 |  | #DIV/0! | #DIV/0!
Sprint 2025-3-3/4 | 21.8333 | 12.6667 | 24.6667 | 14 | 17.8333 | 16.1667 | 16.3333 |  | 27.8333 | 22.3333 | Sprint 2025-3-3/4 | 31.8917 | 14.2944 | 20.6417 | 15.6194 | 19.9556 | 22.8972 | 17.3389 |  | 19.9083 | 25.525 | Sprint 2025-3-3/4 | 7.5235 | 3.7189 | 3.0364 | 3.0419 | 2.9657 | 5.2267 | 3.1597 |  | 11.5616 | 9.4363 | Sprint 2025-3-3/4 | 3.2519 | 2.4474 | 3.4257 | 4.0952 | 3.0841 | 3.1649 | 2.8878 |  | 2.5749 | 3.0597
Sprint 2025-3-5/6 | 20.8056 | 12.6111 | 25.2778 | 13.8333 | 17.4722 | 15.6944 | 15.8889 |  | 30.6389 | 19.3889 | Sprint 2025-3-5/6 | 30.9986 | 14.3435 | 20.9569 | 15.7644 | 19.6148 | 22.2551 | 17.2287 |  | 21.2681 | 25.6542 | Sprint 2025-3-5/6 | 7.7611 | 3.5659 | 3.2224 | 3.2757 | 2.8826 | 5.3306 | 3.1211 |  | 13.1277 | 9.3366 | Sprint 2025-3-5/6 | 3.3324 | 2.4846 | 3.3066 | 4.0643 | 3.0811 | 3.2726 | 2.8444 |  | 2.4841 | 3.2049
| 95% Success Rate Velocity | [10 empty] | 95% Success Rate item Count | [10 empty] | Correlation Velocity VS item Count
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint 2024-4-4+5 | 129 | 17 | 73 | 73 | 65 | 76 | 46 |  | 46 | 30 | Sprint 2024-4-4+5 | 39 | 8 | 16 | 16 | 20 | 28 | 14 |  | 9 | 12 | Sprint 2024-4-4+5
Sprint 2024-4-6/7+8 | 115.4123 | 19.7737 | 60.8687 | 53.1037 | 70.746 | 79.4229 | 46.4973 |  | 47.7179 | 36.9459 | Sprint 2024-4-6/7+8 | 37.4967 | 9.3808 | 16.4924 | 12.9615 | 21.9089 | 28.2489 | 16.0935 |  | 10.3923 | 14.8997 | Sprint 2024-4-6/7+8 | 1 | 1 | -1 | 1 | 1 | 1 | 1 |  | 1 | 1
Sprint 2025-1-1+2 | 113.5676 | 23.5058 | 65.293 | 55.0814 | 62.1248 | 80.4148 | 47.2948 |  | 46.6543 | 43.3941 | Sprint 2025-1-1+2 | 38.5963 | 11.371 | 17.1641 | 13.6914 | 20.6953 | 28.703 | 15.6187 |  | 10.7054 | 16.6576 | Sprint 2025-1-1+2 | 0.62599 | 0.99982 | -0.55628 | 0.98996 | 0.76369 | 0.8894 | 0.64125 |  | 0.67217 | 0.99291
Sprint 2025-1-3+4 | 99.4516 | 24.3447 | 69.0999 | 56.6374 | 61.0186 | 66.9341 | 48.462 |  | 45.8713 | 50.0634 | Sprint 2025-1-3+4 | 34.0647 | 11.4492 | 17.7639 | 13.9062 | 20.1938 | 24.3399 | 16.216 |  | 10.6124 | 19.0844 | Sprint 2025-1-3+4 | 0.88942 | 0.99667 | -0.12701 | 0.98644 | 0.80125 | 0.981 | 0.69543 |  | 0.32664 | 0.99704
Sprint 2025-1-5+6 | 104.3306 | 26.8544 | 70.4573 | 58.3931 | 58.3072 | 68.22 | 49.0991 |  | 47.0188 | 57.1075 | Sprint 2025-1-5+6 | 33.6799 | 12.2526 | 18.352 | 14.4628 | 19.6686 | 23.4234 | 16.6 |  | 11.2616 | 21.0835 | Sprint 2025-1-5+6 | 0.8804 | 0.99145 | 0.14126 | 0.96912 | 0.8611 | 0.96341 | 0.7769 |  | 0.41246 | 0.99762
Sprint 2025-2-1+2 | 91.2789 | 27.0564 | 68.6572 | 59.1246 | 55.6956 | 66.1024 | 45.4958 |  | 49.5922 | 58.458 | Sprint 2025-2-1+2 | 31.137 | 12.5405 | 18.1548 | 14.7619 | 18.864 | 21.825 | 15.541 |  | 12.4823 | 21.53 | Sprint 2025-2-1+2 | 0.932 | 0.99327 | 0.16476 | 0.94429 | 0.91317 | 0.95895 | 0.67895 |  | 0.78655 | 0.99813
Sprint 2025-2-3/4 | 78.5622 | 28.2905 | 65.7927 | 59.4398 | 53.0119 | 61.765 | 44.0757 |  | 54.6775 | 69.2213 | Sprint 2025-2-3/4 | 27.38 | 13.4809 | 19.1144 | 15.128 | 17.688 | 20.024 | 15.541 |  | 15.3851 | 23.4298 | Sprint 2025-2-3/4 | 0.98081 | 0.98584 | 0.62318 | 0.9837 | 0.96946 | 0.97496 | 0.82556 |  | 0.96893 | 0.99062
Sprint 2025-2-5/6 | 74.2858 | 27.3626 | 70.8024 | 60.8943 | 50.7411 | 58.9435 | 43.1152 |  | 59.0776 | 68.6932 | Sprint 2025-2-5/6 | 24.9347 | 12.7727 | 20.0124 | 15.4433 | 17.0627 | 18.9312 | 15.4397 |  | 14.3354 | 21.4971 | Sprint 2025-2-5/6 | 0.98675 | 0.96008 | 0.44758 | 0.97768 | 0.9945 | 0.97512 | 0.86137 |  | 0.9019 | 0.92576
Sprint 2025-3-1/2 | 45.9021 | 25.5655 | 71.8032 | 40.6052 | 51.4973 | 37.0391 | 43.1152 |  | 43.4533 | 47.285 | Sprint 2025-3-1/2 | 15.6571 | 11.2429 | 20.88 | 10.1209 | 16.9752 | 11.9335 | 14.7369 |  | 9.1037 | 14.58 | Sprint 2025-3-1/2 | 0.99357 | 0.92761 | 0.45721 | 0.99502 | 0.98918 | 0.97781 | 0.91811 |  | 0.91967 | 0.84489
Sprint 2025-3-3/4 | 82.6857 | 26.5827 | 69.4691 | 56.0512 | 55.0665 | 59.9653 | 45.568 |  | 50.4855 | 58.6469 | Sprint 2025-3-3/4 | 27.8772 | 12.2952 | 19.0631 | 14.0162 | 18.4131 | 20.1148 | 15.6797 |  | 12.8907 | 20.2649 | Sprint 2025-3-3/4 | 0.99382 | 0.99205 | 0.48866 | 0.99718 | 0.99151 | 0.99304 | 0.90876 |  | 0.90585 | 0.86962
Sprint 2025-3-5/6 | 79.8322 | 26.9544 | 69.5302 | 55.9452 | 54.074 | 58.8022 | 45.0837 |  | 51.1287 | 60.0682 | Sprint 2025-3-5/6 | 26.839 | 12.4334 | 19.2785 | 14.0313 | 18.1163 | 19.4076 | 15.5903 |  | 13.1579 | 20.46 | Sprint 2025-3-5/6 | 0.99745 | 0.99412 | 0.66026 | 0.99848 | 0.98312 | 0.99631 | 0.6989 |  | 0.89332 | 0.90538

## KPIs IDL
| Initially Planned | [11 empty] | Pulled after Start
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 | 79 | 13 | 56 | 59 | 56 | 50 | 40 | 38 |  | 21 |  | Sprint_4_4 | 6 | 1 | 5 | 1 | 6 | 10 | 7 | 5 |  | 2
Sprint_4_5 | 57 | 10 | 39 | 40 | 76 | 40 | 46 | 6 | 29 | 22 |  | Sprint_4_5 | 6 | 10 | 19 | 0 | 3 | 11 | 8 | 8 | 6 | 2
Sprint_4_6 | 46 | 11 | 22 | 31 | 50 | 47 | 27 | 29 | 71 | 20.5 |  | Sprint_4_6 | 19 | 3 | 15 | 4 | 9 | 16 | 11 | 24 | 2 | 31.5
Sprint_4_8 | 65 | 17 | 29 | 28 | 42 | 42 | 17 | 27 | 53 | 28 |  | Sprint_4_8 | 37 | 3 | 3 | 14 | 0 | 15 | 4 | 0 | 1 | 7
Sprint_1_1 | 53 | 11 | 34 | 38 | 32 | 48 | 18 |  | 32 | 36 |  | Sprint_1_1 | 38 | 9 | 20 | 0 | 5 | 8 | 10 |  | 4 | 12
Sprint_1_2 | 48 | 13 | 54 | 26 | 35 | 45 | 27 |  | 31 | 37 |  | Sprint_1_2 | 5 | 19 | 4 | 5 | 6 | 5 | 0 |  | 9 | 19.5
Sprint_1_3 | 74 | 21 | 37 | 41 | 41 | 36 | 23 |  | 19 | 35 |  | Sprint_1_3 | 10 | 3 | 18 | 0 | 0 | 13 | 8 |  | 8 | 52
Sprint_1_4 | 58 | 16 | 52 | 26 | 36 | 29 | 30 |  | 27 | 38 |  | Sprint_1_4 | 6 | 11 | 4 | 21 | 6 | 4 | 8 |  | 8 | 27.5
Sprint_1_5 | 77 | 13 | 29 | 44 | 38 | 27 | 29 |  | 26 | 28 |  | Sprint_1_5 | 6 | 6 | 7 | 3 | 2 | 9 | 6 |  | 13 | 38
Sprint_1_6 | 66 | 15 | 33 | 29 | 31 | 36 | 21 |  | 36 | 21 |  | Sprint_1_6 | 16 | 9 | 19 | 6 | 6 | 20 | 3 |  | 5 | 46
Sprint_2_1 | 38 | 15 | 39 | 36 | 15 | 27 | 24 |  | 47 | 41 |  | Sprint_2_1 | 14 | 5 | 8 | 15 | 8 | 7 | 7 |  | 0 | 15
Sprint_2_2 | 41 | 13 | 46 | 25 | 33 | 34 | 21 |  | 50 | 43 |  | Sprint_2_2 | 2 | 13 | 11 | 5 | 1 | 8 | 2 |  | 9 | 16
Sprint_2_3u4 | 96 | 18 | 36 | 22 | 33 | 33 | 45 |  | 98 | 58 |  | Sprint_2_3u4 | 10 | 12 | 42 | 78 | 20 | 42 | 0 |  | 0 | 45
Sprint_2_5u6 | 104 | 18 | 57 | 52 | 45 | 59 | 43 |  | 81 | 77 |  | Sprint_2_5u6 | 20 | 12 | 56 | 24 | 19 | 29 | 19 |  | 91 | 33
Sprint_3_1u2 | 0 | 38 | 78 | 0 | 37 | 0 | 62 |  | 0 | 0 |  | Sprint_3_1u2 | 0 | 11 | 73 | 0 | 33 | 0 | 0 |  | 0 | 0
Sprint_3_3u4 | [11 empty] | Sprint_3_3u4
Sprint_3_5u6 | [11 empty] | Sprint_3_5u6
| Completed | [11 empty] | Removed | [11 empty] | Not Completed
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 | 70 | 7 | 23 | 50 | 29 | 41 | 16 | 17 |  | 16 |  | Sprint_4_4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Sprint_4_4 | 13 | 4 | 38 | 10 | 33 | 19 | 31 | 26 |  | 7
Sprint_4_5 | 59 | 11 | 50 | 29 | 36 | 34 | 30 | 11 | 24 | 19 |  | Sprint_4_5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 |  | Sprint_4_5 | 4 | 9 | 8 | 11 | 40 | 14 | 24 | 3 | 11 | 5
Sprint_4_6 | 37 | 14 | 34 | 18 | 56 | 38 | 32 | 37 | 58 | 37 |  | Sprint_4_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | Sprint_4_6 | 28 | 0 | 3 | 17 | 3 | 25 | 6 | 16 | 15 | 13
Sprint_4_8 | 74 | 9 | 24 | 34 | 40 | 52 | 18 | 11 | 34 | 32 |  | Sprint_4_8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Sprint_4_8 | 28 | 11 | 8 | 8 | 2 | 5 | 3 | 16 | 20 | 3
Sprint_1_1 | 75 | 9 | 37 | 28 | 29 | 39 | 25 |  | 24 | 23 |  | Sprint_1_1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 6 | 3 |  | Sprint_1_1 | 16 | 11 | 17 | 10 | 3 | 17 | 3 |  | 6 | 22
Sprint_1_2 | 38 | 21 | 45 | 26 | 26 | 49 | 16 |  | 31 | 41.5 |  | Sprint_1_2 | 0 | 5 | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_1_2 | 15 | 6 | 8 | 5 | 15 | 1 | 11 |  | 9 | 15
Sprint_1_3 | 54 | 13 | 34 | 33 | 29 | 34 | 27 |  | 21 | 61 |  | Sprint_1_3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8 |  | Sprint_1_3 | 24 | 11 | 21 | 8 | 12 | 15 | 4 |  | 6 | 18
Sprint_1_4 | 27 | 14 | 56 | 33 | 38 | 27 | 33 |  | 26 | 44.5 |  | Sprint_1_4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5 |  | Sprint_1_4 | 37 | 5 | 0 | 14 | 4 | 6 | 5 |  | 9 | 16
Sprint_1_5 | 72 | 13 | 35 | 42 | 34 | 35 | 32 |  | 36 | 53 |  | Sprint_1_5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_1_5 | 11 | 6 | 1 | 5 | 6 | 1 | 3 |  | 3 | 13
Sprint_1_6 | 68 | 18 | 47 | 28 | 32 | 31 | 19 |  | 36 | 55 |  | Sprint_1_6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_1_6 | 14 | 6 | 5 | 7 | 5 | 25 | 5 |  | 5 | 12
Sprint_2_1 | 40 | 13 | 37 | 40 | 13 | 28 | 19 |  | 37 | 41.5 |  | Sprint_2_1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_2_1 | 12 | 7 | 10 | 11 | 10 | 6 | 12 |  | 10 | 12.5
Sprint_2_2 | 21 | 21 | 42 | 16 | 24 | 33 | 22 |  | 52 | 40 |  | Sprint_2_2 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_2_2 | 22 | 5 | 7 | 14 | 10 | 9 | 1 |  | 7 | 7
Sprint_2_3u4 | 61 | 20 | 71 | 92 | 49 | 61 | 42 |  | 83 | 85.5 |  | Sprint_2_3u4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_2_3u4 | 45 | 9 | 7 | 8 | 4 | 14 | 3 |  | 15 | 17.5
Sprint_2_5u6 | 83 | 26 | 80 | 65 | 50 | 64 | 53 |  | 151 | 97 |  | Sprint_2_5u6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_2_5u6 | 41 | 2 | 33 | 11 | 14 | 24 | 9 |  | 21 | 13
Sprint_3_1u2 | 0 | 26 | 132 | 0 | 56 | 0 | 41 |  | 0 | 0 |  | Sprint_3_1u2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | Sprint_3_1u2 | 0 | 17 | 19 | 0 | 14 | 0 | 21 |  | 0 | 0
Sprint_3_3u4 | [11 empty] | Sprint_3_3u4 | [11 empty] | Sprint_3_3u4
Sprint_3_5u6 | [11 empty] | Sprint_3_5u6 | [11 empty] | Sprint_3_5u6
| Mittelwert | [11 empty] | Standardabweichung | [11 empty] | Mittlere Abweichung vom Mittelwert
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 - Sprint_4_6 | 55.3333 | 10.6667 | 35.6667 | 32.3333 | 40.3333 | 37.6667 | 26 | 21.6667 |  | 24 |  | Sprint_4_4 - Sprint_4_6 | 13.7194 | 2.8674 | 11.0855 | 13.2749 | 11.4407 | 2.8674 | 7.1181 | 11.1156 |  | 9.2736 |  | Sprint_4_4 - Sprint_4_6 | 12.2222 | 2.4444 | 9.5556 | 11.7778 | 10.4444 | 2.4444 | 6.6667 | 10.2222 |  | 8.6667
Sprint_4_5 - Sprint_4_8 | 60 | 10.25 | 32.75 | 32.75 | 40.25 | 41.25 | 24 |  | 38.6667 | 26 |  | Sprint_4_5 - Sprint_4_8 | 14.3701 | 2.586 | 10.8484 | 11.519 | 9.909 | 6.6849 | 7.0711 | 10.6771 | 14.2673 | 8.7464 |  | Sprint_4_5 - Sprint_4_8 | 12 | 2.25 | 9.25 | 9.25 | 7.875 | 5.375 | 7 | 9 | 12.8889 | 8.5
Sprint_4_6 - Sprint_1_1 | 63 | 10 | 33.6 | 31.8 | 38 | 40.8 | 24.2 |  | 35 | 25.4 |  | Sprint_4_6 - Sprint_1_1 | 14.1845 | 2.3664 | 9.8509 | 10.4766 | 9.9398 | 6.0465 | 6.3372 |  | 13.8924 | 7.9145 |  | Sprint_4_6 - Sprint_1_1 | 12 | 2 | 8.08 | 8.16 | 8 | 4.56 | 5.76 |  | 11.5 | 7.28
Sprint_4_8 - Sprint_1_2 | 58.8333 | 11.8333 | 35.5 | 30.8333 | 36 | 42.1667 | 22.8333 |  | 34.2 | 28.0833 |  | Sprint_4_8 - Sprint_1_2 | 15.9522 | 4.6338 | 9.9457 | 9.805 | 10.116 | 6.3092 | 6.5426 |  | 12.5284 | 9.3916 |  | Sprint_4_8 - Sprint_1_2 | 14.2222 | 3.7778 | 8.5 | 7.4444 | 8 | 5.5556 | 6.1667 |  | 9.52 | 8.75
Sprint_1_1 - Sprint_1_3 | 56.1667 | 12.8333 | 37.3333 | 28 | 36 | 41 | 24.6667 |  | 32 | 35.5833 |  | Sprint_1_1 - Sprint_1_3 | 15.1813 | 4.0995 | 8.36 | 5.2599 | 10.116 | 7.0238 | 5.8784 |  | 12.4499 | 13.7187 |  | Sprint_1_1 - Sprint_1_3 | 13.1667 | 3.1667 | 6.7778 | 4 | 8 | 6.3333 | 5.1111 |  | 9.3333 | 10.9167
Sprint_1_2 - Sprint_1_4 | 50.8333 | 13.3333 | 38.3333 | 28.6667 | 36.3333 | 39.8333 | 25.1667 |  | 32.3333 | 39.8333 |  | Sprint_1_2 - Sprint_1_4 | 18.506 | 4.0277 | 10.0111 | 5.5877 | 10.1434 | 8.5131 | 6.414 |  | 12.2565 | 11.7284 |  | Sprint_1_2 - Sprint_1_4 | 16.8333 | 3 | 8.1111 | 4.6667 | 8.3333 | 7.1111 | 5.5 |  | 9.1111 | 9.1667
Sprint_1_3 - Sprint_1_5 | 56.6667 | 13.1667 | 38.5 | 32.6667 | 32.6667 | 39.3333 | 25.1667 |  | 28.6667 | 42.5 |  | Sprint_1_3 - Sprint_1_5 | 18.7409 | 4.0173 | 9.9457 | 5.0881 | 5.0881 | 8.6923 | 6.414 |  | 5.4058 | 12.5698 |  | Sprint_1_3 - Sprint_1_5 | 17 | 2.8889 | 8 | 3.7778 | 4.6667 | 7.4444 | 5.5 |  | 5 | 10.3333
Sprint_1_4 - Sprint_1_6 | 55.6667 | 14.6667 | 42.3333 | 31.6667 | 31.3333 | 35.8333 | 25.3333 |  | 29 | 46.3333 |  | Sprint_1_4 - Sprint_1_6 | 17.932 | 3.8586 | 7.8245 | 5.3125 | 3.9016 | 6.9382 | 6.2361 |  | 5.7735 | 12.2871 |  | Sprint_1_4 - Sprint_1_6 | 16 | 3.2222 | 7 | 4.3333 | 3.3333 | 5.4444 | 5.3333 |  | 5.3333 | 10
Sprint_1_5 - Sprint_2_1 | 49.8333 | 15.3333 | 42.3333 | 33.6667 | 28.6667 | 34 | 24.3333 |  | 31.1667 | 49.4167 |  | Sprint_1_5 - Sprint_2_1 | 16.3138 | 3.0912 | 7.8245 | 5.7927 | 7.9512 | 7.303 | 6.675 |  | 5.9278 | 7.3904 |  | Sprint_1_5 - Sprint_2_1 | 14.8333 | 2.7778 | 7 | 4.8889 | 6.1111 | 5.3333 | 6.3333 |  | 5.1667 | 6.9167
Sprint_1_6 - Sprint_2_2 | 47 | 15.3333 | 41.8333 | 32 | 28.3333 | 31.3333 | 25.3333 |  | 34.6667 | 49.1667 |  | Sprint_1_6 - Sprint_2_2 | 19.3218 | 3.0912 | 7.7334 | 8.544 | 8.0966 | 2.9814 | 5.7349 |  | 9.7582 | 7.6739 |  | Sprint_1_6 - Sprint_2_2 | 17.6667 | 2.7778 | 6.5 | 6.6667 | 6.5556 | 2.6667 | 5.3333 |  | 7.4444 | 7.1667
Sprint_2_1 - Sprint_2_3u4 | 48.1667 | 16.5 | 48 | 41.8333 | 31.6667 | 35.8333 | 27.8333 |  | 45 | 53.25 |  | Sprint_2_1 - Sprint_2_3u4 | 19.9116 | 3.304 | 12.3828 | 24.0029 | 11.2052 | 11.5818 | 8.5131 |  | 18.619 | 15.4563 |  | Sprint_2_1 - Sprint_2_3u4 | 18.8333 | 3.1667 | 10.3333 | 16.7778 | 8.7778 | 8.3889 | 7.8333 |  | 15 | 11.3333
Sprint_2_2 - Sprint_2_5u6 | 57.5 | 18.5 | 52 | 47.1667 | 33.6667 | 42 | 31.1667 |  | 65.8333 | 62 |  | Sprint_2_2 - Sprint_2_5u6 | 20.9026 | 4.5735 | 17.2434 | 24.9828 | 13.0724 | 14.6742 | 12.7465 |  | 41.5348 | 21.6468 |  | Sprint_2_2 - Sprint_2_5u6 | 18 | 3.8333 | 15.6667 | 20.8889 | 10.6667 | 13.6667 | 11.1667 |  | 34.1111 | 19.5
Sprint_2_3u4 - Sprint_3_1u2 | 45.5 | 20.6667 | 68.1667 | 40.1667 | 37.3333 | 36.1667 | 32.6667 |  | 59.8333 | 53.1667 |  | Sprint_2_3u4 - Sprint_3_1u2 | 28.4415 | 4.5338 | 32.4726 | 30.6834 | 15.5099 | 21.6134 | 13.2749 |  | 47.5725 | 31.9018 |  | Sprint_2_3u4 - Sprint_3_1u2 | 25.1667 | 3.6667 | 26.1667 | 25.5556 | 14.3333 | 17.5556 | 12.6667 |  | 38.1111 | 26
Sprint_2_5u6 - Sprint_3_3u4 | [11 empty] | Sprint_2_5u6 - Sprint_3_3u4 | [11 empty] | Sprint_2_5u6 - Sprint_3_3u4
Sprint_3_1u2 - Sprint_3_5u6 | [11 empty] | Sprint_3_1u2 - Sprint_3_5u6 | [11 empty] | Sprint_3_1u2 - Sprint_3_5u6
| TRULY AGILE Scope (Initially Planned + Pulled after Start - Removed) | [11 empty] | FAIRLY AGILE Scope (Initially Planned - Removed) | [11 empty] | Completed PSEUDO-4-weeks Sprints
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_4_4 | 83 | 11 | 61 | 60 | 62 | 60 | 47 | 43 |  | 23 |  | Sprint_4_4 | 77 | 10 | 56 | 59 | 56 | 50 | 40 | 38 |  | 21 |  | Sprint_4_4+Sprint_4_5 | 129 | 18 | 73 | 79 | 65 | 75 | 46 | 28 | 48 | 35
Sprint_4_5 | 63 | 20 | 58 | 40 | 76 | 48 | 54 | 14 | 35 | 24 |  | Sprint_4_5 | 57 | 10 | 39 | 40 | 73 | 37 | 46 | 6 | 29 | 22 |  | Sprint_4_6+Sprint_4_8 | 111 | 23 | 58 | 52 | 96 | 90 | 50 | 48 | 92 | 69
Sprint_4_6 | 65 | 14 | 37 | 35 | 59 | 63 | 38 | 53 | 73 | 50 |  | Sprint_4_6 | 46 | 11 | 22 | 31 | 50 | 47 | 27 | 29 | 71 | 18.5 |  | Sprint_1_1+Sprint_1_2 | 113 | 30 | 82 | 54 | 55 | 88 | 41 |  | 55 | 64.5
Sprint_4_8 | 102 | 20 | 32 | 42 | 42 | 57 | 21 | 27 | 54 | 35 |  | Sprint_4_8 | 65 | 17 | 29 | 28 | 42 | 42 | 17 | 27 | 53 | 28 |  | Sprint_1_3+Sprint_1_4 | 81 | 27 | 90 | 66 | 67 | 61 | 60 |  | 47 | 105.5
Sprint_1_1 | 91 | 20 | 54 | 38 | 32 | 56 | 28 |  | 30 | 45 |  | Sprint_1_1 | 53 | 11 | 34 | 38 | 27 | 48 | 18 |  | 26 | 33 |  | Sprint_1_5+Sprint_1_6 | 140 | 31 | 82 | 70 | 66 | 66 | 51 |  | 72 | 108
Sprint_1_2 | 53 | 27 | 53 | 31 | 41 | 50 | 27 |  | 40 | 56.5 |  | Sprint_1_2 | 48 | 8 | 49 | 26 | 35 | 45 | 27 |  | 31 | 37 |  | Sprint_2_1+Sprint_2_2 | 61 | 34 | 79 | 56 | 37 | 61 | 41 |  | 89 | 81.5
Sprint_1_3 | 78 | 24 | 55 | 41 | 41 | 49 | 31 |  | 27 | 79 |  | Sprint_1_3 | 68 | 21 | 37 | 41 | 41 | 36 | 23 |  | 19 | 27 |  | Sprint_2_3u4 | 61 | 20 | 71 | 92 | 49 | 61 | 42 |  | 83 | 85.5
Sprint_1_4 | 64 | 19 | 56 | 47 | 42 | 33 | 38 |  | 35 | 60.5 |  | Sprint_1_4 | 58 | 8 | 52 | 26 | 36 | 29 | 30 |  | 27 | 33 |  | Sprint_2_5u6 | 83 | 26 | 80 | 65 | 50 | 64 | 53 |  | 151 | 97
Sprint_1_5 | 83 | 19 | 36 | 47 | 40 | 36 | 35 |  | 39 | 66 |  | Sprint_1_5 | 77 | 13 | 29 | 44 | 38 | 27 | 29 |  | 26 | 28 |  | Sprint_3_1u2 | 0 | 26 | 132 | 0 | 56 | 0 | 41 |  | 0 | 0
Sprint_1_6 | 82 | 24 | 52 | 35 | 37 | 56 | 24 |  | 41 | 67 |  | Sprint_1_6 | 66 | 15 | 33 | 29 | 31 | 36 | 21 |  | 36 | 21 |  | Sprint_3_3u4
Sprint_2_1 | 52 | 20 | 47 | 51 | 23 | 34 | 31 |  | 47 | 56 |  | Sprint_2_1 | 38 | 15 | 39 | 36 | 15 | 27 | 24 |  | 47 | 41 |  | Sprint_3_5u6
Sprint_2_2 | 43 | 26 | 49 | 30 | 34 | 42 | 23 |  | 59 | 59 |  | Sprint_2_2 | 41 | 13 | 38 | 25 | 33 | 34 | 21 |  | 50 | 43
Sprint_2_3u4 | 106 | 29 | 78 | 100 | 53 | 75 | 45 |  | 98 | 103 |  | Sprint_2_3u4 | 96 | 17 | 36 | 22 | 33 | 33 | 45 |  | 98 | 58
Sprint_2_5u6 | 124 | 28 | 113 | 76 | 64 | 88 | 62 |  | 172 | 110 |  | Sprint_2_5u6 | 104 | 16 | 57 | 52 | 45 | 59 | 43 |  | 81 | 77
Sprint_3_1u2 | 0 | 43 | 151 | 0 | 70 | 0 | 62 |  | 0 | 0 |  | Sprint_3_1u2 | 0 | 32 | 78 | 0 | 37 | 0 | 62 |  | 0 | 0
Sprint_3_3u4 | [11 empty] | Sprint_3_3u4
Sprint_3_5u6 | [11 empty] | Sprint_3_5u6
| Velocity KPI | [11 empty] | Plan-Velocity-Match (Completed vs. FAIRLY AGILE Scope)
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_1_1 | 2.5 | 2.5 | 3 | 2.5 | 1.5 | 2.5 | 3 |  | 1.5 | 2.5 |  | Sprint_1_1 | -17.58% | -55% | -31.48% | -26.32% | -9.375% | -30.36% | -10.71% |  | -20% | -48.89%
Sprint_1_2 | 1.5 | 2 | 2.5 | 2.5 | 1.5 | 2.5 | 1.5 |  | 2.5 | 2 |  | Sprint_1_2 | -28.3% | -22.22% | -15.09% | -16.13% | -36.59% | -2% | -40.74% |  | -22.5% | -26.55%
Sprint_1_3 | 2.5 | 3 | 2.5 | 3 | 2.5 | 1.5 | 3 |  | 1.5 | 2 |  | Sprint_1_3 | -30.77% | -45.83% | -38.18% | -19.51% | -29.27% | -30.61% | -12.9% |  | -22.22% | -22.78%
Sprint_1_4 | 1.5 | 3 | 2 | 3 | 3 | 1.5 | 2.5 |  | 2.5 | 3 |  | Sprint_1_4 | -57.81% | -26.32% | 0% | -29.79% | -9.524% | -18.18% | -13.16% |  | -25.71% | -26.45%
Sprint_1_5 | 2.5 | 2.5 | 2.5 | 2 | 2.5 | 2.5 | 2.5 |  | 3 | 2.5 |  | Sprint_1_5 | -13.25% | -31.58% | -2.778% | -10.64% | -15% | -2.778% | -8.571% |  | -7.692% | -19.7%
Sprint_1_6 | 3 | 2.5 | 3 | 2.5 | 2.5 | 2.5 | 2.5 |  | 2.5 | 3 |  | Sprint_1_6 | -17.07% | -25% | -9.615% | -20% | -13.51% | -44.64% | -20.83% |  | -12.2% | -17.91%
Sprint_2_1 | 2.5 | 2.5 | 2.5 | 2.5 | 1 | 1.5 | 1.5 |  | 2.5 | 2.5 |  | Sprint_2_1 | -23.08% | -35% | -21.28% | -21.57% | -43.48% | -17.65% | -38.71% |  | -21.28% | -25.89%
Sprint_2_2 | 1.5 | 2.5 | 2.5 | 1 | 2.5 | 2.5 | 2.5 |  | 2 | 1.5 |  | Sprint_2_2 | -51.16% | -19.23% | -14.29% | -46.67% | -29.41% | -21.43% | -4.348% |  | -11.86% | -32.2%
Sprint_2_3u4 | 3 | 2.5 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 |  | Sprint_2_3u4 | -42.45% | -31.03% | -8.974% | -8% | -7.547% | -18.67% | -6.667% |  | -15.31% | -16.99%
Sprint_2_5u6 | 2.5 | 2 | 2 | 3 | 2.5 | 2 | 2 |  | 2 | 2 |  | Sprint_2_5u6 | -33.06% | -7.143% | -29.2% | -14.47% | -21.88% | -27.27% | -14.52% |  | -12.21% | -11.82%
Sprint_3_1u2 | [11 empty] | Sprint_3_1u2
Sprint_3_3u4 | [11 empty] | Sprint_3_3u4
Sprint_3_5u6 | [11 empty] | Sprint_3_5u6
2.125 | 2.1875 | 2.5625 | 2.5625 | 2.375 | 2.125 | 2.125 | 2.375 |  | 2.25 | 2.375 | 2.5625
| Initially Planned vs. TrueScope | [11 empty] | Initially Planned vs. Mean Velocity
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_1_1 | -41.76% | -45% | -37.04% | 0% | 0% | -14.29% | -35.71% |  | 6.667% | -20% |  | Sprint_1_1 | -11.67% | 7.317% | 3.817% | 16.03% | -20.5% | 16.36% | -25% |  | -17.24% | 38.46%
Sprint_1_2 | -9.434% | -51.85% | 1.887% | -16.13% | -14.63% | -10% | 0% |  | -22.5% | -34.51% |  | Sprint_1_2 | -23.81% | 30% | 60.71% | -18.24% | -7.895% | 10.29% | 11.57% |  | -11.43% | 45.67%
Sprint_1_3 | -5.128% | -12.5% | -32.73% | 0% | 0% | -26.53% | -25.81% |  | -29.63% | -55.7% |  | Sprint_1_3 | 25.78% | 77.46% | 4.225% | 32.97% | 13.89% | -14.62% | 0.7299% |  | -44.44% | 24.63%
Sprint_1_4 | -9.375% | -15.79% | -7.143% | -44.68% | -14.29% | -12.12% | -21.05% |  | -22.86% | -37.19% |  | Sprint_1_4 | 3.264% | 24.68% | 39.29% | -7.143% | 0% | -29.27% | 21.62% |  | -15.62% | 6.792%
Sprint_1_5 | -7.229% | -31.58% | -19.44% | -6.383% | -5% | -25% | -17.14% |  | -33.33% | -57.58% |  | Sprint_1_5 | 51.48% | -2.5% | -24.35% | 53.49% | 4.587% | -32.22% | 15.23% |  | -19.59% | -29.71%
Sprint_1_6 | -19.51% | -37.5% | -36.54% | -17.14% | -16.22% | -35.71% | -12.5% |  | -12.2% | -68.66% |  | Sprint_1_6 | 16.47% | 13.92% | -14.29% | -11.22% | -5.102% | -8.475% | -16.56% |  | 25.58% | -50.59%
Sprint_2_1 | -26.92% | -25% | -17.02% | -29.41% | -34.78% | -20.59% | -22.58% |  | 0% | -26.79% |  | Sprint_2_1 | -31.74% | 2.273% | -7.874% | 13.68% | -52.13% | -24.65% | -5.263% |  | 62.07% | -11.51%
Sprint_2_2 | -4.651% | -50% | -6.122% | -16.67% | -2.941% | -19.05% | -8.696% |  | -15.25% | -27.12% |  | Sprint_2_2 | -17.73% | -15.22% | 8.661% | -25.74% | 15.12% | 0% | -13.7% |  | 60.43% | -12.98%
Sprint_2_3u4 | -9.434% | -37.93% | -53.85% | -78% | -37.74% | -56% | 0% |  | 0% | -43.69% |  | Sprint_2_3u4 | 104.3% | 17.39% | -13.94% | -31.25% | 16.47% | 5.319% | 77.63% |  | 182.7% | 17.97%
Sprint_2_5u6 | -16.13% | -35.71% | -49.56% | -31.58% | -29.69% | -32.95% | -30.65% |  | -52.91% | -30% |  | Sprint_2_5u6 | 115.9% | 9.091% | 18.75% | 24.3% | 42.11% | 64.65% | 54.49% |  | 80% | 44.6%
Sprint_3_1u2 | [11 empty] | Sprint_3_1u2
Sprint_3_3u4 | [11 empty] | Sprint_3_3u4
Sprint_3_5u6 | [11 empty] | Sprint_3_5u6
| -15.5% | -33.65% | -19.27% | -16.3% | -10.98% | -20.41% | -17.94% |  | -16.14% | -40.94% |  |  | 1.506% | 17.24% | 8.775% | 6.728% | -6.504% | -10.32% | -1.421% |  | 4.969% | 1.345%
| Velocity KPI (Rang aus 3 Sprints: Verlauf und Tendenz) | [11 empty] | Velocity KPI ("Enginered": mittleren Sprint ignorieren) | [9 empty] | 165.2% |  | Velocity KPI ("Gegen den Trend":Naive Prognose vs. Tatsächlicher Wert) | [9 empty] | 100% |  | Velocity KPI (Delta Trend-Trend-Prognose zu Startwert, rel. zu Endwert) | [9 empty] | 187.5% |  | Velocity vs. Linear Projection | [9 empty] | 1120%
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon |  |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon | -58.62% |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon | -159.3% |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon | -300% |  | Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon | -65.29%
Sprint_1_1 | 3 | 1.5 | 3 | 2 | 1 | 2 | 2 |  | 1 | 1 |  | Sprint_1_1 | 102.7% | -35.71% | 8.824% | 55.56% | -48.21% | 2.632% | -21.88% |  | -58.62% | -37.84% |  | Sprint_1_1 | -48% | 55.56% | 62.16% | -78.57% | 17.24% | -69.23% | 84% |  | 58.33% | -17.39% |  | Sprint_1_1 | 4% | 0% | 105.4% | -64.29% | -113.8% | -100% | 84% |  | -125% | -117.4% |  | Sprint_1_1 | 30.43% | -28% | 25.42% | 55.56% | -45.79% | -22.77% | -3.846% |  |  | -45.88%
Sprint_1_2 | 1 | 3 | 3 | 1 | 1 | 2 | 1 |  | 2 | 3 |  | Sprint_1_2 | -48.65% | 133.3% | 87.5% | -23.53% | -35% | -5.769% | -11.11% |  | -8.824% | 29.69% |  | Sprint_1_2 | -100% | 57.14% | -11.11% | 15.38% | 30.77% | 46.94% | -100% |  | 54.84% | 66.27% |  | Sprint_1_2 | -292.1% | 171.4% | 53.33% | -23.08% | -34.62% | 61.22% | -168.8% |  | 67.74% | 133.7% |  | Sprint_1_2 | -53.94% | 162.5% | 87.5% | -14.75% | -16.13% | 2.083% | -15.79% |  | 6.897% | 40.68%
Sprint_1_3 | 2 | 2 | 1 | 3 | 2.5 | 1 | 3 |  | 1 | 3 |  | Sprint_1_3 | -28% | 44.44% | -8.108% | 17.86% | 0% | -12.82% | 8% |  | -12.5% | 165.2% |  | Sprint_1_3 | 98.15% | -153.8% | -55.88% | 27.27% | 20.69% | -73.53% | 74.07% |  | -80.95% | 1.639% |  | Sprint_1_3 | 88.89% | -184.6% | -97.06% | 63.64% | 31.03% | -132.4% | 122.2% |  | -142.9% | 95.9% |  | Sprint_1_3 | -5.263% | -29.73% | -26.88% | 6.452% | 132% | -31.31% | 116% |  | 50% | 76.81%
Sprint_1_4 | 1 | 2 | 3 | 2.5 | 3 | 1 | 3 |  | 2 | 2 |  | Sprint_1_4 | -28.95% | -33.33% | 24.44% | 26.92% | 46.15% | -44.9% | 106.2% |  | -16.13% | 7.229% |  | Sprint_1_4 | -159.3% | 64.29% | 58.93% | -21.21% | 15.79% | 29.63% | -15.15% |  | 57.69% | -80.9% |  | Sprint_1_4 | -300% | 21.43% | 117.9% | 0% | 71.05% | -77.78% | 54.55% |  | 57.69% | -111.2% |  | Sprint_1_4 | -25% | -26.32% | 25.84% | 13.79% | 72.73% | -16.92% | 26.92% |  | 33.33% | -32.32%
Sprint_1_5 | 3 | 1.5 | 2 | 3 | 2 | 3 | 2 |  | 3 | 2 |  | Sprint_1_5 | 33.33% | 0% | 2.941% | 27.27% | 17.24% | 2.941% | 18.52% |  | 71.43% | -13.11% |  | Sprint_1_5 | 100% | -15.38% | -122.9% | 21.43% | -38.24% | 42.86% | -21.88% |  | 13.89% | 47.17% |  | Sprint_1_5 | 187.5% | -23.08% | -180% | 64.29% | -35.29% | 68.57% | -9.375% |  | 83.33% | 48.11% |  | Sprint_1_5 | 336.4% | -18.75% | -35.78% | 18.31% | -10.53% | 42.86% | -5.882% |  | 46.94% | -16.54%
Sprint_1_6 | 2 | 3 | 2 | 1 | 1 | 2 | 1 |  | 2.5 | 3 |  | Sprint_1_6 | 151.9% | 28.57% | -16.07% | -15.15% | -15.79% | 14.81% | -42.42% |  | 38.46% | 23.6% |  | Sprint_1_6 | -72.06% | 33.33% | 70.21% | -82.14% | 6.25% | -38.71% | -63.16% |  | -27.78% | -11.82% |  | Sprint_1_6 | -17.65% | 83.33% | 76.6% | -150% | -18.75% | -38.71% | -205.3% |  | 0% | 10.91% |  | Sprint_1_6 | 2.256% | 89.47% | 16.05% | -38.46% | -20% | 29.17% | -53.09% |  | 7.463% | 0.9174%
Sprint_2_1 | 1 | 1.5 | 2 | 2 | 1 | 1 | 1.5 |  | 3 | 1 |  | Sprint_2_1 | -44.44% | 0% | 5.714% | -4.762% | -61.76% | -20% | -40.62% |  | 2.778% | -21.7% |  | Sprint_2_1 | -60% | -76.92% | -59.46% | 65% | -130.8% | 3.571% | 68.42% |  | 2.703% | -37.35% |  | Sprint_2_1 | -210% | -115.4% | -81.08% | 90% | -438.5% | -32.14% | 0% |  | 8.108% | -97.59% |  | Sprint_2_1 | -48.05% | -27.78% | -22.11% | 23.08% | -62.32% | -11.11% | -11.63% |  | -14.94% | -18.63%
Sprint_2_2 | 1 | 3 | 2 | 1 | 2 | 3 | 3 |  | 3 | 1 |  | Sprint_2_2 | -69.12% | 16.67% | -10.64% | -42.86% | -25% | 6.452% | 15.79% |  | 44.44% | -27.27% |  | Sprint_2_2 | 42.86% | 61.9% | 35.71% | -225% | 125% | 24.24% | 13.64% |  | 26.92% | 30% |  | Sprint_2_2 | -271.4% | 114.3% | 35.71% | -450% | 137.5% | 45.45% | 40.91% |  | 86.54% | -11.25% |  | Sprint_2_2 | -65.29% | 40% | 29.23% | -57.33% | 140% | 10% | 83.33% |  | 23.81% | -14.44%
Sprint_2_3u4 | 3 | 2 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 |  | Sprint_2_3u4 | 52.5% | 53.85% | 91.89% | 130% | 276.9% | 117.9% | 121.1% |  | 124.3% | 106% |  | Sprint_2_3u4 | 96.72% | -45% | 33.8% | 108.7% | 28.57% | 37.7% | 40.48% |  | 19.28% | 54.97% |  | Sprint_2_3u4 | 196.7% | -15% | 122.5% | 247.8% | 153.1% | 137.7% | 142.9% |  | 112% | 159.6% |  | Sprint_2_3u4 | 1120% | -4.762% | 65.12% | 513.3% | 263% | 106.8% | 171% |  | 58.1% | 149.6%
Sprint_2_5u6 | 3 | 3 | 3 | 2 | 3 | 3 | 3 |  | 3 | 3 |  | Sprint_2_5u6 | 295.2% | 23.81% | 90.48% | 306.2% | 108.3% | 93.94% | 140.9% |  | 190.4% | 142.5% |  | Sprint_2_5u6 | -21.69% | 26.92% | -25% | -158.5% | -48% | -39.06% | -16.98% |  | 24.5% | -35.05% |  | Sprint_2_5u6 | 79.52% | 69.23% | 33.75% | -124.6% | 6% | 14.06% | 62.26% |  | 135.1% | 35.57% |  | Sprint_2_5u6 | 121.3% | 20.93% | 16.79% | -24.42% | 11.11% | 3.226% | 21.84% |  | 65.93% | 24.36%
Sprint_3_1u2 | [11 empty] | Sprint_3_1u2 | [11 empty] | Sprint_3_1u2 | [11 empty] | Sprint_3_1u2 | [11 empty] | Sprint_3_1u2
Sprint_3_3u4 | [11 empty] | Sprint_3_3u4 | [11 empty] | Sprint_3_3u4 | [11 empty] | Sprint_3_3u4 | [11 empty] | Sprint_3_3u4
Sprint_3_5u6 | [11 empty] | Sprint_3_5u6 | [11 empty] | Sprint_3_5u6
1.6875 | 1.75 | 2.1875 | 2.25 | 1.9375 | 1.6875 | 1.875 | 2.0625 |  | 2.1875 | 2 | 2.25 | [13 empty] | -24.79% | 3.259% | -2.787% | -34.73% | 5.842% | -4.279% | 4.993% |  | 13.21% | -0.2979% |  |  | -101.3% | 8.425% | 3.846% | -58.68% | -50.17% | -25.72% | -10.21% |  | 4.445% | -6.101% |  |  | 21.44% | 20.18% | 12.41% | 0.8298% | 23.74% | 0.2484% | 17% |  | 21.93% | -1.175%
Velocity KPI (Rang aus allen Sprints: Verlauf und Tendenz)
| Engineering | Payment | Sales | Vlinder | TTT | TNT | TFS | 0-Noise | Synergy | Papillon
Sprint_1_1 | 100% | 50% | 80% | 40% | 30% | 60% | 60% |  | 37.5% | 60%
Sprint_1_2 | 33.33% | 100% | 83.33% | 33.33% | 16.67% | 83.33% | 25% |  | 60% | 100%
Sprint_1_3 | 42.86% | 71.43% | 50% | 71.43% | 42.86% | 21.43% | 71.43% |  | 16.67% | 100%
Sprint_1_4 | 12.5% | 81.25% | 100% | 68.75% | 75% | 12.5% | 100% |  | 57.14% | 87.5%
Sprint_1_5 | 77.78% | 61.11% | 55.56% | 88.89% | 55.56% | 44.44% | 83.33% |  | 87.5% | 88.89%
Sprint_1_6 | 60% | 90% | 80% | 35% | 50% | 20% | 40% |  | 83.33% | 90%
Sprint_2_1 | 36.36% | 54.55% | 59.09% | 81.82% | 9.091% | 18.18% | 40.91% |  | 90% | 59.09%
Sprint_2_2 | 8.333% | 95.83% | 66.67% | 8.333% | 16.67% | 33.33% | 50% |  | 90.91% | 50%
Sprint_2_3u4 | 61.54% | 84.62% | 100% | 100% | 92.31% | 100% | 100% |  | 100% | 100%
Sprint_2_5u6 | 100% | 100% | 100% | 92.86% | 92.86% | 100% | 100% |  | 100% | 100%
Sprint_3_1u2
Sprint_3_3u4
Sprint_3_5u6
| 46.4% | 75.52% | 71.83% | 53.44% | 36.98% | 36.65% | 58.83% |  | 65.38% | 79.43%

## Sprint_TEST
Sprint 2025_2-3, 13.05.2025 - 27.05.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-Over sensitive [SOs] and Carry-Over sensitive [COs]) | [5 empty] | Team | Epic | CSOsSP Completed ABS | CSOsSP Completed REL
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | 0-Noise |  | 208 | 14.09%
| > > > > Use exactly these team names! > > > > | Engineering | 19 | 7 | 85 | 59 | 54 | 28 | 62 | 144 |  | 32 | 76 | 68 | 17 | 23 | 212.5% |  | Epic #1 | 26 | 12.5%
|  | Payment | 24 | 8 | 121 | 57 | 83 | 51 | 44 | 178 |  | 63 | 76 | 105 | 19 | 15 | 166.7% |  | Epic #10 | 32 | 15.38%
|  | Sales | 26 | 9 | 64 | 79 | 41 | 43 | 59 | 143 |  | 34 | 146 | 105 | 38 | 37 | 308.8% |  | Epic #2 | 11 | 5.288%
|  | Vlinder | 31 | 14 | 51 | 123 | 74 | 41 | 59 | 174 |  | 21 | 202 | 178 | 31 | 14 | 847.6% |  | Epic #3 | 5 | 2.404%
|  | TTT | 29 | 9 | 85 | 64 | 59 | 28 | 62 | 149 |  | 68 | 168 | 190 | 34 | 12 | 279.4% |  | Epic #4 | 8 | 3.846%
|  | TNT | 28 | 7 | 103 | 49 | 36 | 83 | 33 | 152 |  | 78 | 162 | 162 | 15 | 63 | 207.7% |  | Epic #5 | 22 | 10.58%
|  | TFS | 29 | 12 | 38 | 163 | 69 | 70 | 62 | 201 |  | 34 | 234 | 156 | 43 | 69 | 458.8% |  | Epic #6 | 13 | 6.25%
|  | 0-Noise | 35 | 9 | 90 | 103 | 44 | 57 | 92 | 193 |  | 52 | 219 | 208 | 61 | 2 | 400% |  | Epic #7 | 16 | 7.692%
|  | Synergy | 24 | 8 | 80 | 67 | 39 | 59 | 49 | 147 |  | 37 | 128 | 133 | 7 | 25 | 359.5% |  | Epic #8 | 67 | 32.21%
|  | Papillon | 25 | 7 | 93 | 46 | 41 | 80 | 18 | 139 |  | 76 | 146 | 171 | 23 | 28 | 225% |  | Epic #9 | 8 | 3.846%
|  | Total | 221 | 75 | 637 | 697 | 460 | 401 | 473 | 1334 |  | 382 | 1283 | 1172 | 258 | 235 | --- | Engineering |  | 68 | 4.607%
[19 empty] | Epic #1 | 0 | 0%
[19 empty] | Epic #10 | 6 | 8.824%
[19 empty] | Epic #2 | -4 | -5.882%
[19 empty] | Epic #3 | 5 | 7.353%
|  | Category Summary | [16 empty] | Epic #4 | 5 | 7.353%
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total | [5 empty] | Epic #5 | 21 | 30.88%
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP |  |  |  |  | Epic #6 | 8 | 11.76%
|  | Scope | 135 | 900 | 135 | 900 | 270 | 1800 | 180 | 1620 | 90 | 180 | 270 | 1800 |  |  |  |  | Epic #7 | 0 | 0%
|  | Completed | 45 | 300 | 45 | 300 | 90 | 600 | 60 | 540 | 30 | 60 | 90 | 600 |  |  |  |  | Epic #8 | 21 | 30.88%
|  | Not Completed | 45 | 300 | 45 | 300 | 90 | 600 | 60 | 540 | 30 | 60 | 90 | 600 |  |  |  |  | Epic #9 | 6 | 8.824%
|  | Removed | 45 | 300 | 45 | 300 | 90 | 600 | 60 | 540 | 30 | 60 | 90 | 600 |  |  |  | Papillon |  | 171 | 11.59%
[11 empty] | Flat Rate for "-" Story Points | 2 | [6 empty] | Epic #1 | 12 | 7.018%
[19 empty] | Epic #10 | 21 | 12.28%
[5 empty] | 1 |  | 4 |  |  | 5 | 2 | 3 | [6 empty] | Epic #2 | 19 | 11.11%
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Epic | Status | Carry-over | Spill-over | COsSP Initially Planned | COsSP Pulled after Start | CSOsSP Completed | CSOsSP Removed | CSOsSP Not Completed |  | Epic #3 | 40 | 23.39%
[5 empty] | 5 | Vlinder | yes |  | Epic #8 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #4 | 21 | 12.28%
[5 empty] | 13 | TFS | yes |  | Epic #7 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #5 | 32 | 18.71%
[5 empty] | - | TNT | yes |  | Epic #4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #6 | 8 | 4.678%
[5 empty] | 5 | TFS | yes |  | Epic #7 | Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0 |  | Epic #7 | 6 | 3.509%
[5 empty] | 13 | TFS | yes |  | Epic #2 | Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0 |  | Epic #8 | 6 | 3.509%
[5 empty] | - | 0-Noise | yes |  | Epic #1 | Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0 |  | Epic #9 | 6 | 3.509%
[5 empty] | 5 | TTT | yes |  | Epic #2 | Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0 | Payment |  | 105 | 7.114%
[5 empty] | 13 | TNT | yes |  | Epic #8 | Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0 |  | Epic #1 | 11 | 10.48%
[5 empty] | - | 0-Noise | yes |  | Epic #1 | Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0 |  | Epic #10 | 10 | 9.524%
[5 empty] | 5 | Vlinder | yes |  | Epic #7 | Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0 |  | Epic #2 | 8 | 7.619%
[5 empty] | 13 | TTT | yes |  | Epic #4 | Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0 |  | Epic #3 | 13 | 12.38%
[5 empty] | - | TTT | yes |  | Epic #7 | Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0 |  | Epic #4 | 19 | 18.1%
[5 empty] | 5 | Engineering | yes |  | Epic #4 | Completed |  | 0 | 0 | 5 | 5 | 0 | 0 |  | Epic #5 | 21 | 20%
[5 empty] | 13 | Vlinder | yes |  | Epic #4 | Completed |  | 0 | 0 | 13 | 13 | 0 | 0 |  | Epic #6 | 3 | 2.857%
[5 empty] | - | Synergy | yes |  | Epic #7 | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #7 | 0 | 0%
[5 empty] | 5 | TFS | yes |  | Epic #9 | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | Epic #8 | 9 | 8.571%
[5 empty] | 13 | Engineering | yes |  | Epic #1 | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | Epic #9 | 11 | 10.48%
[5 empty] | - | Engineering | yes |  | Epic #8 | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Sales |  | 105 | 7.114%
[5 empty] | 5 | TTT | yes |  | Epic #5 | Completed | 3 | 2 | 0 | 3 | 3 | 0 | 0 |  | Epic #1 | 5 | 4.762%
[5 empty] | 13 | TFS | yes |  | Epic #9 | Completed | 3 | 2 | 0 | 3 | 3 | 0 | 0 |  | Epic #10 | 3 | 2.857%
[5 empty] | - | Vlinder | yes |  | Epic #6 | Completed | 3 | 2 | 0 | 3 | 3 | 0 | 0 |  | Epic #2 | 0 | 0%
[5 empty] | 5 | TTT | yes |  | Epic #9 | Completed | 8 | 2 | 0 | 8 | 8 | 0 | 0 |  | Epic #3 | 13 | 12.38%
[5 empty] | 13 | TTT | yes |  | Epic #4 | Completed | 8 | 2 | 0 | 8 | 8 | 0 | 0 |  | Epic #4 | 1 | 0.9524%
[5 empty] | - | TFS | yes |  | Epic #7 | Completed | 8 | 2 | 0 | 8 | 8 | 0 | 0 |  | Epic #5 | 11 | 10.48%
[5 empty] | 5 | Vlinder | yes |  | Epic #2 | Completed | 21 | 2 | 0 | 21 | 21 | 0 | 0 |  | Epic #6 | 19 | 18.1%
[5 empty] | 13 | Synergy | yes |  | Epic #9 | Completed | 21 | 2 | 0 | 21 | 21 | 0 | 0 |  | Epic #7 | 54 | 51.43%
[5 empty] | - | Synergy | yes |  | Epic #2 | Completed | 21 | 2 | 0 | 21 | 21 | 0 | 0 |  | Epic #8 | -1 | -0.9524%
[5 empty] | 5 | Sales | yes |  | Epic #5 | Completed |  | 2 | 0 | 5 | 5 | 0 | 0 |  | Epic #9 | 0 | 0%
[5 empty] | 13 | Sales | yes |  | Epic #3 | Completed |  | 2 | 0 | 13 | 13 | 0 | 0 | Synergy |  | 133 | 9.011%
[5 empty] | - | Papillon | yes |  | Epic #9 | Completed |  | 2 | 0 | 0 | 0 | 0 | 0 |  | Epic #1 | 22 | 16.54%
[5 empty] | 5 | TTT | yes |  | Epic #1 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Epic #10 | 19 | 14.29%
[5 empty] | 13 | Vlinder | yes |  | Epic #3 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Epic #2 | 21 | 15.79%
[5 empty] | - | TNT | yes |  | Epic #7 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Epic #3 | -2 | -1.504%
[5 empty] | 5 | Vlinder | yes |  | Epic #7 | Completed | 3 |  | 0 | 3 | 3 | 0 | 0 |  | Epic #4 | 29 | 21.8%
[5 empty] | 13 | 0-Noise | yes |  | Epic #8 | Completed | 3 |  | 0 | 3 | 3 | 0 | 0 |  | Epic #5 | 0 | 0%
[5 empty] | - | Payment | yes |  | Epic #4 | Completed | 3 |  | 0 | 3 | 3 | 0 | 0 |  | Epic #6 | 8 | 6.015%
[5 empty] | 5 | Vlinder | yes |  | Epic #10 | Completed | 8 |  | 0 | 8 | 8 | 0 | 0 |  | Epic #7 | 0 | 0%
[5 empty] | 13 | 0-Noise | yes |  | Epic #2 | Completed | 8 |  | 0 | 8 | 8 | 0 | 0 |  | Epic #8 | 9 | 6.767%
[5 empty] | - | 0-Noise | yes |  | Epic #9 | Completed | 8 |  | 0 | 8 | 8 | 0 | 0 |  | Epic #9 | 27 | 20.3%
[5 empty] | 5 | TFS | yes |  | Epic #5 | Completed | 21 |  | 0 | 21 | 21 | 0 | 0 | TFS |  | 156 | 10.57%
[5 empty] | 13 | Payment | yes |  | Epic #5 | Completed | 21 |  | 0 | 21 | 21 | 0 | 0 |  | Epic #1 | 11 | 7.051%
[5 empty] | - | TFS | yes |  | Epic #3 | Completed | 21 |  | 0 | 21 | 21 | 0 | 0 |  | Epic #10 | 3 | 1.923%
[5 empty] | 5 | Papillon | yes |  | Epic #1 | Completed |  |  | 0 | 5 | 5 | 0 | 0 |  | Epic #2 | 22 | 14.1%
[5 empty] | 13 | Payment | yes |  | Epic #4 | Completed |  |  | 0 | 13 | 13 | 0 | 0 |  | Epic #3 | 21 | 13.46%
[5 empty] | - | 0-Noise | yes |  | Epic #7 | Completed |  |  | 0 | 0 | 0 | 0 | 0 |  | Epic #4 | 19 | 12.18%
[5 empty] | 5 | Vlinder |  |  | Epic #5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #5 | 21 | 13.46%
[5 empty] | 13 | 0-Noise |  |  | Epic #4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #6 | 11 | 7.051%
[5 empty] | - | Vlinder |  |  | Epic #9 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #7 | 19 | 12.18%
[5 empty] | 5 | TFS |  |  | Epic #10 | Completed | 3 | 0 | 3 | 0 | 3 | 0 | 0 |  | Epic #8 | 1 | 0.641%
[5 empty] | 13 | Payment |  |  | Epic #6 | Completed | 3 | 0 | 3 | 0 | 3 | 0 | 0 |  | Epic #9 | 28 | 17.95%
[5 empty] | - | 0-Noise |  |  | Epic #8 | Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0 | TNT |  | 162 | 10.98%
[5 empty] | 5 | Payment |  |  | Epic #2 | Completed | 8 | 0 | 5 | 3 | 8 | 0 | 0 |  | Epic #1 | -2 | -1.235%
[5 empty] | 13 | Engineering |  |  | Epic #6 | Completed | 8 | 0 | 8 | 0 | 8 | 0 | 0 |  | Epic #10 | 1 | 0.6173%
[5 empty] | - | Synergy |  |  | Epic #4 | Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0 |  | Epic #2 | 30 | 18.52%
[5 empty] | 5 | Sales |  |  | Epic #7 | Completed | 21 | 0 | 5 | 16 | 21 | 0 | 0 |  | Epic #3 | 0 | 0%
[5 empty] | 13 | Papillon |  |  | Epic #3 | Completed | 21 | 0 | 13 | 8 | 21 | 0 | 0 |  | Epic #4 | 30 | 18.52%
[5 empty] | - | Vlinder |  |  | Epic #10 | Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0 |  | Epic #5 | 3 | 1.852%
[5 empty] | 5 | TFS |  |  | Epic #1 | Completed |  | 0 | 5 | 0 | 5 | 0 | 0 |  | Epic #6 | 40 | 24.69%
[5 empty] | 13 | TNT |  |  | Epic #8 | Completed |  | 0 | 13 | 0 | 13 | 0 | 0 |  | Epic #7 | 38 | 23.46%
[5 empty] | - | TNT |  |  | Epic #10 | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Epic #8 | 22 | 13.58%
[5 empty] | 5 | TNT |  |  | Epic #4 | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | Epic #9 | 0 | 0%
[5 empty] | 13 | Vlinder |  |  | Epic #3 | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0 | TTT |  | 190 | 12.87%
[5 empty] | - | Sales |  |  | Epic #8 | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  | Epic #1 | 21 | 11.05%
[5 empty] | 5 | Papillon |  |  | Epic #5 | Completed | 3 | 2 | 3 | 0 | 3 | 0 | 0 |  | Epic #10 | -2 | -1.053%
[5 empty] | 13 | Papillon |  |  | Epic #8 | Completed | 3 | 2 | 3 | 0 | 3 | 0 | 0 |  | Epic #2 | 8 | 4.211%
[5 empty] | - | Synergy |  |  | Epic #1 | Completed | 3 | 2 | 0 | 3 | 3 | 0 | 0 |  | Epic #3 | 27 | 14.21%
[5 empty] | 5 | 0-Noise |  |  | Epic #6 | Completed | 8 | 2 | 5 | 3 | 8 | 0 | 0 |  | Epic #4 | 37 | 19.47%
[5 empty] | 13 | Payment |  |  | Epic #10 | Completed | 8 | 2 | 8 | 0 | 8 | 0 | 0 |  | Epic #5 | 48 | 25.26%
[5 empty] | - | Sales |  |  | Epic #6 | Completed | 8 | 2 | 0 | 8 | 8 | 0 | 0 |  | Epic #6 | 1 | 0.5263%
[5 empty] | 5 | Engineering |  |  | Epic #5 | Completed | 21 | 2 | 5 | 16 | 21 | 0 | 0 |  | Epic #7 | 42 | 22.11%
[5 empty] | 13 | Synergy |  |  | Epic #4 | Completed | 21 | 2 | 13 | 8 | 21 | 0 | 0 |  | Epic #9 | 8 | 4.211%
[5 empty] | - | TTT |  |  | Epic #3 | Completed | 21 | 2 | 0 | 21 | 21 | 0 | 0 | Vlinder |  | 178 | 12.06%
[5 empty] | 5 | Papillon |  |  | Epic #8 | Completed |  | 2 | 5 | 0 | 5 | 0 | 0 |  | Epic #1 | 3 | 1.685%
[5 empty] | 13 | Sales |  |  | Epic #7 | Completed |  | 2 | 13 | 0 | 13 | 0 | 0 |  | Epic #10 | 53 | 29.78%
[5 empty] | - | Synergy |  |  | Epic #8 | Completed |  | 2 | 0 | 0 | 0 | 0 | 0 |  | Epic #2 | 40 | 22.47%
[5 empty] | 5 | Engineering |  |  | Epic #2 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Epic #3 | 0 | 0%
[5 empty] | 13 | Engineering |  |  | Epic #5 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Epic #4 | 32 | 17.98%
[5 empty] | - | Vlinder |  |  | Epic #7 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Epic #5 | 1 | 0.5618%
[5 empty] | 5 | Vlinder |  |  | Epic #1 | Completed | 3 |  | 3 | 0 | 3 | 0 | 0 |  | Epic #6 | 5 | 2.809%
[5 empty] | 13 | Payment |  |  | Epic #9 | Completed | 3 |  | 3 | 0 | 3 | 0 | 0 |  | Epic #7 | 43 | 24.16%
[5 empty] | - | Sales |  |  | Epic #7 | Completed | 3 |  | 0 | 3 | 3 | 0 | 0 |  | Epic #8 | 1 | 0.5618%
[5 empty] | 5 | TFS |  |  | Epic #7 | Completed | 8 |  | 5 | 3 | 8 | 0 | 0 |  | Epic #9 | 0 | 0%
[5 empty] | 13 | Synergy |  |  | Epic #8 | Completed | 8 |  | 8 | 0 | 8 | 0 | 0
[5 empty] | - | Papillon |  |  | Epic #5 | Completed | 8 |  | 0 | 8 | 8 | 0 | 0
[5 empty] | 5 | TNT |  |  | Epic #7 | Completed | 21 |  | 5 | 16 | 21 | 0 | 0
[5 empty] | 13 | TTT |  |  | Epic #5 | Completed | 21 |  | 13 | 8 | 21 | 0 | 0
[5 empty] | - | Sales |  |  | Epic #7 | Completed | 21 |  | 0 | 21 | 21 | 0 | 0
[5 empty] | 5 | Sales |  |  | Epic #1 | Completed |  |  | 5 | 0 | 5 | 0 | 0
[5 empty] | 13 | Payment |  |  | Epic #3 | Completed |  |  | 13 | 0 | 13 | 0 | 0
[5 empty] | - | TFS |  |  | Epic #10 | Completed |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Papillon | yes |  | Epic #9 | Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | Engineering | yes |  | Epic #7 | Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | - | Synergy | yes |  | Epic #6 | Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Synergy | yes |  | Epic #9 | Not Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | 13 | 0-Noise | yes |  | Epic #5 | Not Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | - | Vlinder | yes |  | Epic #5 | Not Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | 5 | TTT | yes |  | Epic #7 | Not Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | 13 | 0-Noise | yes |  | Epic #4 | Not Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | - | 0-Noise | yes |  | Epic #7 | Not Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | 5 | Engineering | yes |  | Epic #8 | Not Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | 13 | TFS | yes |  | Epic #9 | Not Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | - | Papillon | yes |  | Epic #3 | Not Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | 5 | Engineering | yes |  | Epic #3 | Not Completed |  | 0 | 0 | 5 | 5 | 0 | 0
[5 empty] | 13 | Vlinder | yes |  | Epic #2 | Not Completed |  | 0 | 0 | 13 | 13 | 0 | 0
[5 empty] | - | TTT | yes |  | Epic #10 | Not Completed |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Papillon | yes |  | Epic #3 | Not Completed | 0 | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | 13 | Synergy | yes |  | Epic #3 | Not Completed | 0 | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | - | TNT | yes |  | Epic #1 | Not Completed | 0 | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | 5 | Sales | yes |  | Epic #4 | Not Completed | 3 | 2 | 0 | 3 | 1 | 0 | 2
[5 empty] | 13 | 0-Noise | yes |  | Epic #1 | Not Completed | 3 | 2 | 0 | 3 | 1 | 0 | 2
[5 empty] | - | Vlinder | yes |  | Epic #8 | Not Completed | 3 | 2 | 0 | 3 | 1 | 0 | 2
[5 empty] | 5 | Vlinder | yes |  | Epic #6 | Not Completed | 8 | 2 | 0 | 8 | 6 | 0 | 2
[5 empty] | 13 | Papillon | yes |  | Epic #7 | Not Completed | 8 | 2 | 0 | 8 | 6 | 0 | 2
[5 empty] | - | Sales | yes |  | Epic #5 | Not Completed | 8 | 2 | 0 | 8 | 6 | 0 | 2
[5 empty] | 5 | Vlinder | yes |  | Epic #4 | Not Completed | 21 | 2 | 0 | 21 | 19 | 0 | 2
[5 empty] | 13 | Papillon | yes |  | Epic #2 | Not Completed | 21 | 2 | 0 | 21 | 19 | 0 | 2
[5 empty] | - | TFS | yes |  | Epic #2 | Not Completed | 21 | 2 | 0 | 21 | 19 | 0 | 2
[5 empty] | 5 | Sales | yes |  | Epic #6 | Not Completed |  | 2 | 0 | 5 | 3 | 0 | 2
[5 empty] | 13 | TNT | yes |  | Epic #2 | Not Completed |  | 2 | 0 | 13 | 11 | 0 | 2
[5 empty] | - | Engineering | yes |  | Epic #2 | Not Completed |  | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | 5 | Payment | yes |  | Epic #2 | Not Completed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | Payment | yes |  | Epic #4 | Not Completed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | - | TFS | yes |  | Epic #4 | Not Completed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Vlinder | yes |  | Epic #6 | Not Completed | 3 |  | 0 | 3 | 0 | 0 | 3
[5 empty] | 13 | Vlinder | yes |  | Epic #7 | Not Completed | 3 |  | 0 | 3 | 0 | 0 | 3
[5 empty] | - | Payment | yes |  | Epic #10 | Not Completed | 3 |  | 0 | 3 | 0 | 0 | 3
[5 empty] | 5 | Synergy | yes |  | Epic #5 | Not Completed | 8 |  | 0 | 8 | 0 | 0 | 8
[5 empty] | 13 | TFS | yes |  | Epic #2 | Not Completed | 8 |  | 0 | 8 | 0 | 0 | 8
[5 empty] | - | TNT | yes |  | Epic #9 | Not Completed | 8 |  | 0 | 8 | 0 | 0 | 8
[5 empty] | 5 | Sales | yes |  | Epic #2 | Not Completed | 21 |  | 0 | 21 | 0 | 0 | 21
[5 empty] | 13 | TFS | yes |  | Epic #3 | Not Completed | 21 |  | 0 | 21 | 0 | 0 | 21
[5 empty] | - | TNT | yes |  | Epic #5 | Not Completed | 21 |  | 0 | 21 | 0 | 0 | 21
[5 empty] | 5 | Sales | yes |  | Epic #5 | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
[5 empty] | 13 | TFS | yes |  | Epic #8 | Not Completed |  |  | 0 | 13 | 0 | 0 | 13
[5 empty] | - | Payment | yes |  | Epic #8 | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Payment |  |  | Epic #7 | Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | Synergy |  |  | Epic #1 | Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | - | Engineering |  |  | Epic #5 | Not Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Sales |  |  | Epic #10 | Not Completed | 3 | 0 | 3 | 0 | 3 | 0 | 0
[5 empty] | 13 | 0-Noise |  |  | Epic #10 | Not Completed | 3 | 0 | 3 | 0 | 3 | 0 | 0
[5 empty] | - | Payment |  |  | Epic #4 | Not Completed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | 5 | 0-Noise |  |  | Epic #7 | Not Completed | 8 | 0 | 5 | 3 | 8 | 0 | 0
[5 empty] | 13 | Synergy |  |  | Epic #6 | Not Completed | 8 | 0 | 8 | 0 | 8 | 0 | 0
[5 empty] | - | 0-Noise |  |  | Epic #10 | Not Completed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | 5 | Papillon |  |  | Epic #4 | Not Completed | 21 | 0 | 5 | 16 | 21 | 0 | 0
[5 empty] | 13 | Papillon |  |  | Epic #5 | Not Completed | 21 | 0 | 13 | 8 | 21 | 0 | 0
[5 empty] | - | TNT |  |  | Epic #6 | Not Completed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | 5 | TTT |  |  | Epic #4 | Not Completed |  | 0 | 5 | 0 | 5 | 0 | 0
[5 empty] | 13 | TNT |  |  | Epic #2 | Not Completed |  | 0 | 13 | 0 | 13 | 0 | 0
[5 empty] | - | 0-Noise |  |  | Epic #4 | Not Completed |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | TTT |  |  | Epic #3 | Not Completed | 0 | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | 13 | Sales |  |  | Epic #8 | Not Completed | 0 | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | - | TTT |  |  | Epic #6 | Not Completed | 0 | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | 5 | TFS |  |  | Epic #9 | Not Completed | 3 | 2 | 3 | 0 | 1 | 0 | 2
[5 empty] | 13 | TNT |  |  | Epic #10 | Not Completed | 3 | 2 | 3 | 0 | 1 | 0 | 2
[5 empty] | - | Papillon |  |  | Epic #1 | Not Completed | 3 | 2 | 0 | 3 | 1 | 0 | 2
[5 empty] | 5 | Payment |  |  | Epic #8 | Not Completed | 8 | 2 | 5 | 3 | 6 | 0 | 2
[5 empty] | 13 | Papillon |  |  | Epic #9 | Not Completed | 8 | 2 | 8 | 0 | 6 | 0 | 2
[5 empty] | - | Papillon |  |  | Epic #1 | Not Completed | 8 | 2 | 0 | 8 | 6 | 0 | 2
[5 empty] | 5 | TNT |  |  | Epic #4 | Not Completed | 21 | 2 | 5 | 16 | 19 | 0 | 2
[5 empty] | 13 | TFS |  |  | Epic #4 | Not Completed | 21 | 2 | 13 | 8 | 19 | 0 | 2
[5 empty] | - | Synergy |  |  | Epic #1 | Not Completed | 21 | 2 | 0 | 21 | 19 | 0 | 2
[5 empty] | 5 | Payment |  |  | Epic #8 | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
[5 empty] | 13 | TNT |  |  | Epic #4 | Not Completed |  | 2 | 13 | 0 | 11 | 0 | 2
[5 empty] | - | Vlinder |  |  | Epic #6 | Not Completed |  | 2 | 0 | 0 | -2 | 0 | 2
[5 empty] | 5 | Synergy |  |  | Epic #4 | Not Completed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | Payment |  |  | Epic #1 | Not Completed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | - | 0-Noise |  |  | Epic #5 | Not Completed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Sales |  |  | Epic #7 | Not Completed | 3 |  | 3 | 0 | 0 | 0 | 3
[5 empty] | 13 | TNT |  |  | Epic #8 | Not Completed | 3 |  | 3 | 0 | 0 | 0 | 3
[5 empty] | - | Papillon |  |  | Epic #10 | Not Completed | 3 |  | 0 | 3 | 0 | 0 | 3
[5 empty] | 5 | Payment |  |  | Epic #10 | Not Completed | 8 |  | 5 | 3 | 0 | 0 | 8
[5 empty] | 13 | TTT |  |  | Epic #5 | Not Completed | 8 |  | 8 | 0 | 0 | 0 | 8
[5 empty] | - | Synergy |  |  | Epic #3 | Not Completed | 8 |  | 0 | 8 | 0 | 0 | 8
[5 empty] | 5 | Engineering |  |  | Epic #3 | Not Completed | 21 |  | 5 | 16 | 0 | 0 | 21
[5 empty] | 13 | TNT |  |  | Epic #7 | Not Completed | 21 |  | 13 | 8 | 0 | 0 | 21
[5 empty] | - | TFS |  |  | Epic #5 | Not Completed | 21 |  | 0 | 21 | 0 | 0 | 21
[5 empty] | 5 | Synergy |  |  | Epic #2 | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
[5 empty] | 13 | Papillon |  |  | Epic #4 | Not Completed |  |  | 13 | 0 | 0 | 0 | 13
[5 empty] | - | Papillon |  |  | Epic #3 | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | TNT | yes |  | Epic #2 | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | TTT | yes |  | Epic #4 | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | - | 0-Noise | yes |  | Epic #7 | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Synergy | yes |  | Epic #9 | Removed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | 13 | TFS | yes |  | Epic #9 | Removed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | - | TTT | yes |  | Epic #4 | Removed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | 5 | Sales | yes |  | Epic #6 | Removed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | 13 | TFS | yes |  | Epic #6 | Removed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | - | 0-Noise | yes |  | Epic #1 | Removed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | 5 | 0-Noise | yes |  | Epic #8 | Removed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | 13 | 0-Noise | yes |  | Epic #8 | Removed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | - | Papillon | yes |  | Epic #10 | Removed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | 5 | 0-Noise | yes |  | Epic #3 | Removed |  | 0 | 0 | 5 | 5 | 0 | 0
[5 empty] | 13 | Vlinder | yes |  | Epic #10 | Removed |  | 0 | 0 | 13 | 13 | 0 | 0
[5 empty] | - | Synergy | yes |  | Epic #5 | Removed |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Vlinder | yes |  | Epic #6 | Removed | 0 | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | 13 | Sales | yes |  | Epic #7 | Removed | 0 | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | - | Papillon | yes |  | Epic #8 | Removed | 0 | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | 5 | TFS | yes |  | Epic #8 | Removed | 3 | 2 | 0 | 3 | 1 | 2 | 0
[5 empty] | 13 | Sales | yes |  | Epic #8 | Removed | 3 | 2 | 0 | 3 | 1 | 2 | 0
[5 empty] | - | Payment | yes |  | Epic #10 | Removed | 3 | 2 | 0 | 3 | 1 | 2 | 0
[5 empty] | 5 | 0-Noise | yes |  | Epic #1 | Removed | 8 | 2 | 0 | 8 | 6 | 2 | 0
[5 empty] | 13 | Engineering | yes |  | Epic #9 | Removed | 8 | 2 | 0 | 8 | 6 | 2 | 0
[5 empty] | - | Vlinder | yes |  | Epic #2 | Removed | 8 | 2 | 0 | 8 | 6 | 2 | 0
[5 empty] | 5 | 0-Noise | yes |  | Epic #5 | Removed | 21 | 2 | 0 | 21 | 19 | 2 | 0
[5 empty] | 13 | Synergy | yes |  | Epic #10 | Removed | 21 | 2 | 0 | 21 | 19 | 2 | 0
[5 empty] | - | TNT | yes |  | Epic #7 | Removed | 21 | 2 | 0 | 21 | 19 | 2 | 0
[5 empty] | 5 | TNT | yes |  | Epic #5 | Removed |  | 2 | 0 | 5 | 3 | 2 | 0
[5 empty] | 13 | Payment | yes |  | Epic #1 | Removed |  | 2 | 0 | 13 | 11 | 2 | 0
[5 empty] | - | Sales | yes |  | Epic #7 | Removed |  | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | 5 | Papillon | yes |  | Epic #5 | Removed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | TNT | yes |  | Epic #10 | Removed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | - | TNT | yes |  | Epic #3 | Removed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Sales | yes |  | Epic #4 | Removed | 3 |  | 0 | 3 | 0 | 3 | 0
[5 empty] | 13 | Synergy | yes |  | Epic #3 | Removed | 3 |  | 0 | 3 | 0 | 3 | 0
[5 empty] | - | TNT | yes |  | Epic #4 | Removed | 3 |  | 0 | 3 | 0 | 3 | 0
[5 empty] | 5 | Sales | yes |  | Epic #4 | Removed | 8 |  | 0 | 8 | 0 | 8 | 0
[5 empty] | 13 | TFS | yes |  | Epic #5 | Removed | 8 |  | 0 | 8 | 0 | 8 | 0
[5 empty] | - | TFS | yes |  | Epic #3 | Removed | 8 |  | 0 | 8 | 0 | 8 | 0
[5 empty] | 5 | 0-Noise | yes |  | Epic #5 | Removed | 21 |  | 0 | 21 | 0 | 21 | 0
[5 empty] | 13 | TFS | yes |  | Epic #1 | Removed | 21 |  | 0 | 21 | 0 | 21 | 0
[5 empty] | - | TTT | yes |  | Epic #7 | Removed | 21 |  | 0 | 21 | 0 | 21 | 0
[5 empty] | 5 | Engineering | yes |  | Epic #10 | Removed |  |  | 0 | 5 | 0 | 5 | 0
[5 empty] | 13 | Vlinder | yes |  | Epic #5 | Removed |  |  | 0 | 13 | 0 | 13 | 0
[5 empty] | - | 0-Noise | yes |  | Epic #4 | Removed |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | 0-Noise |  |  | Epic #1 | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | Synergy |  |  | Epic #3 | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | - | 0-Noise |  |  | Epic #4 | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | TTT |  |  | Epic #5 | Removed | 3 | 0 | 3 | 0 | 3 | 0 | 0
[5 empty] | 13 | 0-Noise |  |  | Epic #2 | Removed | 3 | 0 | 3 | 0 | 3 | 0 | 0
[5 empty] | - | TTT |  |  | Epic #6 | Removed | 3 | 0 | 0 | 3 | 3 | 0 | 0
[5 empty] | 5 | TTT |  |  | Epic #3 | Removed | 8 | 0 | 5 | 3 | 8 | 0 | 0
[5 empty] | 13 | Payment |  |  | Epic #9 | Removed | 8 | 0 | 8 | 0 | 8 | 0 | 0
[5 empty] | - | Papillon |  |  | Epic #6 | Removed | 8 | 0 | 0 | 8 | 8 | 0 | 0
[5 empty] | 5 | 0-Noise |  |  | Epic #10 | Removed | 21 | 0 | 5 | 16 | 21 | 0 | 0
[5 empty] | 13 | TTT |  |  | Epic #1 | Removed | 21 | 0 | 13 | 8 | 21 | 0 | 0
[5 empty] | - | TTT |  |  | Epic #5 | Removed | 21 | 0 | 0 | 21 | 21 | 0 | 0
[5 empty] | 5 | 0-Noise |  |  | Epic #6 | Removed |  | 0 | 5 | 0 | 5 | 0 | 0
[5 empty] | 13 | TTT |  |  | Epic #7 | Removed |  | 0 | 13 | 0 | 13 | 0 | 0
[5 empty] | - | TTT |  |  | Epic #2 | Removed |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Vlinder |  |  | Epic #5 | Removed | 0 | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | 13 | Engineering |  |  | Epic #2 | Removed | 0 | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | - | TNT |  |  | Epic #7 | Removed | 0 | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | 5 | Synergy |  |  | Epic #8 | Removed | 3 | 2 | 3 | 0 | 1 | 2 | 0
[5 empty] | 13 | Payment |  |  | Epic #10 | Removed | 3 | 2 | 3 | 0 | 1 | 2 | 0
[5 empty] | - | TNT |  |  | Epic #8 | Removed | 3 | 2 | 0 | 3 | 1 | 2 | 0
[5 empty] | 5 | TNT |  |  | Epic #2 | Removed | 8 | 2 | 5 | 3 | 6 | 2 | 0
[5 empty] | 13 | Engineering |  |  | Epic #10 | Removed | 8 | 2 | 8 | 0 | 6 | 2 | 0
[5 empty] | - | TFS |  |  | Epic #1 | Removed | 8 | 2 | 0 | 8 | 6 | 2 | 0
[5 empty] | 5 | TNT |  |  | Epic #6 | Removed | 21 | 2 | 5 | 16 | 19 | 2 | 0
[5 empty] | 13 | 0-Noise |  |  | Epic #8 | Removed | 21 | 2 | 13 | 8 | 19 | 2 | 0
[5 empty] | - | Vlinder |  |  | Epic #7 | Removed | 21 | 2 | 0 | 21 | 19 | 2 | 0
[5 empty] | 5 | TFS |  |  | Epic #6 | Removed |  | 2 | 5 | 0 | 3 | 2 | 0
[5 empty] | 13 | Vlinder |  |  | Epic #10 | Removed |  | 2 | 13 | 0 | 11 | 2 | 0
[5 empty] | - | TTT |  |  | Epic #10 | Removed |  | 2 | 0 | 0 | -2 | 2 | 0
[5 empty] | 5 | Vlinder |  |  | Epic #7 | Removed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 13 | Sales |  |  | Epic #9 | Removed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | - | Sales |  |  | Epic #1 | Removed | 0 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 5 | Engineering |  |  | Epic #8 | Removed | 3 |  | 3 | 0 | 0 | 3 | 0
[5 empty] | 13 | Engineering |  |  | Epic #10 | Removed | 3 |  | 3 | 0 | 0 | 3 | 0
[5 empty] | - | TTT |  |  | Epic #4 | Removed | 3 |  | 0 | 3 | 0 | 3 | 0
[5 empty] | 5 | Vlinder |  |  | Epic #5 | Removed | 8 |  | 5 | 3 | 0 | 8 | 0
[5 empty] | 13 | TTT |  |  | Epic #7 | Removed | 8 |  | 8 | 0 | 0 | 8 | 0
[5 empty] | - | Payment |  |  | Epic #1 | Removed | 8 |  | 0 | 8 | 0 | 8 | 0
[5 empty] | 5 | Sales |  |  | Epic #1 | Removed | 21 |  | 5 | 16 | 0 | 21 | 0
[5 empty] | 13 | Papillon |  |  | Epic #2 | Removed | 21 |  | 13 | 8 | 0 | 21 | 0
[5 empty] | - | 0-Noise |  |  | Epic #1 | Removed | 21 |  | 0 | 21 | 0 | 21 | 0
[5 empty] | 5 | Payment |  |  | Epic #6 | Removed |  |  | 5 | 0 | 0 | 5 | 0
[5 empty] | 13 | 0-Noise |  |  | Epic #9 | Removed |  |  | 13 | 0 | 0 | 13 | 0
[5 empty] | - | TTT |  |  | Epic #7 | Removed |  |  | 0 | 0 | 0 | 0 | 0

## Sprint_3_1u2
Sprint 2025_3_1/2, 08.07.2025 - 05.08.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-Over sensitive [SOs] and Carry-Over sensitive [COs])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Payment | 20 | 9 | 44 | 11 | 28 | 17 | 10 | 55 |  | 38 | 11 | 26 | 6 | 17 | 68.42%
|  | Sales | 43 | 39 | 78 | 73 | 132 | 19 | 0 | 151 |  | 78 | 73 | 132 | 0 | 19 | 169.2%
|  | Vlinder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TTT | 22 | 19 | 47 | 33 | 66 | 14 | 0 | 80 |  | 37 | 33 | 56 | 0 | 14 | 151.4%
|  | TNT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | TFS | 20 | 13 | 72 | 0 | 51 | 21 | 0 | 72 |  | 62 | 0 | 41 | 0 | 21 | 66.13%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Papillon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Total | 105 | 80 | 241 | 117 | 277 | 71 | 10 | 358 |  | 215 | 117 | 255 | 6 | 71 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 67 | 247 | 38 | 119 | 105 | 366 | 101 | 358 | 4 | 8 | 105 | 366
|  | Completed | 50 | 184 | 30 | 93 | 80 | 277 | 80 | 277 | 0 | 0 | 80 | 277
|  | Not Completed | 13 | 49 | 7 | 24 | 20 | 73 | 19 | 71 | 1 | 2 | 20 | 73
|  | Removed | 4 | 14 | 1 | 2 | 5 | 16 | 2 | 10 | 3 | 6 | 5 | 16
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Epic | Status | Carry-over | Spill-over | COsSP Initially Planned | COsSP Pulled after Start | CSOsSP Completed | CSOsSP Removed | CSOsSP Not Completed
ANP-29057 | Parameter replication is not working on till level/Tills had to be manually rebooted to trigger update | bug | 1 | closed | 5 | Payment | yes | M |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28913 | Workaround for TIM Terminal 3.41 issue for NEWPOSS 4.12.0 | bug | 1 | closed | 3 | Payment | yes | M |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25440 | Logfiles: Multi-Lane Till Development | story | 3 | closed | 3 | Payment |  | M | [ANP-22244] Collect Logfiles in /var/log | Completed | 0 |  | 0 | 0 | 0 | 0 | 0
ANP-27041 | Switch Transaction Data Endpoints | story | 3 | in acceptance | 5 | Payment |  | PD | [ANP-25952] Backoffice Transaction Data Refactoring - Switch Transaction data endpoints (MCO) | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-28397 | EFT IT - Card information mapping to MeansOfPayment (MCO) | bug | 2 | closed | 2 | Payment |  | M; preliminary retrospective estimation by RE |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-28543 | refine short-notice bugs prior to processing | task | 1 | closed | 3 | Payment |  | M; preliminary value summing up analysis for ANP-28399, 28370, 28170 |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25064 | Store- credit card payments against signature, the merchant receipt will no longer be printed- EM: no | story | 2 | in development | 5 | Payment |  | PD; issue type changed from bug to story | [ANP-24505] MCO #04 ¦ [INT] Transaction Data | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-28370 | Integrate POS-3724: Means of Payment cannot be resolved for MCO with TIM implementation | story | 2 | concept design | - | Payment |  | M | [ANP-24505] MCO #04 ¦ [INT] Transaction Data | Removed |  |  | 0 | 0 | 0 | 0 | 0
ANP-28399 | Integrate POS-3729: Means of Payment cannot be resolved for MCO with direct implementation for IT | story | 2 | concept design | - | Payment | yes | M; retrospective estimation by RE | [ANP-24505] MCO #04 ¦ [INT] Transaction Data | Removed |  |  | 0 | 0 | 0 | 0 | 0
ANP-28170 | Integrate POS-3728: INC5253414 - Means of Payment cannot be resolved for MCO | story | 3 | concept design | - | Payment |  | M; retrospective estimation by RE | [ANP-24505] MCO #04 ¦ [INT] Transaction Data | Removed |  |  | 0 | 0 | 0 | 0 | 0
ANP-28571 | [MCO] AT: Fiscalization error | bug | 2 | closed | 3 | Payment |  | M | [ANP-27720] MCO #01 ¦ Fiscalization | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25955 | Customers get charged more than the total receipt sum | bug | 3 | blocked | 5 | Payment |  | M | [ANP-24505] MCO #04 ¦ [INT] Transaction Data | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-28354 | INC5323862 - Unrecoverable error (UK) | bug | 3 | blocked | 5 | Payment |  | M; moved to CHO |  | Removed |  | 3 | 5 | 0 | 2 | 3 | 0
ANP-28355 | INC5366201 - Unrecoverable error (UK) during logIn process | bug | 3 | blocked | 5 | Payment |  | M; moved to CHO |  | Removed |  | 3 | 5 | 0 | 2 | 3 | 0
ANP-28469 | Till prints wrong card payment information and doesn't charge customer after failed payment | bug | 3 | in development | 5 | Payment |  | M | [ANP-24505] MCO #04 ¦ [INT] Transaction Data | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-28506 | set up testlab for ANP-25541 | task | 3 | in progress | - | Payment |  | M |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-28536 | [SPIKE] Prep&Spec: POS<->ACI Interface | story | 3 | closed | 3 | Payment |  | PD | [ANP-27742] MCO Base - Conceptional preparation for HFBC (Healthy Food Benefits Card) | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-28938 | Pick Tickets for 4.7.15 | story | 3 | closed | 1 | Payment | yes | RT |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28946 | Pick Tickets for 4.7.16 | story | 3 | open | 1 | Payment | yes | RT |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
ANP-27222 | Analysis of ANP-26719: EFT after Total / Discount coupon in advanced tendering mode leads to a lost receipt | story | 2 | in development | 1 | Payment | yes | M |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
NPSCO-22216 | Cherry Pick 4.23.1 | task | 3 | CLOSED | 1 | TFS |  | RT |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-21098 | Cherry Pick Down Merge EGC Maintenance Release 4.13.3 | task | 3 | IN PROGRESS | 13 | TFS |  | RT |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-22347 | Adjust Means of Payments values in CFRM parameter for SCO | task | 2 | IN PROGRESS | 2 | TFS |  | M |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-22101 | For failed card payments the SCO sends paymentTypes unknown to the BO | bug | 2 | CLOSED | 3 | TFS |  | M |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-22302 | [AUS] EFT devices constantly loose connection | bug | 2 | IN DEVELOPMENT | 3 | TFS |  | M |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-21717 | EFT IT - Card information mapping to MeansOfPayment (SCO) | bug | 2 | IN REVIEW | 3 | TFS |  | M |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-21824 | EFT data is missing with autocommit = false in the tim config | bug | 2 | CLOSED | 2 | TFS |  | M |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-15181 | Restrict iptables rule to EFT Terminals | bug | 3 | BLOCKED | 2 | TFS |  | M |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
NPSCO-21799 | [SCO CH] Apply rounding logic for EGC payment | story | 3 | IN DEVELOPMENT | 3 | TFS |  | PD |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-21166 | Timeout when paying with event voucher only restricted items | bug | 3 | CLOSED | 3 | TFS |  | M |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20230 | Implement Jenkins client for building and following jobs | task | 3 | CLOSED | 3 | TFS |  | M |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21910 | Test - Pick EGC features to ER 4.1 | task | 3 | IN PROGRESS | 5 | TFS |  | RT |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-21181 | Test Task Release 4.13.2 | task | 3 | READY | 3 | TFS |  | RT |  | Not Completed | 3 |  | 3 | 0 | 0 | 0 | 3
NPSCO-21831 | Onboarding Claudia Wipperfeld | task | 3 | IN PROGRESS | 5 | TFS |  | M |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-21833 | Onboarding Simone Lindner | task | 3 | IN PROGRESS | 5 | TFS |  | M |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-21835 | Onboarding Timothy Ernst | task | 3 | IN PROGRESS | 5 | TFS |  | M |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-22269 | Test Task Release 4.23.1 | task | 3 | IN PROGRESS | 3 | TFS |  | RT |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-22409 | EFT data is missing with autocommit = false in the tim config - Releases 4.23.2 & 5.0.0 | bug | 2 | READY | 2 | TFS |  | M |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
NPSCO-22396 | Cherry Pick for Maintenance Release 4.13.2 | task | 3 | CLOSED | 3 | TFS |  | RT |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-22382 | SCO adds cash payment to receipt after pressing contactless resulting in a loss for ALDI | bug | 1 | CLOSED | 3 | TFS |  | M |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21992 | Cherry Pick 3.18.8 | task | 3 | Closed | 1 | TTT | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-20297 | Pick EGC features to ER 4.1 (Sales) | story | 3 | In Development | 8 | TTT |  |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-21115 | Test - Pick EGC features to ER 4.1 (Sales) | task | 3 | In Progress | 8 | TTT |  |  |  | Not Completed | 8 |  | 8 | 0 | 0 | 0 | 8
NPSCO-20414 | Change DN call for driver licence button | story | 3 | Closed | 5 | TTT |  |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-21296 | Customer Intervention when scanning EGC is not shown when "recharge" is selected | bug | 3 | Closed | 3 | TTT |  |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-21706 | EGC payment is not labeled on the CH receipt | bug | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21840 | Include receipt number in the requests to the etc interface | story | 3 | Closed | 5 | TTT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-21681 | Purchase clears the finalized transaction after 24h (not 3h) | story | 3 | Closed | 2 | TTT |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-21491 | [UK] Customer intervention in Sales | story | 3 | Closed | 2 | TTT |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20797 | Change LayoutIDs for PinPrinting | story | 3 | In Development | 5 | TTT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20648 | Discounts are using wrong format on the receipt/Ejournal | bug | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18838 | Attendant intervention for weight input is not triggered immediately after a WERW item is added by itemid | bug | 3 | Closed | 5 | TTT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-22081 | Gather data for main driver SCO #02 ¦ [INT] SCOs Offline & SCOs showing offline on ATS | task | 3 | Ready | 5 | TTT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-21815 | Split up deposit values per tax class on the Till Reports | story | 3 | In Development | 5 | TTT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-21855 | Cherry Pick to Release 4.23.1 (ER 4.2C.1) | task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-22034 | Release Test 4.23.1 | task | 3 | Closed | 2 | TTT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-22073 | Release test 3.18.8 | task | 3 | Closed | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-22373 | Release Test 4.13.2 | task | 3 | In Progress | 2 | TTT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-22428 | US Tax calculation for PinPrinting | bug | 3 | In Development | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20447 | Epay export failure after an empty card was ringed (Mock only) | bug | 3 | In Development | 3 | TTT | yes |  |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-22361 | Check if Delta Update for Articles deletes Entry in DB or sets it to Deleted and import newer version | task | 3 | In Progress | 3 | TTT | yes |  |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-22522 | Analysis and support for VSS-2258 | task | 3 | Closed | 1 | TTT | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-26854 | Avoid boot loops due to unnecessary restarts triggered due to unavailable NEWPOSS Store Server | Story | 3 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27133 | Warranty text is not printed on receipt | Bug | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27150 | [Infinity] SAP FICO - problems with the sales foreign currency postings - no em | Bug | 4 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27424 | Implementation of new till sharing functionality 21+CODE for GB/IE | Story | 3 | Closed | 8 | Sales |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-27468 | Determine differences between receipt layout configuration in production and provided configuration scripts | Task | 1 | Closed | 8 | Sales |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-27483 | StringTokenizer does not return empty tokens, leading to multiple line breaks being unrecognized | Bug | 3 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27580 | Analysis capturing of lottery items and related receipt position creation [half a day] | Task | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27613 | Remove capturing and printing of pensioner ids | Story | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27638 | RIE [Stores] Multiple Articles affected - Wrong price for the single bottle. (Pfandartikel) | Bug | 4 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27693 | Build MCO part of NEWPOSS release 4.7.12 | Story | 3 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27698 | Adjust US receipt layout regarding weight and tare label | Story | 1 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27713 | Brainstorming on fraud protection mechanism on MCO | Task | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27715 | PI Planning and effort estimation | Task | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27716 | Pick of the compacting mechanism to ER 4.1/NEWPOSS 4.7 | Story | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27718 | Include receipt number in the requests to the etc interface | Story | 3 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27761 | Analyse and Fix Nullpointer in HUFCUFixture fixtures.pos.fiscalization.hu.hufcu, HUEuroSwitchFixture fixtures.pos.fiscalization.hu.hueuroswitch and HUFiscalizationTillFixture fixtures.pos.fiscalization.hu.hufiscalizationtill | Story | 3 | Closed | 8 | Sales | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-27769 | Remove layout tests from HU related integrity tests | Story | 3 | Closed | 5 | Sales |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-27974 | HU 4.7.11/1.26.7.11 HU Special Characters in Layout are shown as '?' | Bug | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27993 | [UK] EFT EndOfDay not triggered by ACO tilljobevent | Bug | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27997 | [UK] EndOfDay not triggered by quartz scheduler | Bug | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28000 | Re-enable owasp plugin for all MCO repositories | Story | 3 | Closed | 1 | Sales | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28165 | Build MCO part of NEWPOSS release 4.7.13 | Story | 3 | Closed | 1 | Sales | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28175 | Till restart message appearing on MCO #1 | Bug | 2 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28205 | Build MCO part of NEWPOSS release 4.10.1 | Story | 3 | Closed | 2 | Sales | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-28356 | Build MCO part of NEWPOSS release 4.7.14 | Story | 3 | Closed | 2 | Sales | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-28405 | [US] Till requests pickup drop before the cash limit is reached | Bug | 2 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-17348 | Validate master data retrieved from back office server via ACO before import | Story | 3 | In Development | 8 | Sales |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25038 | Maven install command fails | Bug | 3 | Closed | 5 | Sales |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26738 | Analyse back office communication and prevent calls in offline state | Story | 3 | Closed | 8 | Sales |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26888 | Remove non-layout business logic from AldiItemReceiptPosition BO | Story | 3 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27170 | Items with UPC-A Barcode starting with "26" are added to receipt with quantity of zero | Bug | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-28174 | ESL - incorrect receipt info on product - N/A | Bug | 4 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28226 | AU Store - Articles/Items printed double on receipts | Bug | 4 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28359 | Support with manual tests in testlab | Task | 1 | Closed | 5 | Sales | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28385 | Adjust receipt layout differences (CFRM vs till-dev) based on analysis results | Story | 3 | Closed | 5 | Sales | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28500 | [MCO] Superfluous lines on receipts - 4.1C5 version | Bug | 4 | In Development | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26491 | Harmonize Voiding for POSA and POR items | Story | 3 | In Development | 8 | Sales | yes |  |  | Not Completed |  |  | 0 | 8 | 0 | 0 | 8
ANP-28557 | Improve documentation for Till Sharing feature | Task | 3 | Open |  | Sales |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-28559 | Review of the backlog | Task | 3 | In Development | 3 | Sales |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-28560 | Knowledge transfer and overview regarding Till Sharing | Task | 3 | Open |  | Sales |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-28349 | Show all available tax classes in respective country on the Till/Financial Reports (18/8+Code) | Story | 3 | In Development | 5 | Sales | yes |  |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
ANP-28350 | Adapt the displaying of the currency on the Till/Financial Reports (18/8+Code) | Story | 3 | In Development | 3 | Sales | yes |  |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-25700 | Harmonize suspend & retrieve workflow for POSA and POR items | Story | 3 | Closed | 5 | Sales |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_2_5u6
Sprint 2025_2-5/6, 10.06.2025 - 08.07.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-Over sensitive [SOs] and Carry-Over sensitive [COs])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | Completed of Initially Planned | Completed of Pulled after Sprint
| > > > > Use exactly these team names! > > > > | Engineering | 33 | 23 | 104 | 20 | 83 | 41 | 0 | 124 |  | 104 | 20 | 83 | 0 | 41 | 79.81% | 68 | 15
|  | Payment | 13 | 11 | 20 | 10 | 25 | 3 | 2 | 30 |  | 18 | 12 | 26 | 2 | 2 | 144.4% | 15 | 10
|  | Sales | 36 | 27 | 68 | 56 | 81 | 43 | 0 | 124 |  | 57 | 56 | 80 | 0 | 33 | 140.4% | 44 | 37
|  | Vlinder | 17 | 13 | 52 | 24 | 52 | 24 | 0 | 76 |  | 52 | 24 | 65 | 0 | 11 | 125% | 36 | 16
|  | TTT | 21 | 17 | 52 | 19 | 47 | 24 | 0 | 71 |  | 45 | 19 | 50 | 0 | 14 | 111.1% | 36 | 11
|  | TNT | 28 | 20 | 59 | 28 | 63 | 24 | 0 | 87 |  | 59 | 29 | 64 | 0 | 24 | 108.5% | 44 | 19
|  | TFS | 23 | 20 | 43 | 19 | 43 | 19 | 0 | 62 |  | 43 | 19 | 53 | 0 | 9 | 123.3% | 27 | 16
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
|  | Synergy | 90 | 79 | 81 | 91 | 151 | 21 | 0 | 172 |  | 81 | 91 | 151 | 0 | 21 | 186.4% | 73 | 78
|  | Papillon | 24 | 17 | 77 | 33 | 59 | 51 | 0 | 110 |  | 77 | 33 | 97 | 0 | 13 | 126% | 44 | 15
|  | Total | 171 | 131 | 398 | 176 | 394 | 178 | 2 | 574 |  | 378 | 179 | 421 | 2 | 134 | --- | 270 | 124
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 162 | 560 | 123 | 300 | 285 | 860 | 283 | 856 | 2 | 4 | 285 | 860
|  | Completed | 129 | 391 | 98 | 217 | 227 | 608 | 225 | 604 | 2 | 4 | 227 | 608
|  | Not Completed | 32 | 167 | 25 | 83 | 57 | 250 | 57 | 250 | 0 | 0 | 57 | 250
|  | Removed | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 0 | 1 | 2
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Epic | Status | Carry-over | Spill-over | COsSP Initially Planned | COsSP Pulled after Start | CSOsSP Completed | CSOsSP Removed | CSOsSP Not Completed
ANP-28241 | EFTPOS key not working on 4.1 C6 | Bug | 1 | closed | 5 | Payment | yes | M |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28122 | Authorisation Code not sent with EFT Transaction on OPI | Bug | 2 | closed | 2 | Payment | yes | M |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-27669 | [UK] Integrate POS Core for OPI boolean fix | Bug | 2 | closed | 2 | Payment |  | M |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-27197 | Build MCO part of NEWPOSS release 4.10.0 | Story | 3 | closed | 3 | Payment |  | RT |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27238 | EFT data is missing with autocommit = false in the tim config | Bug | 2 | closed | 3 | Payment |  | M | [ANP-26021] OPS & Support Initiative | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-27564 | Analysis of ANP-24330: POS3 - CHOP - NCR 7199 PinPrinting not correct | Story | 2 | closed | 1 | Payment |  | M | [ANP-26021] OPS & Support Initiative | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-27245 | additional Analysis of ANP-25541: [CHOP] Global Blue (12+Code) not working for card payments and last receipt | Story | 3 | blocked | 2 | Payment |  | M | [ANP-18572] CHOP AT [DMND0061403] | Removed | 2 | 2 | 2 | 0 | 0 | 2 | 0
ANP-28132 | Integrate POS-Core 2.7.61 in MCO Till | Story | 3 | closed | 1 | Payment | yes | RT |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27211 | Build MCO part of NEWPOSS release 4.11.0 | Story | 3 | closed | 3 | Payment |  | RT |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25440 | Logfiles: Multi-Lane Till Development | Story | 3 | in development | 3 | Payment |  | M; formal spill-over | [ANP-22244] Collect Logfiles in /var/log | Completed | 1 | 0 | 1 | 0 | 1 | 0 | 0
ANP-26704] | [SPIKE] Multilane Mock improvement for application tests | Story | 3 | closed | 1 | Payment | yes | RT | [ANP-9451] Development Improvements for MCO | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27041 | Switch Transaction Data Endpoints | Story | 3 | in development | 3 | Payment |  | PD | [ANP-25952] Backoffice Transaction Data Refactoring - Switch Transaction data endpoints (MCO) | Not Completed | 5 | 2 | 3 | 2 | 3 | 0 | 2
ANP-28374 | Pick Tickets to 4.7.14 | Story | 3 | closed | 1 | Payment | yes | RT |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-17305 | Deploy POS-App-Adapter in the combined services JVM | Story | 3 | BLOCKED | 1 | TNT |  |  |  | Completed |  | 7 | 1 | 0 | 1 | 0 | 0
NPSCO-20626 | SCO No POS Connection after Update (postrgres migration fails) | Bug | 1 | CLOSED | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19917 | SCO ¦ [KW14] 0% VAT rate mapping issues | Bug | 2 | CLOSED | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19395 | Update RP Services | Story | 3 | CLOSED | 5 | TNT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16137 | SCO device manager hardware device information interface | Story | 3 | CLOSED | 3 | TNT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20363 | Adapt configure.xml to provide monitored item MQTT user and secret | Story | 3 | CLOSED | 5 | TNT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20806 | Extension of the heartbeat message to include "unsentmessages" and "unsenterromessages" | Story | 3 | CLOSED | 5 | TNT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20799 | Incorrect creation of log file path [RP Services Log Files] | Bug | 2 | CLOSED | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21174 | Test Release 4.22 | Task | 3 | CLOSED | 5 | TNT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-21079 | Transmit correct unit quantity | Story | 3 | CLOSED | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21175 | [Spike] Evaluate if PosCore changes to support AIDs with increased length break payment processing | Task | 3 | CLOSED | 2 | TNT |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-21241 | JAXB-IMPL missing after Java 17 upgrade when paying by card in UK | Bug | 3 | CLOSED | 3 | TNT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21381 | Setup docker images for Rocky Linux based VSS International R32 | Task | 3 | CLOSED | 2 | TNT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21274 | Error in pos connection after restarting infra adaper | Bug | 3 | CLOSED | 3 | TNT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21480 | Test Release 4.23 | Task | 3 | CLOSED | 5 | TNT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-21519 | Build Hotfix 4.22.1 | Task | 1 | CLOSED | 2 | TNT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21545 | Analyse SCO freeze live incident INC5353424 | Task | 3 | CLOSED | 1 | TNT | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-18575 | [DE] Receipt sometimes shows "TSE not reachable" for no apparent reason | Bug | 3 | CLOSED | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16394 | Integrate Purchase Service into single JVM deployment | Story | 3 | IN DEVELOPMENT | 3 | TNT |  |  |  | Completed |  | 5 | 3 | 0 | 3 | 0 | 0
NPSCO-19202 | Implement Firewalld Configuration for SCO | Story | 3 | CLOSED | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15567 | Open Port 5665 for CheckMK | Story | 3 | CLOSED | 3 | TNT |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17964 | Set taxBase value to the second BOGOF item in export | Story | 3 | CLOSED | 3 | TNT |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-20879 | Create Masterdata Service | Story | 3 | IN DEVELOPMENT | 5 | TNT |  |  |  | Not Completed |  | 8 | 5 | 0 | -3 | 0 | 8
NPSCO-21276 | Some Celonis events are missing values | Bug | 3 | IN DEVELOPMENT | 2 | TNT |  |  |  | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
NPSCO-21123 | Enhancement item price | Story | 3 | CLOSED | 2 | TNT | yes |  |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
NPSCO-21122 | on/off switch for publishing events | Story | 3 | CLOSED | 5 | TNT | yes |  |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
NPSCO-17408 | [Tech Debt Task] Implement a purchase command for adding extension properties only - follow up | Task | 3 | IN PROGRESS | 2 | TNT |  |  |  | Not Completed | 3 | 1 | 2 | 1 | 2 | 0 | 1
NPSCO-21067 | [Spike] Collect usage statistics for Monitored Item Adapter | Task | 3 | IN PROGRESS | 2 | TNT | yes |  |  | Not Completed |  | 1 | 0 | 2 | 1 | 0 | 1
NPSCO-21310 | [UK] Transactions can't be processed in BO after switching from pepper to direct integration (opi) | Bug | 1 | CLOSED | 3 | TFS | yes |  |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-21478 | Authorisation Code not Sent with EFT Transaction on OPI | Bug | 3 | IN DEVELOPMENT | 3 | TFS | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20690 | Deactivate Force close in UK | Story | 3 | CLOSED | 5 | TFS |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-21169 | Test event voucher after epay adjustments (aHead) | Task | 3 | CLOSED | 1 | TFS |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20446 | Add objectType to cardTransactionData object | Story | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21298 | Card transaction data for voided EFT payments are not printed on the receipt. | Bug | 2 | CLOSED | 2 | TFS | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21098 | Cherry Pick Down Merge EGC Maintenance Release 4.13.3 | Task | 3 | IN PROGRESS | 13 | TFS |  |  |  | Not Completed |  | 3 | 13 | 0 | 10 | 0 | 3
NPSCO-21482 | [UK] Prevent Force Close: Restrict partial/split payments with EGC items to avoid incorrect transactions | Story | 3 | CLOSED | 3 | TFS | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21099 | Build Maintenance Release 4.13.2 | Task | 3 | CLOSED | - | TFS |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-21183 | Test Task Release 4.22.1 | Task | 3 | CLOSED | 2 | TFS |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-21100 | Test Task Release 4.22.0 | Task | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21084 | [UK] Integrate POS Core for OPI boolean fix | Bug | 2 | CLOSED | 2 | TFS |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20317 | Follow up RP ticket purchase error after power off | Bug | 2 | CLOSED | 1 | TFS |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20793 | Correction of Customer Intervention for insufficient Balance during payment | Bug | 3 | CLOSED | 1 | TFS |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-21177 | Build Release 4.23.0 | Task | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21178 | Build Maintenance Release 4.13.3 | Task | 3 | CLOSED | - | TFS |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-21180 | Test Task Release 4.23.0 | Task | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21181 | Test Task Release 4.13.3 | Task | 3 | READY | 3 | TFS |  |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-20795 | Test event voucher (legacy) | Task | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21371 | Estimations for upcoming PI-3 | Task | 3 | CLOSED | 2 | TFS | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21601 | Onboarding Claudia Wipperfeld | Task | 3 | CLOSED | 2 | TFS | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21602 | Onboarding Simone Lindner | Task | 3 | CLOSED | 2 | TFS | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21633 | Onboarding Timothy Ernst | Task | 3 | CLOSED | 2 | TFS | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-26106 | NCR CX8 x CS300 not working in 4.1 release | Bug | 2 | Closed | 8 | Engineering |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26705 | Provide printer configuration to HU fiscal middleware | Story | 3 | Closed | 8 | Engineering |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-27085 | MCO part of CHO-6158 | Story | 3 | Closed | 1 | Engineering |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-28169 | Configure LFS for till-msi maintenance branches | Task | 3 | Closed | 1 | Engineering | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28197 | MCO Part for CHO-6370 | Story | 3 | Closed | 1 | Engineering | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-4600 | Implement CheckMK check that monitors DN scanners on an SCO till | Story | 3 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4826 | [HU] Retain relevant HU middleware files during installation from scratch | Story | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5041 | Provide SCO DN-managed devices information to HWLM | Story | 3 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6370 | Extend device information for Bizerba C2 scale to CMDB | Story | 3 | Closed | 5 | Engineering | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
CHO-6529 | Update HU fiscal middleware artifact | Story | 3 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6651 | HWLM: differentiate between Quest 720 and 850 terminals for cmdb | Story | 3 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6706 | AUS: Scanner/Scales not responding. | Bug | 1 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6707 | ATS - Stuck in boot loop post 3.2 update | Bug | 2 | Closed | 8 | Engineering |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-6750 | Ensure consistent till updates | Bug | 2 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6762 | Add option to reinstall as different till number for support cases | Story | 1 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6813 | Release CHO Artifacts for Store 2014 4.2B | Story | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6821 | Release CHO Artifacts for Store 2014 4.1C6 | Story | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6833 | CHO Part of ANP-26705 | Story | 3 | Closed | 1 | Engineering | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-20457 | Refactor till msi build from its current state to a standard maven build | Story | 3 | Ready | 13 | Engineering |  |  |  | Not Completed |  |  | 13 | 0 | 0 | 0 | 13
ANP-27533 | Update 3.2B9 to 4.1TB2 fails | Bug | 1 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27815 | Software Journal: Faulty permissions prevent Journal.txt to be updated | Bug | 1 | In Development | 3 | Engineering |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-28172 | POS update 3.18.3.1>>3.18.4.1 not automatically triggered | Bug | 2 | Closed | 3 | Engineering | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28187 | Bizerba C2 with Datalogic 9900i encounters "Ausnahmefehler" if cashiers try to weigh with speed | Bug | 1 | In Test | 5 | Engineering | yes |  |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
ANP-28248 | Part of CHO-6651 quest model name mapping | Story | 3 | In Development | 1 | Engineering |  |  |  | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
CHO-4825 | [HU] Add relevant HU middleware files to debug shortcut | Story | 3 | In Development | 2 | Engineering |  |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-6523 | Automatically document release artifact dependencies | Story | 3 | In Development | 5 | Engineering |  |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6665 | Release Sprint 2025_PI2-5/6 Artifacts | Story | 3 | Blocked | 2 | Engineering |  |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-6733 | 4.1C4 - DN Beetle requires manual input after BIOS update | Bug | 3 | Open | 3 | Engineering |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6806 | HU middleware monitoring | Story | 3 | In Review | 5 | Engineering |  |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6831 | Support for MCO + SCO for firewall configuration | Task | 3 | Open | 2 | Engineering |  |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-6832 | Testlab maintenance | Task | 3 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6877 | Support for Niko Lamertz @Aldi | Task | 3 | Closed | 1 | Engineering | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-7029 | Support HU test setups | Task | 3 | Closed | 3 | Engineering | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19621 | Customer button for PinPrinting-DIC menu | Story | 3 | Closed | 5 | TTT |  |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-19620 | Export of PinPrinting items | Story | 3 | Closed | 3 | TTT |  |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-20440 | Button order for Multipack screens | Story | 3 | Closed | 2 | TTT |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20856 | Build 4.22.0 Release | Task | 3 | Closed | 3 | TTT |  |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-21179 | TEST 4.22.0 Release | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21182 | Test 4.2B Release | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20855 | Cancel request for EGC and PinPrinting items to the provider (ETC) failed | Bug | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20647 | [Spike] Change DN call for driver licence button | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20297 | Pick EGC features to ER 4.1 (Sales) | Story | 3 | In Development | 8 | TTT |  |  |  | Not Completed |  | 3 | 8 | 0 | 5 | 0 | 3
NPSCO-20959 | PIN printing articles are unaffected by promotions | Bug | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20854 | PinPrinting items is not counted on SalesReceipt | Bug | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21641 | Requesting balance of EGC does not work if EGC is scanned after clicking the EGC button | Bug | 3 | Closed | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21115 | Test - Pick EGC features to ER 4.1 (Sales) | Task | 3 | In Review | 8 | TTT |  |  |  | Not Completed |  | 8 | 8 | 0 | 0 | 0 | 8
NPSCO-21116 | PI Planning and estimation | Task | 3 | Closed | 2 | TTT |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-21117 | Refund analysis | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20414 | Change DN call for driver licence button | Story | 3 | In Development | 5 | TTT | yes |  |  | Not Completed |  | 2 | 0 | 5 | 3 | 0 | 2
NPSCO-21269 | ExitGate Barcode Time format should be 24h | Story | 3 | Closed | 2 | TTT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21656 | SPR Analysis | Task | 3 | In Progress | 1 | TTT | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-21290 | Add [es-US] translation for EGC Customer intervention in Sales | Story | 3 | In Development | 2 | TTT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21697 | Customer is falsely told EGC payment is not possbile | Bug | 3 | Closed | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21296 | Customer Intervention when scanning EGC is not shown when "recharge" is selected | Bug | 3 | In Development | 3 | TTT | yes |  |  | Not Completed |  | 1 | 0 | 3 | 2 | 0 | 1
ANP-28405 | [US] Till requests pickup drop before the cash limit is reached | Bug | 2 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27993 | [UK] EFT EndOfDay not triggered by ACO tilljobevent | Bug | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27424 | Implementation of new till sharing functionality 21+CODE for GB/IE | Story | 3 | In Development | 8 | Sales |  |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-27997 | [UK] EndOfDay not triggered by quartz scheduler | Bug | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27974 | HU 4.7.11/1.26.7.11 HU Special Characters in Layout are shown as '?' | Bug | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27468 | Determine differences between receipt layout configuration in production and provided configuration scripts | Task | 1 | Closed | 8 | Sales |  |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-28356 | Build MCO part of NEWPOSS release 4.7.14 | Story | 3 | Closed | 2 | Sales | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-28359 | Support with manual tests in testlab | Task | 1 | In Progress | 5 | Sales | yes |  |  | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
ANP-27769 | Remove layout tests from HU related integrity tests | Story | 3 | Closed | 5 | Sales |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-27761 | Analyse and Fix Nullpointer in HUFCUFixture fixtures.pos.fiscalization.hu.hufcu, HUEuroSwitchFixture fixtures.pos.fiscalization.hu.hueuroswitch and HUFiscalizationTillFixture fixtures.pos.fiscalization.hu.hufiscalizationtill | Story | 3 | In Development | 8 | Sales | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-26854 | Avoid boot loops due to unnecessary restarts triggered due to unavailable NEWPOSS Store Server | Story | 3 | In Development | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27718 | Include receipt number in the requests to the etc interface | Story | 3 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27483 | StringTokenizer does not return empty tokens, leading to multiple line breaks being unrecognized | Bug | 3 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27613 | Remove capturing and printing of pensioner ids | Story | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27698 | Adjust US receipt layout regarding weight and tare label | Story | 1 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26738 | Analyse back office communication and prevent calls in offline state | Story | 3 | In Development | 8 | Sales |  |  |  | Not Completed |  | 1 | 8 | 0 | 7 | 0 | 1
ANP-17348 | Validate master data retrieved from back office server via ACO before import | Story | 3 | In Development | 8 | Sales |  |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-27716 | Pick of the compacting mechanism to ER 4.1/NEWPOSS 4.7 | Story | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27580 | Analysis capturing of lottery items and related receipt position creation [half a day] | Task | 3 | In Progress | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27563 | Pick missing test adjustments for fiscal till id number to 4.7 application tests | Task | 3 | Closed | 0 | Sales |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-27693 | Build MCO part of NEWPOSS release 4.7.12 | Story | 3 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27713 | Brainstorming on fraud protection mechanism on MCO | Task | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27715 | PI Planning and effort estimation | Task | 3 | Ready | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27638 | RIE [Stores] Multiple Articles affected - Wrong price for the single bottle. (Pfandartikel) | Bug | 4 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27133 | Warranty text is not printed on receipt | Bug | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27170 | Items with UPC-A Barcode starting with "26" are added to receipt with quantity of zero | Bug | 3 | In Development | 3 | Sales |  |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
ANP-25038 | Maven install command fails | Bug | 3 | In Development | 5 | Sales |  |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-27150 | [Infinity] SAP FICO - problems with the sales foreign currency postings - no em | Bug | 4 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-28000 | Re-enable owasp plugin for all MCO repositories | Story | 3 | Closed | 1 | Sales | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28165 | Build MCO part of NEWPOSS release 4.7.13 | Story | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-28205 | Build MCO part of NEWPOSS release 4.10.1 | Story | 3 | Closed | 2 | Sales | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-28175 | Till restart message appearing on MCO #1 | Bug | 2 | Blocked | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28174 | ESL - incorrect receipt info on product - N/A | Bug | 4 | Blocked | 3 | Sales | yes |  |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-28385 | Adjust receipt layout differences (CFRM vs till-dev) based on analysis results | Story | 3 | In Development | 5 | Sales | yes |  |  | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
ANP-26888 | Remove non-layout business logic from AldiItemReceiptPosition BO | Story | 3 | In Development | 3 | Sales | yes |  |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-28226 | AU Store - Articles/Items printed double on receipts | Bug | 4 | In Development | 3 | Sales | yes |  |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-25386 | HU DRS: Implement Voucher Processing Flow for Partial Cash-Out | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25643 | HU Md: NEWPOSS tests | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25832 | HU Md: Update services in the workflow: suspendandretrieve (Updating the interfaces) | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25915 | HU DRS: Change/update existing Integrity tests | Story | 3 | Closed | 5 | Synergy |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26502 | HU DRS: Fix printer error after suspend (CreateDepositReturnPayoutReceiptActivity) | Bug | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26746 | We detected a problem with bottle deposit in AHEAD | Bug | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26792 | HU Md: Manual testing for egc.autorefund | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26793 | HU Md: Manual testing for cancelreceipt | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26799 | HU Md: Manual testing for recieptfiscalnumber | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26800 | HU Md: Manual testing for refund | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26801 | HU Md: Manual testing for suspendandretrieve | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26802 | HU Md: Manual testing for tendering | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26803 | HU Md: Manual testing for voiding | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26829 | HU Md: Manual testing for errorhandling | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27555 | HU Md: NEWPOSS tests | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27755 | Code 89 is displayed in the list and triggers specific data on the till screen | Bug | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27756 | Error message appears after each successful code list printing | Bug | 2 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27757 | Full receipt printing with code 15 for selected period | Bug | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27759 | Error on Login after logging out from till | Bug | 1 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27762 | Print Receipt Header and Footer | Bug | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27763 | Refund with receipt reference is not working | Bug | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27766 | Receipt Cancellation through void leads to exception | Bug | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27768 | Closing a receipt with negative amount leads to till freeze | Bug | 1 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27777 | Receipt printing starts without paper warning and triggers non-resettable error | Bug | 2 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27784 | [SPIKE] Integration requirements analysis | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27786 | No fiscal memory data printed for the date when no transactions occurred on the selected day | Bug | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27936 * | Error when using 33 code | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27988 * | Error when paying by receipt in cash above the amount of the receipt | Bug | 1 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27989 * | The change is not displayed correctly on the receipt | Bug | 1 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27990 * | The first opening day fiscal receipt does not show the amount of cash deposited | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27991 * | Euros deposited at the till are shown as Hungarian currency on the receipt | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27992 * | Printer error VÁRATLAN HIBA is displayed on the screen every time after logging in | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28063 * | Exception occurs when canceling receipt and receipt not printed | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28108 * | Interruption of the receipt when opening a fiscal day and depositing euros | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28133 * | Original receipt is deleted instead of being closed when switching to invoice mode | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28138 * | SUBTOTAL ("RÉSZÖSSZESEN") line is missing on a receipt | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28139 * | Error and freezing of till when a receipt is suspended | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28140 * | Impossible to retrieve an invoice receipt after suspend | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28141 * | Error when scanning a weight item | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28163 * | Error and till freezing of till when a receipt with negative amount | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28171 * | Replace EGC in limitation period not working anymore | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28173 * | Error and freezing of till when using refund | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28176 * | Barcode is not printed on the receipt | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28177 * | Receipt for PIN Printing items is not printed | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28178 * | Barcode with receipt suspension cannot be scanned | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28180 * | Receipt Prints Immediately on Void Before Confirmation | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28181 * | There are 2 receipts are printed if it is an invoice receipt | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28184 * | Error and till freeze when voiding an item | Bug | 2 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28188 * | Unable to void an invoice receipt | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28191 * | Error and freezing of till if the printer is unplugged | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28198 * | Cash drawer not recognized by till | Bug | 2 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28204 * | Unable to сomplete Wastage Log process | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28219 * | The till does not start up | Bug | 1 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28220 * | Make possible adding regular items when the first item in a receipt was a Bottle Refund | Story | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28239 * | CFRM configuration before launching the till in the test lab | Story | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28240 * | Receipt fiscalization does not work | Bug | 1 | Closed | 5 | Synergy | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28259 * | Failed to perform backup on the till | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28261 * | Impossible to open a fiscal day | Bug | 1 | Closed | 5 | Synergy | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28262 * | Receipt Cannot Be Voided Completely | Bug | 2 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28281 * | Error not being handled during fiscalization | Bug | 2 | Closed | 5 | Synergy | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28287 * | Cash In Receipt during login contains wrong amount if fiscal day was closed during login | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28303 * | No receipt is printed when canceling a sale | Bug | 2 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28318 * | Gift card status receipt cannot be printed | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28328 * | PLU report cannot be printed | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28344 * | Non-bottle deposit return items can be added to bottle refund receipt | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28345 * | Wrong error msg is shown when trying to print cash register report with open printer cover | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28346 * | Printer error Nincs nyomtató is displayed on the screen every time after logging in | Bug | 2 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28358 * | Complete void of receipt containing multi-purpose EGC leads to exception | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28365 * | A term nem uzemkesz error when suspend receipt with bottle deposit | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-28390 * | Cancellation receipt printed with barcode and number to retrieve | Bug | 2 | Closed | 3 | Synergy | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-28412 * | Error message is cleared on the second attempt only if the paper runs out during a sale | Bug | 3 | Closed | 1 | Synergy | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-24512 | ITA the refund reference number is not the expected with old format barcode refund. | Bug | 3 | In Development | 3 | Synergy |  |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
ANP-25641 | HU Md: Bug fixing | Story | 3 | In Development | 8 | Synergy |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25914 | HU DRS: Smoke testing | Story | 3 | In Development | 5 | Synergy |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26735 | [2] Main Driver: Conduction of RCA for "Waage inaktiv/Scale inactive" | Story | 1 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27557 | HU Md: NEWPOSS tests | Story | 3 | In Development | 5 | Synergy |  |  |  | Not Completed |  | 5 | 5 | 0 | 0 | 0 | 5
ANP-28166 * | HU: Middleware + DRS merge into one branch | Story | 3 | Closed | 5 | Synergy | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28361 * | Errors when voiding a receipt with SINGLEUSE_DEPOSIT_RETURN items | Bug | 2 | In Development | 3 | Synergy | yes |  |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-28364 * | Receipt isn't printed when cancel invoice receipt with negative amount | Bug | 3 | In Development | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-28387 * | Unnecessary data on gift card receipts | Bug | 3 | In Development | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-28388 * | Add proper error handling for fiscal day state management operations | Bug | 3 | In Test | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-28389 * | Invoice receipt is interrupted if the value of bottle deposits exceeds the total amount of articles | Bug | 3 | In Development | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-28403 * | Printer screen retains last payment information persistently | Bug | 3 | Blocked | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-28404 * | Adding bottles to an invoice receipt converts it into a sale receipеt | Bug | 3 | In Development | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-28411 * | Suspend receipt is interrupted if the paper runs out | Bug | 2 | In Development | 3 | Synergy | yes |  |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-28435 * | Receipt error during a refund if only bottle deposits remain in the transaction | Bug | 3 | In Test | 1 | Synergy | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-26775 | HU Md: Manual testing for postlogin | Story | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26795 | HU Md: Manual testing for login | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26796 | HU Md: Manual testing for logout | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26797 | HU Md: Manual testing for postlogout | Story | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-23589 | BF-226 Text | Story | 3 | Closed | 5 | Vlinder |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-27710 | BF-1540 Waiting..-Bug with cashier login | Story | 2 | Closed | 3 | Vlinder |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27711 | BF-1595 Waiting..-Bug with suspend | Story | 2 | Closed | 3 | Vlinder |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27712 | BF-1594 Aggr. EGC in sale and void | Story | 3 | Closed | 5 | Vlinder |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-27980 | BF-1605 Bug - 2nd refund | Story | 3 | Closed | 3 | Vlinder |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27981 | BF-1620 Bug - Transmission of dimension | Story | 3 | Closed | 3 | Vlinder |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-28111 * | BF-1400 Restore state after tendering | Story | 3 | Closed | 5 | Vlinder | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-28326 * | BF-1643 Waiting..-Bug with partial payment | Story | 3 | Closed | 3 | Vlinder | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24908 * | BF-776 copy with item voids | Story | 3 | In Development | 5 | Vlinder | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-26551 | BF-836 Agg. for PDF | Story | 3 | In Development | 5 | Vlinder |  |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-27534 | AHEAD Parameter Guard in Java Code | Story | 3 | In Development | 3 | Vlinder |  |  |  | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
ANP-27622 | BF-1473 remove via code function | Story | 3 | In Development | 8 | Vlinder |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-27624 | BF-239 disable receipt printing | Story | 3 | In Development | 8 | Vlinder |  |  |  | Not Completed |  | 3 | 8 | 0 | 5 | 0 | 3
ANP-27706 | BF-1592 Waiting..-Bug with cash-payment | Story | 1 | In Development | 3 | Vlinder |  |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-27982 | BF-1256 PDF rendering | Story | 3 | In Development | 3 | Vlinder |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-28157 * | BF-1614 line duplication in PDF | Story | 3 | In Development | 8 | Vlinder | yes |  |  | Not Completed |  | 3 | 0 | 8 | 5 | 0 | 3
ANP-28270 * | BF-1645 - Support Tests PI_2-5&6 | Story | 3 | In Development | 3 | Vlinder | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-507 | [ADAPTER] Add ability to send sale void receipts to Yocuda | Story | 3 | Closed | 5 | Papillon |  |  |  | completed |  |  | 5 | 0 | 5 | 0 | 0
BF-1412 | [ADAPTER] Revise BF adapter tests and test data | Story | 3 | Closed | 8 | Papillon |  |  |  | completed |  |  | 8 | 0 | 8 | 0 | 0
BF-1616 | [SCO] Release tests PI-2-5(&6) | Story | 3 | Closed | 3 | Papillon |  |  |  | completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1625 * | [ADAPTER] Add PDF and processing state to GetSerializedReceiptByNumber response | Story | 3 | Closed | 5 | Papillon | yes |  |  | completed |  |  | 0 | 5 | 5 | 0 | 0
BF-1635 * | [ADAPTER] Calculation of remaining quantities should return correct count in production and mock profile | Story | 3 | Closed | 5 | Papillon | yes |  |  | completed |  |  | 0 | 5 | 5 | 0 | 0
BF-1661 * | [SCO] Test - Removal of Unavailable SCO image on POSGetStatusView | Story | 3 | Closed | 1 | Papillon | yes |  |  | completed |  |  | 0 | 1 | 1 | 0 | 0
BF-1672 * | [SCO] The Yocuda article_id item property is filled with the article number for a financial transaction position and not the article id | Bug | 3 | Closed | 2 | Papillon | yes |  |  | completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-8198 | Reorganise local config | Task | 3 | Closed | 5 | Papillon |  |  |  | completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-8693 | Rework till start | Task | 3 | Closed | 5 | Papillon |  |  |  | completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20671 | SCO exports wrong values in the TaxInformation->taxClass filed for sold EGCs. | Bug | 3 | Closed | 2 | Papillon |  |  |  | completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20701 | [SCO] Update of CH receipts analogous to MCO | Story | 3 | Closed | 3 | Papillon |  |  |  | completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-21040 | Receipt header and footer are not in line with CFRM | Bug | 2 | Closed | 2 | Papillon |  |  |  | completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-21238 | Taxes cannot be calculated for receipts with EGC positions in US | Bug | 3 | Closed | 3 | Papillon |  |  |  | completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1609 * | [ADAPTER][SCO] Check state of messages in Butterfly adapter before deleting the database or message queues | Story | 3 | In Development | 8 | Papillon | yes |  |  | not completed |  | 3 | 0 | 8 | 5 | 0 | 3
BF-1615 | [SCO][ADAPTER] Update Butterfly adapter in combined service PI-2-5(&6) | Story | 3 | Closed | 0.5 | Papillon |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
BF-1617 | [SCO] Deployment and test support PI-2-5(&6) | Story | 3 | Closed | 3 | Papillon |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1658 * | Onboarding Kateryna | Task | 3 | Closed | 2 | Papillon | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-4758 | Refactor AsyncDomainEventSink | Task | 3 | closed | 5 | Papillon |  |  |  | completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-12862 | Create minimal fail-fast config read at system start | Task | 3 | In Progress | 13 | Papillon |  | there were more unknown dependencies than expected, so there is a SP adjustment from 5 to 13 SP. |  | not completed |  | 3 | 13 | 0 | 10 | 0 | 3
NPSCO-13007 | Consolidation of the access to configuration options that are based on environment variables | Task | 3 | In Progress | 13 | Papillon |  | The ticket was reverted due to failing on the tills. Now we´re analyzing again how to fix it. |  | not completed |  | 2 | 13 | 0 | 11 | 0 | 2
NPSCO-19696 | Use Spring Boot gRPC server instead of custom NettyServerBuilder usage (pos-adapter) | Task | 3 | In Review | 5 | Papillon |  |  |  | not completed |  | 2 | 5 | 0 | 3 | 0 | 2
NPSCO-20702 * | [SCO] F&V Bags Selection Screen | Story | 3 | In Test | 5 | Papillon | yes |  |  | not completed |  | 1 | 0 | 5 | 4 | 0 | 1
NPSCO-20703 * | [SCO] Auto Void F&V Bag Items | Story | 3 | In Test | 5 | Papillon | yes |  |  | not completed |  | 1 | 0 | 5 | 4 | 0 | 1
NPSCO-21252 | Rework DomainEventSinkManager | Task | 3 | In Progress | 2 | Papillon |  |  |  | not completed |  | 1 | 2 | 0 | 1 | 0 | 1
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_2_3u4
Sprint 2025_2-3/4, 13.05.2025 - 10.06.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-Over sensitive [SOs] and Carry-Over sensitive [COs])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 30 | 21 | 96 | 10 | 61 | 45 | 0 | 106 |  | 96 | 10 | 61 | 0 | 45 | 63.54%
|  | Payment | 19 | 11 | 21 | 10 | 21 | 9 | 1 | 31 |  | 18 | 12 | 20 | 1 | 9 | 111.1%
|  | Sales | 23 | 20 | 36 | 42 | 60 | 18 | 0 | 78 |  | 36 | 42 | 71 | 0 | 7 | 197.2%
|  | Vlinder | 22 | 19 | 22 | 91 | 94 | 19 | 0 | 113 |  | 22 | 78 | 92 | 0 | 8 | 418.2%
|  | TTT | 18 | 15 | 38 | 20 | 51 | 7 | 0 | 58 |  | 33 | 20 | 49 | 0 | 4 | 148.5%
|  | TNT | 25 | 18 | 33 | 42 | 55 | 0 | 0 | 75 |  | 33 | 42 | 61 | 0 | 14 | 184.8%
|  | TFS | 15 | 14 | 45 | 0 | 40 | 5 | 0 | 45 |  | 45 | 0 | 42 | 0 | 3 | 93.33%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 31 | 24 | 98 | 0 | 79 | 0 | 0 | 98 |  | 98 | 0 | 83 | 0 | 15 | 84.69%
|  | Papillon | 26 | 18 | 58 | 45 | 67 | 36 | 0 | 103 |  | 58 | 45 | 85.5 | 0 | 17.5 | 147.4%
|  | Total | 152 | 118 | 291 | 215 | 382 | 103 | 1 | 506 |  | 283 | 204 | 396 | 1 | 90 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 136 | 451 | 73 | 260 | 209 | 711 | 207 | 707 | 2 | 4 | 209 | 711
|  | Completed | 111 | 360 | 49 | 168 | 160 | 528 | 160 | 528 | 0 | 0 | 160 | 528
|  | Not Completed | 13 | 61 | 19 | 78 | 32 | 139 | 32 | 139 | 0 | 0 | 32 | 139
|  | Removed | 3 | 5 | 0 | 0 | 3 | 5 | 1 | 1 | 2 | 4 | 3 | 5
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Epic | Status | Carry-over | Spill-over | COsSP Initially Planned | COsSP Pulled after Start | CSOsSP Completed | CSOsSP Removed | CSOsSP Not Completed
ANP-25421 | EFT - Foreign cards transactions (Carrefour France, Ukraine) were not successful according to cash register, but charged to customer | bug | 2 | closed | 3 | Payment |  | M | [ANP-26021] OPS & Support Initiative | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-25572 | Display Separate Receipt Total and Cashback Amount in Switzerland at Monolane and Multilane Till | story | 3 | closed | 3 | Payment |  | PD; was created as Bug, but then it turned out to be more than a just a fix and a more thorough specification was made | [ANP-25743] Fix critical CHOP SIT/UAT findings (Payment) | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-25550 | [CHOP] 90+CODE does not print printer and terminal information | bug | 4 | closed | 1 | Payment |  | M; formal spill-over | [ANP-25743] Fix critical CHOP SIT/UAT findings (Payment) | Completed | 0 |  | 0 | 0 | 0 | 0 | 0
ANP-26616 | Analysis of ANP-25064: Store- credit card payments against signature, the merchant receipt will no longer be printed- EM: no | story | 3 | closed | 1 | Payment |  | M |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-25453 | [CHOP] The 1st in-sale Subtotal line on receipt is incorrect ( = the final subtotal amount of the receipt, which has additional items ringed after pressing the subtotal button) | bug | 3 | closed | 3 | Payment |  | M |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25440 | Logfiles: Multi-Lane Till Development | story | 3 | in development | 2 | Payment |  | M | [ANP-22244] Collect Logfiles in /var/log | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
ANP-27102 | CHOP: Clean up Multilane dependencies and move OSGI Runtime dependencies to maven | story | 3 | closed | 3 | Payment |  | M | [ANP-25418] Hypercare for CHOP AT/CH Pilots (Payment) - Q2 | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27106 | Missing ressources/translations for CHOP CH Italian/French language for cashback | bug | 3 | closed | 2 | Payment |  | M; re-estimated from 2SP to 3SP retrospectively |  | Completed | 3 |  | 2 | 1 | 3 | 0 | 0
ANP-27464 | Pick Ticket for 4.7.11 Release | story | 3 | closed | 1 | Payment | yes | RT |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27463 | Set up terminal for TIM middleware | task | 3 | closed | 2 | Payment | yes | RT; estimated retrospectively |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-27245 | additional Analysis of ANP-25541: [CHOP] Global Blue (12+Code) not working for card payments and last receipt | story | 2 | ready | 1 | Payment | yes | M; re-estimated from 1SP to 2SP retrospectively |  | Not Completed | 2 | 2 | 0 | 2 | 0 | 0 | 2
ANP-27241 | Analysis of ANP-27238: EFT data is missing with autocommit = false in the tim config | story | 2 | closed | 1 | Payment | yes | M |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27565 | Pick Till Application Test 19941 and 19414 to Version 4.7 | story | 3 | closed | 1 | Payment |  | RT |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27238 | EFT data is missing with autocommit = false in the tim config | bug | 2 | ready | 3 | Payment | yes | M |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-27669 | [UK] Integrate POS Core for OPI boolean fix | bug | 2 | in development | 2 | Payment | yes | M |  | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
ANP-27564 | Analysis of ANP-24330: POS3 - CHOP - NCR 7199 PinPrinting not correct | story | 3 | ready | 1 | Payment |  | M |  | Not Completed |  | 1 | 1 | 0 | 0 | 0 | 1
ANP-27521 | analyse debug-info shortcut script for inclusion of multilane logs from var/log/newposs | task | 3 | ready | - | Payment |  | PD |  | Removed |  |  | 0 | 0 | 0 | 0 | 0
ANP-26706 | check if refactoring for getHighestPiorityState is needed | task | 3 | ready | - | Payment |  | M |  | Removed |  |  | 0 | 0 | 0 | 0 | 0
ANP-26704 | [SPIKE] Multilane Mock improvement for application tests | story | 3 | in development | 1 | Payment |  | RT; spill-over estimated by RE |  | Removed |  |  | 1 | 0 | 0 | 1 | 0
NPSCO-20463 | SCO includes the complete value of a lottery item in the totalSalesSum | Bug | 1 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20401 | Cherry-pick release 4.13.1 [TTT] | Task | 3 | Closed | 5 | TTT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20852 | Build Hotfix 3.18.7 | Task | 3 | Closed | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20453 | Build Maintenance Release 4.13.1 | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20458 | Test Maintenance Release 4.13.1 | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20002 | Sprint build 422 | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20091 | All SCOs - Asking customers if they want to print receipt | Bug | 4 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19618 | Errorhandling for PinPrinting | Story | 3 | Closed | 8 | TTT |  |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-19346 | [Test] Margin calculation | Story | 3 | Closed | 2 | TTT |  |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-19619 | Pin Printing receipt | Story | 3 | Closed | 5 | TTT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20041 | Sprint test 421 | Task | 3 | Closed | 3 | TTT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20370 | [TEST] cancel-/ suspend transaction and discounts with PinPrinting articles | Task | 3 | Closed | 2 | TTT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-20188 | The merchantLocation in the Request for an EGC of BLACKHAWK is exceeding the maximum Length of '40' characters | Bug | 3 | Closed | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19995 | SCO - Incorrect Syntax for Attempt to Discount Item Over Limit | Bug | 3 | Closed | 3 | TTT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20605 | Broken messages when violating the discount limit on price override | Bug | 3 | Closed | 2 | TTT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-19621 | Customer button for PinPrinting-DIC menu | Story | 3 | In Development | 3 | TTT | yes |  |  | Not Completed |  | 2 | 0 | 3 | 1 | 0 | 2
NPSCO-19620 | Export of PinPrinting items | Story | 3 | In Development | 3 | TTT | yes |  |  | Not Completed |  | 1 | 0 | 3 | 2 | 0 | 1
NPSCO-20856 | Release build 4.22.0 | Task | 3 | In Progress | 1 | TTT | yes |  |  | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
NPSCO-20364 | Leftover rocky linux migration job is still executed on Rocky and can interrupt other updater processes | Bug | 1 | CLOSED | 1 | TFS |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20374 | Maintenance Release 4.13.1Cherry Pick | Task | 3 | CLOSED | 5 | TFS |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20326 | SCO CH, EFT payment with TIM integration - EFT payment failed due to error "TRX_LIMIT_EXCEEDED" on EFT terminal | Bug | 2 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19093 | Unclear Customer Intervention for empty ePay Gift Cards | Bug | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19962 | Support epay event vouchers (Legacy mode) | Story | 3 | IN DEVELOPMENT | 8 | TFS |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
NPSCO-19833 | Re-enable EGC Payment button | Task | 3 | CLOSED | 1 | TFS |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20316 | Only one event voucher per transaction (ahead) | Story | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19141 | [UK] payment order incorrect on the virtual receipt | Bug | 3 | CLOSED | 5 | TFS |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20815 | Test Task Hotfix 3.18.7 | Task | 3 | CLOSED | 1 | TFS |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20466 | Test Task Maintenance Release 4.13.1 | Task | 3 | IN PROGRESS | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20809 | Test Task Sprint 422 | Task | 3 | CLOSED | 3 | TFS |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20794 | Test event voucher (aHead) | Task | 3 | IN PROGRESS | 2 | TFS |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20690 | Deactivate Force close in UK | Story | 3 | IN DEVELOPMENT | 5 | TFS |  |  |  | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
NPSCO-20763 | Only one event voucher per transaction (legacy) | Story | 3 | CLOSED | 0 | TFS |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-20634 | Deactivated customer intervention in payment for event voucher | Story | 3 | CLOSED | 2 | TFS |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27490 | Print till identification number on fiscal receipts in AT | Story | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27678 | Temporary AU Software Version in BUNDLE_VERSIONS for NEWPOSS 4.7.x | Story | 1 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27468 | Determine differences between receipt layout configuration in production and provided configuration scripts | Task | 1 | In Progress | 8 | Sales | yes |  |  | Not Completed |  | 2 | 0 | 8 | 6 | 0 | 2
ANP-27559 | Prepare "Sprint-Review Checkout Base, Checkout Client" meeting | Task | 3 | Closed | 0 | Sales |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-27138 | POS 3 freezing | Bug | 1 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27230 | Unable to activate Internal EGC on IRL Test Store (982-116). | Bug | 2 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27221 | Integrate till with HU Middleware (simulator) in till-application-tests | Story | 3 | Closed | 13 | Sales |  |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-27466 | Provide AHEAD parameter guards missing in recent releases | Story | 3 | Closed | 8 | Sales | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-27424 | Implementation of new till sharing functionality 21+CODE for GB/IE | Story | 3 | In Development | 8 | Sales | yes |  |  | Not Completed |  | 3 | 0 | 8 | 5 | 0 | 3
ANP-27471 | Enable usage of 33+CODE (Cash Lift) during the cash lift till blocking prompt | Story | 3 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27472 | Swap functionality of 94+CODE (Till Lock Fallback) and 33+CODE (Cash Lift) for US | Story | 3 | Closed | 3 | Sales | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26752 | Create circuit breaker for NEWPOSS Store Server REST calls from MCO | Story | 3 | Closed | 5 | Sales |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26423 | MCO's no longer logging when out of sync | Bug | 3 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26978 | Merge HU Pensioners Card stories to the 4.7 maintenance branch | Story | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26961 | Move HU pensioner ID test to new use case | Task | 3 | Closed | 1 | Sales |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26889 | Add checkMK monitoring value for database size | Story | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27172 | Enable cash lift code functionality (33+CODE) for US | Story | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27175 | Cash drawer remains closed following a drawer takeover after till sharing logout (20+CODE) | Story | 3 | Closed | 3 | Sales |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27196 | Build MCO part of NEWPOSS release 4.7.11 | Story | 3 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27064 | 31 code to print PLU list is not working | Bug | 4 | Closed | 2 | Sales |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27413 | Setup HU2 test system for demo | Task | 3 | Closed | 0 | Sales | yes |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-27483 | StringTokenizer does not return empty tokens, leading to multiple line breaks being unrecognized | Bug | 3 | In Development | 2 | Sales | yes |  |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
ANP-27883 | Disable Owasp plugin temporarily until the plugin is fixed | Story | 3 | Closed | 1 | Sales | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27244 | [DN P1200] Cannot operate DN P1200 due to missing directories and correlating permissions | Bug | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27545 | [MCO] Auto-Start of Compound Service: Long-Term Solution | Story | 3 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27593 | Configure Azure Proxy for butterfly-adapter in MCO | Bug | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27612 | mco-storedata.txt file is missing mandatory header content for CheckMK | Bug | 1 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4824 | Install HU middleware in a basic way | Story | 3 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6000 | Provide device information for the DN P1200 printer to CMDB | Story | 3 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6318 | Enable distinguishing of Gryphon scanners | Story | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6422 | [IT] No Fiscal Data transmitted to Fiscal Server | Bug | 1 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6514 | NCR line display is displayed as “CR 5976” in devices.xml | Bug | 3 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6520 | New DN Touch Screens ( D2156 D1156) not working | Bug | 1 | Closed | 3 | Engineering |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6522 | Error message when checking the scale firmware - big problem when calibartion officer ("Eichamtsperson") wants to check the scales | Bug | 1 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6550 | SCO prompting for entry of passphrase for disk | Bug | 2 | Closed | 5 | Engineering |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6586 | [NCR 7199] Scripts required for execution of 222 code are not rolled out for 1.25Ev2/3.2B9 for several Stores | Bug | 3 | Closed | 8 | Engineering |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-6674 | Testlab maintenance | Task | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6675 | Update from CHO-Platform 6.13 to 6.16 does not provide credentials for monitored item adapter | Bug | 2 | Closed | 1 | Engineering |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-6676 | Verify Bizerba c2 artifact for software update and compatibility with Rocky 9.5 | Task | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6698 | Integrate fixed Bizerba C2 driver | Bug | 1 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6720 | [IT] Bump Fiscal adapter version to 2.0.9-0 | Story | 3 | Closed | 1 | Engineering |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-6771 | [UK] EFT payments with signature fail with OPI direct integration | Bug | 2 | Closed | 2 | Engineering | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-20043 | devices.xml must be readable by user or group discovery_stores | Story | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20853 | Configure Azure Proxy for butterfly-adapter for SCO | Bug | 3 | Closed | 2 | Engineering |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26106 | NCR CX8 x CS300 not working in 4.1 release | Bug | 2 | Blocked | 8 | Engineering |  |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-27533 | [QA][Tr-Stores-IIT-Legacy testroom] TILL does not always update to NP 4.9.0.1 from lower versions during Ivanti update path tests for Releases 4.1TB2 | Bug | 2 | Blocked | 3 | Engineering |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5041 | Provide SCO DN-managed devices information to HWLM | Story | 3 | In Review | 5 | Engineering |  |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6651 | HWLM: differentiate between Quest 720 and 850 terminals | Story | 3 | In Development | 3 | Engineering |  |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6706 | AUS: Scanner/Scales not responding. | Bug | 1 | Blocked | 5 | Engineering |  |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6707 | ATS - Stuck in boot loop post 3.2 update | Bug | 2 | In Development | 8 | Engineering |  |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
CHO-6733 | 4.1C4 - DN Beetle requires manual input after BIOS update | Bug | 1 | In Development | 3 | Engineering | yes |  |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-6750 | Ensure consistent till updates | Bug | 2 | In Development | 5 | Engineering |  |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6762 | Add option to reinstall as different till number for support cases | Story | 1 | In Review | 5 | Engineering | yes |  |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
ANP-25637 | HU Md: Update current worklow: suspendandretrieve | Story | 3 | Closed | 5 | Synergy |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25832 | HU Md: Update services in the workflow: suspendandretrieve (Updating the interfaces) | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26502 | HU DRS: Fix printer error after suspend (CreateDepositReturnPayoutReceiptActivity) | Bug | 3 | In Development | 3 | Synergy | [6 empty] | 3 | 0 | 0 | 0 | 3
ANP-26295 | HU DRS: CSR handling (TESTING only) | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25776 | HU DRS: Implement local saving of redeemed vouchers/check if the voucher was redeemed on use (TESTING only) | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26771 | HU Md: Manual testing for personalize | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26715 | HU DRS: Implement separate error messages for LOCAL voucher validation | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26450 | HU DRS: Check Item Restrictions during Ringing | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26891 | HU DRS: Retrieve Process for RVM Vouchers (after suspend) | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25831 | HU Md: Update services in the workflow: refund | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26893 | HU Md: Update services in the workflow: suspendandretrieve (Connecting new adapter to the service) | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25834 | HU Md: Update services in the workflow: voiding | Story | 3 | Closed | 5 | Synergy |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25627 | HU Md: Update current worklow: errorhandling | Story | 3 | Closed | 5 | Synergy |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25824 | HU Md: Update services in the workflow: errorhandling (Updating the interfaces) | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26892 | HU Md: Update services in the workflow: errorhandling (Connecting new adapter to the service) | Story | 3 | Closed | 5 | Synergy |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25987 | AHEAD Stores - MCO to MCO Suspend/Retrieve Transactions are not Applying Chicago Water Bottle Tax Correctly. | Bug | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26746 | We detected a problem with bottle deposit in AHEAD | Bug | 3 | IN DEVELOPMENT | 2 | Synergy | [5 empty] | 1 | 2 | 0 | 1 | 0 | 1
ANP-25386 | HU DRS: Implement Voucher Processing Flow for Partial Cash-Out | Story | 3 | IN DEVELOPMENT | 2 | Synergy | [5 empty] | 1 | 2 | 0 | 1 | 0 | 1
ANP-25915 | HU DRS: Change/update existing Integrity tests | Story | 3 | OPEN | 5 | Synergy | [6 empty] | 5 | 0 | 0 | 0 | 5
ANP-27538 | MCO - Implement Firewall Configuration for NEWPOSS | Story | 3 | Closed | 8 | Synergy |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-27187 | HU Md: Update non-fiscal receipt (code) | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27184 | HU Md: Mapping | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27555 | HU Md: NEWPOSS tests | Story | 3 | OPEN | 2 | Synergy | [6 empty] | 2 | 0 | 0 | 0 | 2
ANP-27554 | HU Md: NEWPOSS tests | Story | 3 | Closed | 8 | Synergy |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-27556 | HU Md: NEWPOSS tests | Story | 3 | IN DEVELOPMENT | 2 | Synergy | [5 empty] | 1 | 2 | 0 | 1 | 0 | 1
ANP-27557 | HU Md: NEWPOSS tests | Story | 3 | IN DEVELOPMENT | 3 | Synergy | [5 empty] | 2 | 3 | 0 | 1 | 0 | 2
ANP-25461 | HU DRS: Training mode implementation (TESTING only) | Story | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26798 | HU Md: Manual testing for prestart, login, postlogin, logout, postlogout | Story | 3 | Closed | 3 | Synergy |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26774 | HU Md: Manual testing for codes | Story | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26794 | HU Md: Manual testing for fiscalmenu | Story | 3 | Closed | 2 | Synergy |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26105 | HU DRS: Make expiration date for voucher configurable / refactoring (TESTING only) | Story | 3 | Closed | 1 | Synergy |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20626 | SCO No POS Connection after Update (postrgres migration fails) | Bug | 1 | In Development | 2 | TNT | yes |  |  |  |  | 1 | 0 | 2 | 1 | 0 | 1
NPSCO-19395 | Update RP Services | Story | 3 | Closed | 5 | TNT |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19728 | post_update.jobs not performed during package update | Bug | 2 | Closed | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19917 | SCO ¦ [KW14] 0% VAT rate mapping issues | Bug | 2 | BLOCKED | 3 | TNT | [6 empty] | 3 | 0 | 0 | 0 | 3
NPSCO-20365 | Amounts of salesPerTaxRate, the amount is not the same as totalSales | Bug | 2 | Closed | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20569 | Cherry-pick release 4.13.1 [TNT] | Task | 3 | Closed | 5 | TNT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-15234 | Use postgres 16 with Alpine | Task | 3 | Closed | 2 | TNT |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17559 | Add spans and traces to all services | Story | 3 | Closed | 1 | TNT |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20127 | SCO - Infrastructure Adapter Java Upgrade 17 | Story | 3 | Closed | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19998 | POS-Core-Update to 3.99 | Story | 3 | Closed | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18835 | Replace own tiles of infrastructure-adapter by warp-tiles | Task | 3 | Closed | 2 | TNT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-17408 | [Tech Debt Task] Implement a purchase command for adding extension properties only - follow up | Task | 3 | IN PROGRESS | 3 | TNT | [5 empty] | 2 | 3 | 0 | 1 | 0 | 2
NPSCO-20318 | Setup Jira/Confluence Access | Task | 3 | Closed | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20459 | Build MSIs for Sprint 421 | Task | 3 | Closed | 1 | TNT |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-20465 | Test SCO Sprint 421 | Task | 3 | Closed | 3 | TNT |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19202 | Implement Firewalld Configuration for SCO | Story | 3 | IN DEVELOPMENT | 5 | TNT | yes |  |  |  |  | 3 | 0 | 5 | 2 | 0 | 3
NPSCO-15567 | Open Port 5665 for CheckMK | Story | 2 | IN DEVELOPMENT | 3 | TNT | yes |  |  |  |  | 1 | 0 | 3 | 2 | 0 | 1
NPSCO-20672 | SCO totalSalesSum calculation | Story | 2 | Closed | 5 | TNT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-20814 | Test SCO Sprint 422 | Task | 3 | Closed | 2 | TNT | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-20363 | Adapt configure.xml to provide monitored item MQTT user and secret | Story | 3 | IN DEVELOPMENT | 3 | TNT | yes |  |  |  |  | 2 | 0 | 3 | 1 | 0 | 2
NPSCO-20806 | Extension of the heartbeat message to include "unsentmessages" and "unsenterromessages" | Story | 3 | Closed | 5 | TNT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-21016 | Test Hotfix Release 3.18.7 | Task | 3 | Closed | 3 | TNT | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21023 | Test Maintenance Release 4.13.1 | Task | 3 | Closed | 5 | TNT | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-21058 | Analyse SCO freeze live incident INC5286646 | Task | 3 | Closed | 1 | TNT | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-20799 | Incorrect creation of log file path [RP Services Log Files] | Bug | 2 | OPEN | 1 | TNT | yes |  |  |  |  | 2 | 0 | 1 | -1 | 0 | 2
BF-1530 | [ADAPTER] Fix code coverage in adapter to include all tests | Story | 3 | Closed | 2 | Papillon |  |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-1549 * | [ADAPTER] Calculation of remaining quantities should not remove items | Story | 3 | Closed | 2 | Papillon | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1561 * | [SCO] Update Product Branding Name - FUT | Story | 1 | Closed | 2 | Papillon | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18029 | Extract and cleanup component tests from pos-app-adapter | Task | 2 | Closed | 8 | Papillon |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
NPSCO-18531 | Remove conditional Bean creation in pricing service | Task | 3 | Closed | 5 | Papillon |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18556 | Copying of the .Xauthority-diebold file is no longer necessary for the infrastructure adapter | Task | 3 | Closed | 3 | Papillon |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18806 | pos-app-adapter maven clean phase does not work alone | Task | 3 | Closed | 5 | Papillon |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19363 | Merge the three article lookup methods into one | Task | 3 | Closed | 13 | Papillon |  | adjusted estimation from 8 SP to 13 |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
NPSCO-20600 * | Fix TaxRequest in assco-rp-pricing sent to middleware causing null TaxResponse | Bug | 3 | Closed | 1 | Papillon | yes |  |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-20711 * | When Exit Gate is printed the EFT customer lines are also printed. | Bug | 3 | Closed | 2 | Papillon | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-20775 * | [Spike] Evaluate how we can parallelize the component tests | Task | 3 | Closed | 8 | Papillon | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
NPSCO-21002 * | When customer selects start for transaction to begin SCO will display "starting transaction" for 6-8 seconds which is considerably longer than normal behaviour | Bug | 2 | Closed | 2 | Papillon | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-21102 * | [SCO] Enable QR-Code scan of eGift Card during tendering in US | Story | 3 | Closed | 3 | Papillon | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-21104 * | [SCO] Test applicability of Bar-code for eGift Cards | Story | 3 | Closed | 2 | Papillon | yes |  |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1532 | [SCO][ADAPTER] Update Butterfly adapter in combined service PI-2-3 | Story | 3 | Closed | 0.5 | Papillon |  |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
BF-1533 | [SCO] Release tests PI-2-3 | Story | 3 | Closed | 3 | Papillon |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1534 | [SCO] Deployment and test support PI-2-3 | Story | 3 | Closed | 3 | Papillon |  |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1550 * | Onboarding Jonas | Story | 3 | Closed | 3 | Papillon | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-507 | [ADAPTER] Add ability to send sale void receipts to Yocuda | Story | 3 | In Acceptance | 5 | Papillon |  | The work on this story has only been scarcely distributed over the current sprint as the changes relate to test data only and the sprint being (again) packed with more important tasks. The remaining estimate is 0,5 SP. |  | Not Completed |  | 0.5 | 5 | 0 | 4.5 | 0 | 0.5
BF-1412 | [ADAPTER] Revise BF adapter tests and test data | Story | 3 | In Development | 8 | Papillon |  | Is done, but as this ticket has been split from BF-507: [ADAPTER] Add ability to send sale void receipts to Yocuda In Acceptance and thus also developed together with BF-507: [ADAPTER] Add ability to send sale void receipts to Yocuda In Acceptance both tickets have to be done to merge the related changes |  | Not Completed |  | 0 | 8 | 0 | 8 | 0 | 0
NPSCO-8198 | Reorganise local config | Task | 3 | In Progress | 3 | Papillon |  |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
NPSCO-12862 * | Create minimal fail-fast config read at system start | Task | 3 | In Progress | 5 | Papillon | yes |  |  | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
NPSCO-13007 * | Consolidation of the access to configuration options that are based on environment variables | Task | 3 | In Progress | 8 | Papillon | yes |  |  | Not Completed |  | 5 | 0 | 8 | 3 | 0 | 5
NPSCO-20671 * | SCO exports wrong values in the TaxInformation->taxClass filed for sold EGCs. | Bug | 3 | Open | 2 | Papillon | yes |  |  | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
NPSCO-20701 * | [SCO] Update of CH receipts analogous to MCO | Story | 3 | Blocked | 3 | Papillon | yes |  |  | Not Completed |  | 1 | 0 | 3 | 2 | 0 | 1
NPSCO-20798 * | [SCO] Adaption of single bottle and multipack button icons | Story | 3 | Blocked | 2 | Papillon | yes |  |  | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
ANP-26548 * | BF-1088 Test aggregation | Story | 3 | In Acceptance | 8 | Vlinder | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-26552 | BF-1315 Export voids | Story | 3 | Closed | 8 | Vlinder |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26553 | BF-1237 PoD with CEP | Story | 3 | Closed | 8 | Vlinder |  |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26728 * | BF-1321 integrity tests for BF-73 | Story | 3 | Closed | 5 | Vlinder | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-26743 * | BF-1416 Bug PDF in Yocuda | Story | 2 | Closed | 3 | Vlinder | yes |  |  | Completed | 1 |  | 0 | 1 | 1 | 0 | 0
ANP-26904 * | BF-843 Promotions on Display | Story | 3 | Closed | 8 | Vlinder | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-26905 * | BF-175 Change refund workflow | Story | 3 | Closed | 5 | Vlinder | yes |  |  | Completed | 2 |  | 0 | 2 | 2 | 0 | 0
ANP-27067 * | BF-1476 - Bug for mapping | Story | 2 | Closed | 3 | Vlinder | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27173 | BF-1472 Add URID to EGC-Auto-Refunds | Story | 3 | Closed | 5 | Vlinder |  |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-27219 * | BF-1517 - Repo API update | Story | 3 | Closed | 5 | Vlinder | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-27350 * | BF-777 Case No PDF created | Story | 3 | Closed | 5 | Vlinder | yes |  |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-27568 * | [MCO] Update transmission of EGC and PIN printing article in transaction data due to changes caused by BF-623 | Story | 3 | Closed | 5 | Vlinder | yes | SP adjusted from 0 to 5 |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-27579 * | BF-1584 - Test Build PI_2-3 (1st half) | Story | 3 | Closed | 3 | Vlinder | yes | SP adjusted from 0 to 3 |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27707 * | BF-1597 Waiting..-Bug with failed card payment | Story | 2 | Closed | 3 | Vlinder | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-27708 * | BF-1596 Waiting..-Bug with Sale Void | Story | 1 | Closed | 3 | Vlinder | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26547 * | BF-835 Agg. printed receipts | Story | 3 | In Development | 13 | Vlinder | yes |  |  | Not Completed | 5 | 2 | 0 | 5 | 3 | 0 | 2
ANP-27177 | BF-1535 Test support PI-2-3 | Story | 3 | Closed | 1 | Vlinder |  |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27220 * | BF-1354 - Return position properties | Story | 3 | In Development | 5 | Vlinder | yes | SP adjusted from 3 to 5 |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-27534 * | AHEAD Parameter Guard in Java Code | Story | 3 | In Development | 3 | Vlinder | yes |  |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-27620 * | BF-1562 sale and refund receipt | Story | 3 | In Development | 8 | Vlinder | yes |  |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-27706 * | BF-1592 Waiting..-Bug with cash-payment | Story | 1 | In Development | 3 | Vlinder | yes |  |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-27779 * | Fix for failed test cep0311 | Story | 2 | In Development | 3 | Vlinder | yes |  |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0
Ergebnis | [14 empty] | 19

## Sprint_2_2 (hidden)
Sprint 2025_2-2, 29.04.2025 - 13.05.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 13 | 8 | 41 | 2 | 21 | 22 | 0 | 43 |  | 41 | 2 | 21 | 0 | 22 | 51.22%
|  | Payment | 12 | 8 | 13 | 13 | 18 | 8 | 0 | 26 |  | 13 | 13 | 21 | 0 | 5 | 161.5%
|  | Sales | 13 | 10 | 46 | 11 | 39 | 10 | 8 | 57 |  | 46 | 11 | 42 | 8 | 7 | 91.3%
|  | Vlinder | 11 | 6 | 39 | 9 | 21 | 27 | 0 | 48 |  | 25 | 5 | 16 | 0 | 14 | 64%
|  | TTT | 13 | 10 | 36 | 1 | 25 | 12 | 0 | 37 |  | 33 | 1 | 24 | 0 | 10 | 72.73%
|  | TNT | 13 | 9 | 36 | 8 | 30 | 14 | 0 | 44 |  | 34 | 8 | 33 | 0 | 9 | 97.06%
|  | TFS | 8 | 7 | 21 | 2 | 20 | 3 | 0 | 23 |  | 21 | 2 | 22 | 0 | 1 | 104.8%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 21 | 18 | 50 | 9 | 49 | 10 | 0 | 59 |  | 50 | 9 | 52 | 0 | 7 | 104%
|  | Papillon | 22 | 16 | 60 | 16 | 43 | 33 | 0 | 76 |  | 43 | 16 | 40 | 0 | 7 | 93.02%
|  | Total | 83 | 58 | 232 | 46 | 174 | 96 | 8 | 278 |  | 213 | 42 | 179 | 8 | 68 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 95 | 342 | 31 | 71 | 126 | 413 | 126 | 413 | 0 | 0 | 126 | 413
|  | Completed | 71 | 222 | 21 | 44 | 92 | 266 | 92 | 266 | 0 | 0 | 92 | 266
|  | Not Completed | 23 | 112 | 10 | 27 | 33 | 139 | 33 | 139 | 0 | 0 | 33 | 139
|  | Removed | 1 | 8 | 0 | 0 | 1 | 8 | 1 | 8 | 0 | 0 | 1 | 8
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-26181 | List integrated scale as separate device in devices.xml | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6319 | Document device names for HWLM | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6448 | CMDB: 6.5" display not recorded | Bug | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6449 | CMDB: GM4500 scanner not present in cmdb.py output | Bug | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26106 | 102-125 Scale Port error - 4.7.2.1 - Datalogic Bizerba Serial_virtual_usb | Bug | 2 | In Development | 8 | Engineering |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-27085 | MCO part of CHO-6158 | Story | 3 | In Acceptance | 1 | Engineering | yes |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
CHO-6158 | Provide HWLM information for Preh keyboards | Story | 3 | In Acceptance | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6520 | New DN Touch Screens ( D2156 D1156) not working | Bug | 1 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6522 | Error message when checking the scale firmware - big problem when calibartion officer ("Eichamtsperson") wants to check the scales | Bug | 3 | Blocked | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6550 | SCO prompting for entry of passphrase for disk | Bug | 2 | In Development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6560 | Release Sprint 2025_PI2-2 Artifacts | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6569 | Testlab maintenance | Task | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6655 | CHO Part of NPSCO-17577: extend mqtt config | Story | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-26869 | Analysis of ANP-26718: [1] Main Driver: Conduction of RCA for "no printer" | Story | 1 | closed | 1 | Payment |  | M | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27068 | Terminals wont initialize after login | Bug | 1 | closed | 8 | Payment | yes | M; assumed estimate | Completed |  |  | 0 | 8 | 8 | 0 | 0
ANP-25421 | EFT - Foreign cards transactions (Carrefour France, Ukraine) were not successful according to cash register, but charged to customer | Bug | 2 | blocked | 3 | Payment |  | M | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
ANP-25572 | Display Separate Receipt Total and Cashback Amount in Switzerland at Monolane and Multilane Till | Story | 3 | in development | 3 | Payment |  | PD; was created as Bug, but then it turned out to be more than a just a fix and a more thorough specification was made | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
ANP-23958 | [IT Ejournal] Error during Ejournal entry creation with EPSON Fiscal Printer | Bug | 3 | closed | 3 | Payment |  | M | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26614 | Analysis of ANP-25550: [CHOP] 90+CODE does not print printer and terminal information | Story | 3 | closed | 1 | Payment |  | M | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26615 | Analysis of ANP-25417: when multilane till is restarted during unfinished sales of 2 customers, only 1 cancelled sale receipt appears in db instead of two | Story | 3 | closed | 1 | Payment | yes | M | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25550 | [CHOP] 90+CODE does not print printer and terminal information | Bug | 4 | in development | 1 | Payment | yes | M; formal spill-over | Not Completed |  | 0 | 0 | 1 | 1 | 0 | 0
ANP-26616 | Analysis of ANP-25064: Store- credit card payments against signature, the merchant receipt will no longer be printed- EM: no | Story | 3 | in development | 1 | Payment | yes | M | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-26974 | test maturity assessment | task | 3 | closed | 2 | Payment |  | RT; estimated retrospectively | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26617 | Analysis of ANP-25453: [CHOP] The 1st in-sale Subtotal line on receipt is incorrect ( = the final subtotal amount of the receipt, which has additional items ringed after pressing the subtotal button) | Bug | 3 | closed | 1 | Payment | yes | M | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27095 | attend meeting regarding ANP-24559 "HU: NEWPOSS Middleware solution for Hungary / Testing Efforts for Payment (2025_PI2)" | task | 3 | closed | 1 | Payment | yes | RT; estimated retrospectively | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-27103 | [QA][Tr-Stores-IIT-Legacy] Blackhawk EGC direct integration error on till - service error | Bug | 1 | In Development | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26747 | ER 4.1 HU - legacy - Unexpected scale error on MCO | Bug | 2 | Closed | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-27109 | Provide missing AHEAD parameter guard in 4.8.0/1.27.8.0 | Story | 3 | In Development | 5 | Sales | yes |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
ANP-26387 | Enable database compacting with scheduled application restarts | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26752 | Create circuit breaker for NEWPOSS Store Server REST calls from MCO | Story | 3 | In Development | 5 | Sales |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-26377 | [QA] No authorization is requested when voiding a receipt over the cashier's void limit. | Bug | 3 | Closed | 3 | Sales |  | Reopened; Analysis will continue with newly provided information | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26665 | Perform documentation export after NEWPOSS 4.8.0 release | Task | 3 | Closed | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26340 | Performance Analysis - Conduct analysis regarding masterdata provison processing | Story | 3 | In Development | 8 | Sales |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-12281 | Remove non-layout business logic from BOs | Story | 3 | In Development | 13 | Sales |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-27089 | Mask the HU pensioner ID to the till log files | Story | 3 | In Development | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-26977 | Implement Parameter workaround for ACOClientMessagingSenderConfiguration on 4.7 maintenance | Story | 3 | Closed | 0 | Sales | yes | 0 SP since effort was taken into account within the relase story | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-27058 | Build MCO part of NEWPOSS release 4.7.9 | Story | 3 | Closed | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-17348 | Validate master data retrieved from back office server via ACO before import | Story | 3 | Ready | 8 | Sales |  |  | Removed |  |  | 8 | 0 | 0 | 8 | 0
ANP-25837 | HU DRS: Implement voucher state management | Story | 3 | closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25829 | HU Md: Update services in the workflow: postlogout | Story | 3 | CLOSED | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25827 | HU Md: Update services in the workflow: logout | Story | 3 | CLOSED | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25830 | HU Md: Update services in the workflow: recieptfiscalnumber | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25636 | HU Md: Update current worklow: refund | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25637 | HU Md: Update current worklow: suspendandretrieve | Story | 3 | IN DEVELOPMENT | 5 | Synergy |  |  | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
ANP-25832 | HU Md: Update services in the workflow: suspendandretrieve (Updating the interfaces) | Story | 3 | IN DEVELOPMENT | 2 | Synergy |  |  | Not Completed |  | 2 | 2 | 0 | 0 | 0 | 2
ANP-25638 | HU Md: Update current worklow: tendering | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25833 | HU Md: Update services in the workflow: tendering | Story | 3 | Closed | 1 | Synergy |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25626 | HU Md: Update current worklow: egc.autorefund | Story | 3 | CLOSED | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25823 | HU Md: Update services in the workflow: egc.autorefund | Story | 3 | CLOSED | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26886 | HU Md: Update current worklow: voiding - Find fcu dependencies | Story | 3 | CLOSED | 2 | Synergy | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25639 | HU Md: Update current worklow: voiding - Changing parts to fit the new adapter | Story | 3 | Closed | 3 | Synergy | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26903 | Hu MD: Update tasks description +diagrams | Story | 3 | Closed | 1 | Synergy |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26107 | HU DRS: Suspend Process for RVM Vouchers | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26502 | HU DRS: Fix printer error after suspend (CreateDepositReturnPayoutReceiptActivity) | Bug | 3 | IN DEVELOPMENT | 3 | Synergy |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
ANP-25388 | HU DRS: Handle API Failures | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-26022 | HU DRS: Offline Scenarios handling | Story | 3 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25733 | [SPIKE] Till unresponsive after display show "Resource for de.gebi" | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27090 | Build MCO part of NEWPOSS release 4.7.10 | Story | 3 | CLOSED | 2 | Synergy | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-27099 | Build MCO part of NEWPOSS release 4.9.0 | Story | 3 | CLOSED | 2 | Synergy | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-20089 | Calculate eligible sum for event vouchers | Task | 3 | CLOSED | 3 | TFS |  | PD | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19961 | Support epay event vouchers | Story | 3 | IN DEVELOPMENT | 3 | TFS |  | PD | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18834 | Prevent Force Close: Restrict partial/split payments with EGC items to avoid incorrect transactions [US only] | Story | 3 | IN DEVELOPMENT | 3 | TFS |  | PD | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19093 | Unclear Customer Intervention for empty ePay Gift Cards | Bug | 3 | IN DEVELOPMENT | 3 | TFS |  | M | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
NPSCO-18025 | SCO 9 (lane 5) - Is showing signs of double charge SCO bug | Bug | 2 | IN DEVELOPMENT | 3 | TFS |  | M | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19094 | Unclear Customer Intervention for insufficient Balance during payment | Bug | 3 | IN DEVELOPMENT | 3 | TFS |  | M | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20187 | Card payment screen includes split payment option | Bug | 2 | CLOSED | 2 | TFS | yes | M | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-20152 | Onboarding Thien-Phuoc Hoang | Task | 3 | IN PROGRESS | 3 | TFS |  | M | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19395 | Update RP Services | Story | 3 | closed | 5 | TNT |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-19913 | Testing monitored item adapter implementation | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19917 | SCO ¦ [KW14] 0% VAT rate mapping issues | Bug | 2 | IN DEVELOPMENT | 3 | TNT |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-20078 | Releasetesting 4.21 | Task | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17559 | Add spans and traces to all services | Story | 3 | IN DEVELOPMENT | 3 | TNT |  |  | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
NPSCO-20127 | SCO - Infrastructure Adapter Java Upgrade 17 | Story | 3 | IN DEVELOPMENT | 5 | TNT |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
NPSCO-20189 | Knowledge Transfer for QF-Test PoC | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20190 | Knowledge Transfer for gRPC Performance Test | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20200 | Exchange of ideas to find solutions (Frozen SCO) | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17408 | [Tech Debt Task] Implement a purchase command for adding extension properties only - follow up | Task | 3 | closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-20318 | Onboarding Bashar Deeb | Task | 3 | closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20365 | Amounts of salesPerTaxRate, the amount is not the same as totalSales | Bug | 2 | In Progress | 3 | TNT | yes |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
NPSCO-20441 | Provide MSIs Containing Celonis | Task | 3 | closed | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18838 | WRONG CHECK DIGIT intervention is not triggered immediately after a WERW item is added to receipt by itemid | Bug | 3 | In Development | 5 | TTT |  | Bocked, waiting for alignment with DN | Not Completed | 5 |  | 5 | 0 | 0 | 0 | 5
NPSCO-20192 | Barcode is wrongly detected as PERW item | Bug | 2 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19980 | Java Error when closing and opening lane | Bug | 3 | Closed | 3 | TTT |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-19990 | Release Tests 4.21.0 | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18840 | Remove first prepareCharge call when pressing charge after scanning EGC (EPAY only) | Story | 3 | Closed | 2 | TTT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-19181 | Correct workflow for entering invalid EGC | Bug | 3 | Closed | 3 | TTT |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-19346 | [Test] Margin calculation | Story | 3 | In Test | 2 | TTT |  |  | Not Completed |  | 2 | 2 | 0 | 0 | 0 | 2
NPSCO-18829 | [US] Customer intervention in Sales | Story | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19147 | Correct error messages | Bug | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20205 | Knowledge Transfer for TNT | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19347 | Customer intervention after entering PinPrinting item | Story | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19618 | Errorhandling for PinPrinting | Story | 3 | In Development | 5 | TTT |  |  | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
NPSCO-17173 | Clean up TODOs [1 PD] (follow up) | Task | 2 | In Development | 1 | TTT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-26547 | BF-835 Agg. printed receipts | Story |  | In Development | 13 | Vlinder |  |  | Not Completed | 3 | 5 | 3 | 0 | -2 | 0 | 5
ANP-26728 | BF-1321 integrity tests for BF-73 | Story |  | In Development | 5 | Vlinder |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-26743 | BF-1416 Bug PDF in Yocuda | Story |  | In Development | 3 | Vlinder | yes |  | Not Completed | 3 | 3 | 0 | 3 | 0 | 0 | 3
ANP-26963 | BF-1458 Build MSI | Story |  | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26959 | BF-1457 Test Support | Story |  | Closed | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26904 | BF-843 Promotions on Display | Story |  | in development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26905 | BF-175 Change refund workflow | Story |  | in development | 5 | Vlinder |  |  | Not Completed | 3 | 2 | 3 | 0 | 1 | 0 | 2
ANP-26973 | BF-1425 Bug - receipt with EFT-payment | Story |  | closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-27087 | BF-1477 Bug EFT identifcation | Story |  | in development | 3 | Vlinder | yes |  | Not Completed | 2 | 1 | 0 | 2 | 1 | 0 | 1
ANP-26902 | Update technical documentation | Story |  | Closed | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-27067 | BF-1476 - Bug for mapping | Story |  | in development | 3 | Vlinder | yes |  | Not Completed | 0 | 3 | 0 | 0 | -3 | 0 | 3
BF-1409 | [SCO] Integrate POS core version 3.1.37 and integrate changes to NFC capturing implementation | Story | 3 | Closed | 2 | Papillon |  |  | Completed | 0.5 | 0 | 2 | 0 | - | 0 | 0
BF-1419 | [SCO] Remove retailer receipt from customer receipt PDF | Story | 3 | Closed | 3 | Papillon |  |  | Completed | 3 | 0 | 3 | 0 | 3 | 0 | 0
BF-1427 | [ADAPTER] Add receipt_position_type and receipt_position_article_type information | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1429 | [SCO] Set value to indicate whether a financial transaction (EGC/PP) is a SALE or a RETURN | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1437 | [ADAPTER] Update receipt repository API in Butterfly adapter | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  | 0 | 0 | 2 | 2 | 0 | 0
BF-1438 | [SCO] Refund Functionality has to be configured in order to activate Repository based Refund | Bug | 3 | Closed | 2 | Papillon |  |  | Completed |  | 0 | 2 | 0 | 2 | 0 | 0
BF-1442 | [SCO][ADAPTER] Update Butterfly adapter in combined service PI-2-2 | Story | 3 | Closed | 0.5 | Papillon |  |  | Completed |  | 0 | 0 | 0 | - | 0 | 0
BF-1443 | [SCO] Do not print unique receipt ID and flag receipts, that have been closed via "Force Close" | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1459 | [ADAPTER] Do not forward receipts closed via "Force Close" to Yocuda | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  | 0 | 2 | 0 | 2 | 0 | 0
BF-1474 | [SCO] Add parameter to steer whether the customer card reminder pop-up should be displayed | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  | 0 | 0 | 3 | 3 | 0 | 0
BF-1484 | [ADAPTER] use OpenAPI mapping in Yocuda mock to increase code coverage | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  | 0 | 0 | 2 | 2 | 0 | 0
NPSCO-18815 | FTH: Fix all bugs and vulnerabilities listed in Sonar | Task | 3 | Closed | 2 | Papillon |  |  | Completed |  | 0 | 2 | 0 | 2 | 0 | 0
NPSCO-18817 | Pricing: Fix all bugs and vulnerabilities listed in Sonar | Task | 3 | Closed | 2 | Papillon | yes |  | Completed |  | 0 | 0 | 2 | 2 | 0 | 0
NPSCO-20021 | [SCO] Update SCO parameter documentation | Story | 3 | Closed | 8 | Papillon |  |  | Completed | 0.5 | 0 | 8 | 0 | - | 0 | 0
BF-1440 | [SCO] Deployment and test support PI-2-2 | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1441 | [SCO] Release tests PI-2-2 | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-507 | [ADAPTER] Add ability to send sale void receipts to Yocuda | Story | 3 | In Development | 5 | Papillon |  | The story not being closed is primarily related to more important tasks taking precedence with the review of the created test data being put on the back burner. | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
BF-1412 | [ADAPTER] Revise BF adapter tests and test data | Story | 3 | In Development | 8 | Papillon |  | Is done, but as this ticket has been split from BF-507: [ADAPTER] Add ability to send sale void receipts to Yocuda and thus also developed together with BF-507: [ADAPTER] Add ability to send sale void receipts to Yocuda. both tickets have to be done to merge the related changes. | Not Completed | 1 | 0 | 1 | 0 | 1 | 0 | 0
BF-1505 | Onboarding Jonas | Story | 3 | In Development | 0 | Papillon |  |  | Not Completed |  | 0 | 0 | 0 | 0 | 0 | 0
NPSCO-18531 | Remove conditional Bean creation in pricing service | Task | 3 | Closed | 5 | Papillon | yes |  | Not Completed |  | 1 | 0 | 5 | 4 | 0 | 1
NPSCO-19363 | Merge the three article lookup methods into one | Task | 3 | In Development | 13 | Papillon |  | re-estimated to 13 SP due to lots of open questions | Not Completed | 7 | 5 | 7 | 0 | 2 | 0 | 5
BF-1530 | [ADAPTER] Fix code coverage in adapter to include all tests | Story | 3 | In Development | 2 | Papillon | yes |  | Not Completed |  | 0.5 | 0 | 2 | - | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_2_1 (hidden)
Sprint 2025_2-1, 16.04.2025 - 29.04.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 21 | 17 | 38 | 14 | 40 | 12 | 0 | 52 |  | 38 | 14 | 40 | 0 | 12 | 105.3%
|  | Payment | 11 | 7 | 15 | 5 | 13 | 7 | 0 | 20 |  | 15 | 5 | 13 | 0 | 7 | 86.67%
|  | Sales | 10 | 8 | 39 | 8 | 26 | 21 | 0 | 47 |  | 39 | 8 | 37 | 0 | 10 | 94.87%
|  | Vlinder | 13 | 11 | 47 | 15 | 44 | 18 | 0 | 62 |  | 36 | 15 | 40 | 0 | 11 | 111.1%
|  | TTT | 11 | 7 | 26 | 8 | 25 | 9 | 0 | 34 |  | 15 | 8 | 13 | 0 | 10 | 86.67%
|  | TNT | 11 | 9 | 33 | 7 | 32 | 8 | 0 | 40 |  | 27 | 7 | 28 | 0 | 6 | 103.7%
|  | TFS | 10 | 6 | 26 | 7 | 17 | 16 | 0 | 33 |  | 24 | 7 | 19 | 0 | 12 | 79.17%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 13 | 11 | 47 | 0 | 34 | 13 | 0 | 47 |  | 47 | 0 | 37 | 0 | 10 | 78.72%
|  | Papillon | 16 | 10 | 48 | 15 | 29 | 34 | 0 | 63 |  | 41 | 15 | 41.5 | 0 | 12.5 | 101.2%
|  | Total | 87 | 65 | 224 | 64 | 197 | 91 | 0 | 288 |  | 194 | 64 | 190 | 0 | 68 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 85 | 321 | 31 | 79 | 116 | 400 | 115 | 398 | 1 | 2 | 116 | 400
|  | Completed | 67 | 220 | 19 | 40 | 86 | 260 | 86 | 260 | 0 | 0 | 86 | 260
|  | Not Completed | 17 | 99 | 12 | 39 | 29 | 138 | 29 | 138 | 0 | 0 | 29 | 138
|  | Removed | 1 | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 2
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-26712 | Integrate new SI FURS certificate for fiscalisation | Story | 1 | Closed | 5 | Engineering | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
CHO-6200 | Power Button on Beetle PCs not working | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6435 | CMDB: Printer vendor equals model number | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6452 | Discuss MCO virtualisation with Sascha Küppers (ADX QA) | Task | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6462 | Determine NCR printer firmware versions currently in production | Task | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-6470 | Improve RPM Vulnerability Report | Task | 4 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-6505 | Support NIT UK in mapping card types to means of payment for P400 over TransaxEFT OPI | Task | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-6519 | Pick CHO-4864 into 1.25E2 release | Bug | 1 | Closed | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
CHO-6521 | CHO-Part of ANP-26712 (Add new Slovenian certificate to CHO-artefacts) | Story | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-6543 | Support SCO with udate-problems | Task | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-26106 | 102-125 Scale Port error - 4.7.2.1 - Datalogic Bizerba Serial_virtual_usb | Bug | 3 | Ready | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6158 | Provide HWLM information for Preh keyboards | Story | 3 | In Development | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6422 | [IT] No Fiscal Data transmitted to Fiscal Server | Bug | 1 | In Test | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6438 | CMDB: 2x20 character display is always present in cmdb.py output | Bug | 3 | In Acceptance | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6445 | CMDB: Integrate <spec> elements as <component> elements | Story | 3 | In Review | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6448 | CMDB: 6.5" display not recorded | Bug | 3 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6449 | CMDB: GM4500 scanner not present in cmdb.py output | Bug | 3 | In Development | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6475 | Release Sprint 2025_PI2-1 Artifacts | Story | 3 | Blocked | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6485 | Testlab maintenance | Task | 3 | In Progress | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6520 | New DN Touch Screens ( D2156 D1156) not working | Bug | 1 | Blocked | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-19939 | Receive CHO environment configuration for butterfly | Story | 3 | In Review | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26411 | CHOP AT ¦ receipt signature timestamp not considered as leading ordering data in DEP | Story | 2 | closed | 3 | Payment |  | ANP- | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26447 | Pick Tickets for Releases 4.7.6 and 4.7.7 | Story | 3 | closed | 1 | Payment |  | RT | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26109 | Build MCO part of NEWPOSS release 4.7.6 | Story | 3 | closed | 3 | Payment |  | RT | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25421 | EFT - Foreign cards transactions (Carrefour France, Ukraine) were not successful according to cash register, but charged to customer | Bug | 2 | in development | 3 | Payment |  | M | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
ANP-26500 | Clean stale branches | Task | 3 | closed | - | Payment |  | M | Removed |  |  | 0 | 0 | 0 | 0 | 0
ANP-25572 | [CHOP] Incorrect POS display message during Cashback | Bug | 3 | in development | 3 | Payment | yes | M | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-25479 | [CHOP] 97+CODE does not trigger the print of the dayend receipt | Bug | 2 | closed | 3 | Payment |  | M | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26506 | Analysis of ANP-25572: [CHOP] Incorrect POS display message during Cashback | Story | 3 | closed | 1 | Payment |  | M | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26507 | Analysis of ANP-25544: [CHOP] Main printer does not indicate empty paper roll | Story | 3 | closed | 1 | Payment |  | M | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26613 | Analysis of ANP-25567: [CHOP] Lane status do not show "Low Paper" Warning | Story | 3 | closed | 1 | Payment | yes | M | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-26869 | Analysis of ANP-26718: [1] Main Driver: Conduction of RCA for "no printer" | Story | 1 | ready | 1 | Payment | yes | M | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
ANP-26379 | Unable to sell articles on 3 out of 4 tills | Bug | 1 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26612 | 4 out of 6 tills are non operational, they can not be used for trading. | Bug | 1 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26717 | [QA] only offline balancing available after 1.25E1 update | Bug | 1 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26456 | Scanning of pensioners card at ringing | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26458 | Print pensioners ID number on the receipt | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-26340 | Performance Analysis - Conduct analysis regarding masterdata provison processing | Story | 3 | In Development | 8 | Sales |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-26056 | Build MCO part of NEWPOSS release 4.8.0 | Story | 3 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26448 | Build MCO part of NEWPOSS release 4.7.7 | Story | 3 | In Development | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-12281 | Remove non-layout business logic from BOs | Story | 3 | In Development | 13 | Sales |  |  | Not Completed |  | 2 | 13 | 0 | 11 | 0 | 2
ANP-26870 | Build MCO part of NEWPOSS release 4.7.8 | Story | 3 | In Development | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25386 | HU DRS: Implement Voucher Processing Flow for Partial Cash-Out | Story | 3 | Blocked | 8 | Synergy |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-25623 | HU Md: Update current worklow: cancelreceipt | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25628 | HU Md: Update current worklow: fiscalmenu | Story | 3 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25630 | HU Md: Update current worklow: logout | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25640 | HU Md: Update services in the workflow: prestart | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25822 | HU Md: Update services in the workflow: cancelreceipt | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25825 | HU Md: Update services in the workflow: fiscalmenu | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25826 | HU Md: Update services in the workflow: login | Story | 3 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25827 | HU Md: Update services in the workflow: logout | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25829 | HU Md: Update services in the workflow: postlogout | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25836 | HU DRS: Connection to back office API to check validity online | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25837 | HU DRS: Implement voucher state management | Story | 3 | In Development | 5 | Synergy |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-26012 | ROUND_TAX_AMOUNT tax rounding method not working as expected | Bug | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19102 | [ITA] Stuck in the transaction after broken fiscalisation and egc | Bug | 3 | in development | 5 | TFS |  | M | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19773 | [Bug] Receipt cannot be found after power off | Bug | 2 | in development | 5 | TFS |  | M | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-18834 | Prevent Force Close: Restrict partial/split payments with EGC items to avoid incorrect transactions [US only] | Story | 3 | in development | 5 | TFS |  | PD | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
NPSCO-18025 | SCO 9 (lane 5) - Is showing signs of double charge SCO bug | Bug | 2 | in development | 3 | TFS |  | M | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-20087 | Prepare event vouchers test data | Task | 3 | closed | 2 | TFS |  | PD | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-20089 | Calculate eligible sum for event vouchers | Task | 3 | in progress | 3 | TFS | yes | PD | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-20022 | Test Task 4.19.0 | Task | 3 | closed | 3 | TFS |  | RT | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20023 | Release Build 4.21.0 | Task | 3 | in progress | 3 | TFS |  | RT | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20148 | Test Task 4.21.0 | Task | 3 | in progress | 3 | TFS | yes | RT | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-20144 | Onboarding Thien-Phuoc Hoang | Task | 3 | in progress | 1 | TFS | yes | M | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19497 | [8] Move configuration to CFRM | Story | 3 | CLOSED | 8 | TNT |  |  | Completed | 4 |  | 4 | 0 | 4 | 0 | 0
NPSCO-19400 | SCO Freezes ASSCO 3.13.5 | Bug | 2 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19730 | Install and document memory related tools in the test lab | Story | 3 | CLOSED | 5 | TNT |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-19395 | Update RP Services | Story | 3 | IN DEVELOPMENT | 5 | TNT |  |  | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
NPSCO-17533 | [Infinity] DRS/RVM causing balancing issues on SCOs. | Bug | 2 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19714 | [Spike 3 Days] Getting traceids with opentelemetry between grpc calls | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19873 | RVM voucher selling is not possible on IRL SCO | Bug | 2 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19913 | Testing monitored item adapter implementation | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-20042 | Testing Sprint 419 MSIs | Story | 3 | CLOSED | 1 | TNT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-20078 | Releasetesting 4.21 | Story | 3 | CLOSED | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-17559 | Add spans and traces to all services | Story | 3 | IN DEVELOPMENT | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-19991 | Mock extension for event voucher | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17958 | Integrate CHO's MQTT service | Story | 3 | Closed | 5 | TTT |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-15130 | Allow maintenance of SixpackConfig.xml via CFRM | Story | 3 | Closed | 3 | TTT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-18801 | Adapt Medion/ETC provider to support PIN printing items | Story | 3 | Closed | 5 | TTT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-18823 | [Receipt Archive] Some receipts in the receipt archive lead to an error and can not be printed | Bug | 3 | Closed | 3 | TTT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-18838 | WRONG CHECK DIGIT intervention is not triggered immediately after a WERW item is added to receipt by itemid | Bug | 3 | In Development | 1 | TTT |  | Further investigation requried, possibly code change in SCO required | Not Completed |  | 5 | 1 | 0 | -4 | 0 | 5
NPSCO-19915 | Till Report - changing layout for display currency | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19990 | Release Tests 4.21.0 | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19980 | Java Error when closing and opening lane | Bug | 3 | In Development | 3 | TTT | yes |  | Not Completed |  | 2 | 0 | 3 | 1 | 0 | 2
NPSCO-18840 | Remove first prepareCharge call when pressing charge after scanning EGC (EPAY only) | Story | 3 | In Development | 2 | TTT | yes |  | Not Completed |  | 1 | 0 | 2 | 1 | 0 | 1
NPSCO-19181 | Correct workflow for entering invalid EGC | Bug | 3 | in development | 3 | TTT | yes |  | Not Completed |  | 2 | 0 | 3 | 1 | 0 | 2
ANP-25605 | BF-73 [MCO] Customer ID - Identify customer ID via EFT device with NFC during ringing - 2-tap-solution | Story | 3 | Closed | 13 | Vlinder |  | SP adjusted from 8 to 13 | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-26128 | BF-1181 Bug for BF-458 | Story | 2 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26180 | BF-1287 Build MSI on 16.04.2025 | Story | 3 | Closed | 3 | Vlinder |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-26445 | BF-1364 Bug - regular items in structured data | Story | 2 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26550 * | BF-1247 Bug for BF-620 | Story | 3 | Closed | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26753 * | Standards & Trainings | Story | 3 | Closed | 1 | Vlinder | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25192 | BF-833 Aggregation Pt.3 | Story | 3 | In Development | 3 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-26546 | BF-1163 Ref. Refund | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26547 | BF-835 Agg. printed receipts | Story | 3 | In Development | 13 | Vlinder |  | SP adjusted from 8 to 13 | Not Completed |  | 8 | 13 | 0 | 5 | 0 | 8
ANP-26604 | BF-1389 Test Support | Story | 3 | In Development | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26728 * | BF-1321 integrity tests for BF-73 | Story | 3 | In Development | 5 | Vlinder | yes |  | Not Completed |  | 3 | 0 | 5 | 2 | 0 | 3
ANP-26743 * | BF-1416 Bug PDF in Yocuda | Story | 2 | In Development | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26760 * | BF-1415 Aggregation Pt. 5 | Story | 3 | In Development | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-507 | [ADAPTER] Add ability to send sale void receipts to Yocuda | Story | 3 | In Development | 5 | Papillon |  | Bottleneck RE approval | not completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
BF-1409 | [SCO] Integrate POS core version 3.1.37 and integrate changes to NFC capturing implementation | Story | 3 | In Development | 2 | Papillon | yes | Only test and merge remain. | not completed |  | 0.5 | 0 | 2 | - | 0 | 0
BF-1412 | [ADAPTER] Revise BF adapter tests and test data | Story | 3 | In Development | 8 | Papillon | yes | was created on the basis of BF-507 and pulled directly into the sprint | not completed |  | 1 | 0 | 8 | 7 | 0 | 1
BF-1419 | [SCO] Remove retailer receipt from customer receipt PDF | Story | 3 | In Development | 3 | Papillon | yes | was puled just before end of sprint | not completed |  | 3 | 0 | 3 | 0 | 0 | 3
NPSCO-19363 | Merge the three article lookup methods into one | Task | 3 | In Progress | 8 | Papillon |  | Updated to 8 SP because of the additional creation of the masterdata service. 7 SP remaining | not completed | 5 | 7 | 5 | 0 | -2 | 0 | 7
NPSCO-20021 | [SCO] Update SCO parameter documentation | Story | 3 | In Development | 8 | Papillon |  |  | not completed | 8 | 0.5 | 8 | 0 | 7.5 | 0 | 0.5
BF-511 | [ADAPTER] Extend Butterfly adapter documentation with a general description of the adapter | Story | 3 | Closed | 5 | Papillon |  |  | completed |  | 0 | 5 | 0 | 5 | 0 | 0
BF-1159 | [ADAPTER] Extend return information provision for multi-receipt cases with special article types (intermediate refund functionality with quantity checks only) | Story | 3 | Closed | 5 | Papillon |  |  | completed |  | 0 | 5 | 0 | 5 | 0 | 0
BF-1316 | [ADAPTER][SCO] Create and test installation artifacts for system integration test at ALDI (due 16.04.25 EOB) | Story | 3 | Closed | 5 | Papillon |  |  | completed |  | 0 | 5 | 0 | 5 | 0 | 0
BF-1317 | [SCO] Add customer card capturing method parameterization | Story | 3 | Closed | 3 | Papillon |  |  | completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1318 | [ADAPTER] Add the option to provide returnPositionProperties on position level and forward this information to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1378 | [SCO] Deployment and test support PI-2-1 | Story | 3 | Closed | 0.5 | Papillon |  |  | completed |  | 0 | 0.5 | 0 | 0.5 | 0 | 0
BF-1379 | [SCO] Release tests 4.21.0 | Story | 3 | Closed | 3 | Papillon |  |  | completed |  | 0 | 3 | 0 | 3 | 0 | 0
BF-1380 | [SCO][ADAPTER] Update Butterfly adapter in combined service PI-2-1 | Story | 3 | Closed | 0.5 | Papillon |  |  | completed |  | 0 | 0.5 | 0 | 0.5 | 0 | 0
NPSCO-18816 | Purchase: Fix all bugs and vulnerabilities listed in Sonar | Task | 3 | Closed | 2 | Papillon |  |  | completed |  | 0 | 2 | 0 | 2 | 0 | 0
NPSCO-20174 | Autoupdate fails due to interference from CHO updater | Bug | 1 | Closed | 2 | Papillon | yes |  | completed |  | 0 | 0 | 2 | 2 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_1_6 (hidden)
Sprint 2025_1-6, 02.04.2025 - 15.04.2025, Status at Sprint Completion
|  | Team Summary |  |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 25 | 19 | 66 | 16 | 68 | 14 | 0 | 82 |  | 66 | 16 | 68 | 0 | 14 | 103%
|  | Payment | 13 | 11 | 36 | 9 | 39 | 6 | 0 | 45 |  | 15 | 9 | 18 | 0 | 6 | 120%
|  | Sales | 16 | 15 | 37 | 19 | 48 | 8 | 0 | 56 |  | 33 | 19 | 47 | 0 | 5 | 142.4%
|  | Vlinder | 11 | 8 | 40 | 6 | 32 | 14 | 0 | 46 |  | 29 | 6 | 28 | 0 | 7 | 96.55%
|  | TTT | 13 | 9 | 46 | 6 | 26 | 26 | 0 | 52 |  | 31 | 6 | 32 | 0 | 5 | 103.2%
|  | TNT | 16 | 10 | 36 | 20 | 31 | 25 | 0 | 56 |  | 36 | 20 | 31 | 0 | 25 | 86.11%
|  | TFS | 10 | 8 | 23 | 3 | 18 | 8 | 0 | 26 |  | 21 | 3 | 19 | 0 | 5 | 90.48%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 14 | 12 | 37 | 5 | 36 | 6 | 0 | 42 |  | 36 | 5 | 36 | 0 | 5 | 100%
|  | Papillon | 22 | 16 | 31 | 28.5 | 51 | 21 | 0 | 77 |  | 21 | 46 | 55 | 0 | 12 | 261.9%
|  | Total | 104 | 80 | 284 | 79 | 262 | 101 | 0 | 363 |  | 231 | 79 | 243 | 0 | 67 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 100 | 369.5 | 40 | 114.5 | 140 | 484 | 139 | 482 | 1 | 2 | 140 | 484
|  | Completed | 84 | 293.5 | 24 | 57.5 | 108 | 351 | 107 | 349 | 1 | 2 | 108 | 351
|  | Not Completed | 16 | 76 | 15 | 52 | 31 | 128 | 31 | 128 | 0 | 0 | 31 | 128
|  | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-25478 | [CHOP] Till restarts lead to unresolvable error since no customer scanner was found | Bug | 2 | closed | 3 | Payment | yes | M | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-21583 | Refactor Multilane State | Story | 3 | in development | 21 | Payment |  | PD; practially completed; retroacitvely re-estimated (was 8SP) | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-25381 | Implement Remedy Feature for ANP-25351 | Story | 2 | closed | 3 | Payment |  | PD | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-25543 | [CHOP] EFT dayend only works after first cashier login | Bug | 2 | closed | 3 | Payment |  | M | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-26166 | Pick Tickets for Releases 3.18.11 and 4.7.6 | Story | 3 | closed | 1 | Payment |  | RT | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25992 | Build MCO part of NEWPOSS release 3.18.11 | Story | 2 | closed | 3 | Payment |  | RT; probably completed by end of sprint | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26109 | Build MCO part of NEWPOSS release 4.7.6 | Story | 3 | blocked | 3 | Payment |  | RT | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-26124 | create merge request and follow up ANP-23958 | Task | 3 | closed | 1 | Payment |  | M; estimated retroactively | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26125 | attend Q&A meeting for CDC | Task | 3 | closed | 1 | Payment |  | PD; estimated retroactively | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26402 | Documentation of CHOP AT Specification | Task | 3 | in development | - | Payment | yes | PD; will be estimated retroactively | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-26446 | Analysis of ANP-26411 | Story | 3 | in development | 2 | Payment | yes | PD; will be closed by sprint end | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-26451 | check if ANP-25573 has been fixed (by fixing ANP-25478) | Task | 2 | closed | 1 | Payment | yes | M; estimated retroactively | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25479 | [CHOP] 97+CODE does not trigger the print of the dayend receipt | Bug | 2 | ready | 3 | Payment | yes | M | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-26015 | Proact. - POS - Manual EOD needed on all tills - NO EM | Bug | 1 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24755 | Evaluate capabilities of the receipt layouter component in context of print on demand and receipt shooting | Story | 3 | Closed | 5 | Sales |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-26110 | [Analysis] UK March 2025 Till reboots | Story | 3 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26111 | Build till sharing test artifacts for BO #2 | Story | 3 | Closed | 1 | Sales |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25739 | Merge till sharing feature adaptations to Master | Story | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25949 | Adjust internal data model for POR items in regards to workflow harmonization | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25704 | Harmonize ringing workflow of POSA and POR items (Invoice) | Story | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25169 | Harmonize ringing workflow of POSA and POR items (Inventory/Wastage) | Story | 3 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25699 | Harmonize ringing workflow of POSA and POR items (Sale) | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23825 | General improvements in receipt layout files | Story | 3 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25613 | [HU] Typo displayed on till when void is not possible | Bug | 3 | Closed | 1 | Sales |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25738 | Server mock does not properly simulate Masterdata update | Bug | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26294 | Pick ANP-23677 to 3.18 | Task | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-24855 | Till workflow stuck in CHOP workflow activity after closing a receipt | Bug | 3 | Closed | 5 | Sales | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-12281 | Remove non-layout business logic from BOs | Story | 3 | In Development | 8 | Sales | yes | was pulled after start and it was clear that it is not possible to complete it | Not Completed |  | 5 | 0 | 8 | 3 | 0 | 5
ANP-26397 | Analyse newposs-application test memory issues | Task | 3 | Closed | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25039 | ITA Warranty - Non deductable extra text does not appear on the receipt | Bug | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25631 | Update current worklow+service: personalize | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25751 | HU DRS: Automate Applying Vouchers to Transactions | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25838 | HU DRS: Test documentation | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25629 | Update current worklow: login | Story | 3 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25632 | Update current worklow: postlogin | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25644 | Update services in the workflow: codes | Story | 3 | In Development | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25828 | Update services in the workflow: postlogin | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25836 | HU DRS: Connection to back office API to check validity online | Story | 3 | In Development | 3 | Synergy |  |  | Not Completed | 2 |  | 2 | 0 | 0 | 0 | 2
ANP-26080 | HU DRS: Rejection of Quantity for RVM Vouchers | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26108 | [SPIKE] Suspend & Retrieve Process for RVM Vouchers | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26380 * | Sonar Challenge. Rename this constant name to match the regular expression. u2013 - U2013. | Bug | 3 | Closed | 1 | Synergy | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25635 | Update current worklow: recieptfiscalnumber | Task | 3 | closed | 1 | Synergy | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19102 | [ITA] Stuck in the transaction after broken fiscalisation and egc | Bug | 3 | IN DEVELOPMENT | 5 | TFS |  |  | Not Completed | 3 | 2 | 3 | 0 | 1 | 0 | 2
NPSCO-19715 | 1.25E UAT ITA ¦ Fiscal Block Error in SCO Receipt Block | Bug | 1 | CLOSED | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19773 | [Bug] Receipt cannot be found after power off | Bug | 2 | IN DEVELOPMENT | 3 | TFS |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-19717 | [Spike] workflow for event voucher (DE) | Task | 3 | CLOSED | 2 | TFS |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19695 | [SPIKE] Force close in US | Task | 3 | CLOSED | 2 | TFS |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19630 | SCO Receipt is showing Variant numbers (9 digits) - Should only show sellable Generic/ Single | Bug | 3 | CLOSED | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15156 | Dismantle workaround of start Fiscalisation Service only in countries where it's needed | Story | 3 | IN DEVELOPMENT | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19795 | Test Task 4.18.0 | Task | 3 | CLOSED | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19797 | Cherry Pick 3.18.6 | Task | 3 | CLOSED | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19944 | Test Task 3.18.6 | Task | 3 | CLOSED | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19497 | [8] Move configuration to CFRM | Story | 3 | IN DEVELOPMENT | 8 | TNT |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
NPSCO-18312 | Small field-local changes in receipt exports | Story | 3 | closed | 8 | TNT |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
NPSCO-18803 | [Test] Adjust tax rate to 6 decimal places | Story | 3 | closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19189 | The heartbeat frequency should be changed to 10 seconds | Story | 3 | closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19790 | Test SCO Sprint 418 | Story | 3 | closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19145 | Open transactions not always checked after reboot or shutdown of the pos adaper | Bug | 3 | closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19123 | [UK] Export and Notifcation of canceld transaction missing after hard shutdown | Bug | 3 | closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19151 | Full Resync of SCO not working in Gebit testlab | Bug | 3 | closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19400 | SCO Freezes ASSCO 3.13.5 | Bug | 2 | IN DEVELOPMENT | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-15156 | SCO Freezing randomly | Bug | 3 | IN DEVELOPMENT | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-19730 | Install and document memory related tools in the test lab | Task | 3 | IN PROGRESS | 5 | TNT | yes |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
NPSCO-19922 | Test 3.18.6 | Story | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19873 | RVM voucher selling is not possible on IRL SCO | Bug | 2 | IN DEVELOPMENT | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-18665 | Testing every existing promotions | Story | 3 | CLOSED | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19952 | [AUS] Cancel payment button leads to wrong attendant intervention | Bug | 3 | closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19913 | Testing monitored item adapter implementation | Story | 3 | IN DEVELOPMENT | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-19455 | Scanned Grapes (9317948011236) causing intervention for price on SCO | Bug | 2 | Closed | 5 | TTT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-19299 | Product Block did not work on 25th of Januar for 826704 & 810998 in multiple stores | Bug | 3 | Closed | 3 | TTT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19793 | Hot fix build 3.18.6 | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19794 | Release test 3.18.6 | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19734 | Sprint Test 418 | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17958 | Integrate CHO's MQTT service | Story | 3 | In Development | 13 | TTT |  | not enough knowledge at the beginning and much more complex than expected | Not Completed | 4 | 2 | 4 | 0 | 2 | 0 | 2
NPSCO-18819 | simplify teststart | Story | 3 | Closed | 3 | TTT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-15130 | Allow maintenance of SixpackConfig.xml via CFRM | Story | 3 | In Development | 5 | TTT |  | trouble with the local IDE resulted in test problems | Not Completed |  | 1 | 5 | 0 | 4 | 0 | 1
NPSCO-18215 | Test of assco-java-grpc-test-client on Different SCO Systems | Story | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19344 | Implement CFRM parameter for PinPrinting | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18801 | Adapt Medion/ETC provider to support PIN printing items | Story | 3 | In Development | 5 | TTT |  | testing not yet completed | Not Completed |  | 1 | 5 | 0 | 4 | 0 | 1
NPSCO-19471 | Sprint build 419 | Story | 3 | Ready | 1 | TTT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18823 | [Receipt Archive] Some receipts in the receipt archive lead to an error and can not be printed | Bug | 3 | In Development | 3 | TTT | yes | testing not yet completed | Not Completed |  | 1 | 0 | 3 | 2 | 0 | 1
ANP-26112 | BF-1259 Build MSI | Story | 3 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26127 * | BF-796 Bug for BF-64 | Story | 3 | Closed | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-26129 | BF-1154 GetReceiptReturnInformationByNumber | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24907 | BF-775 double item lines | Story | 3 | In Development | 8 | Vlinder |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-25192 | BF-833 Aggregation Pt.3 | Story | 3 | In Development | 3 | Vlinder |  | LTC creation took longer than expected | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
ANP-25605 | BF-73 [MCO] Customer ID - Identify customer ID via EFT device with NFC during ringing - 2-tap-solution | Story | 3 | In Development | 8 | Vlinder |  | Start/Stop listening to VAS-NFC-chip more complex than expected | Not Completed | 2 | 2 | 2 | 0 | 0 | 0 | 2
ANP-25778 | BF-1080 Adapter changes | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-26113 | BF-1260 Support Tests | Story | 3 | In Development | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26123 | Standards & Trainings | Story | 3 | Ready | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26126 | BF-923 Discount info Bug | Story | 3 | In Development | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26180 * | BF-1287 Build MSI on 16.04.2025 | Story | 3 | Ready | 3 | Vlinder | yes | Story pulled into wrong sprint | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-24318 | EFT: Double debiting of card payments | Bug | 2 | Closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25045 | Add butterfly-adapter/combined RPM to release | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5513 | NHPI reconfiguration may fail without exit code indicating an error | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5573 | [5PT] Analyze Hardware information for C2 scale | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5875 | Provide device information for integrated Datalogic scales | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6054 | Fix the jenkins pipeline for cho-ansible 1.2 and 1.9 | Bug | 3 | Closed | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
CHO-6338 | Adjust mosquitto configuration for integration | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6399 | Tills are stuck in GRUB after update 1.23E11 -> 3.1.A13 | Bug | 1 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-6414 | Create documentation for the configuration of the Verifone M424 | Task | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-26181 | List integrated scale as separate device in devices.xml | Story | 3 | In Development | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-26455 | ANP Part of BF-779 | Story | 3 | In Development | 1 | Engineering | yes |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
BF-779 | Provide configuration for Butterfly to tills | Story | 3 | In Review | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-5877 | Provide device information for P400 (OPI) EFT devices to CMDB | Story | 3 | In Test | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-5878 | [3PD] Analyze hardware information for Verifone M424 EFTs | Story | 3 | In Review | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-6158 | Provide HWLM information for Preh keyboards | Story | 3 | In Development | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6200 | Power Button on Beetle PCs not working | Bug | 3 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6201 | Fix testlab CCV Pads | Bug | 3 | In Development | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6324 | NCR 7606, NCR 7607 USB device issues on first rocky versions (UDEV?) | Bug | 3 | In Review | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-6341 | Release Sprint 2025_PI1-6 Artifacts | Story | 3 | Blocked | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6356 | TLRD Task | Task | 3 | In Progress | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6417 | Support team Vlinder in integrating listening for VAS data via NFC Taps | Task | 3 | In Review | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-6455 | CHO part of BF-779 | Story | 3 | In Development | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19874 | List integrated scale as separate device in devices.xml | Story | 3 | In Development | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19939 * | Receive CHO environment configuration for butterfly | Story | 3 | In Review | 1 | Engineering |  |  | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
CHO-6466 | Support team Vlinder for butterfly test system configuration integration | Task | 3 | In Review | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19392 | [SCO] Provide language keys and values | Story | 3 | Closed | 2 | Papillon |  |  | completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1257 | [SCO] Add EGC status receipts to receipt PDF | Story | 3 | Closed | 5 | Papillon |  |  | completed |  |  | 0 | 5 | 5 | 0 | 0
BF-1241 | [SCO][ADAPTER] Update Butterfly adapter in combined service PI-1-6 | Story | 3 | Closed | 0.5 | Papillon |  |  | completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-1239 | [SCO] Release tests PI-1-6 | Story | 3 | Closed | 3 | Papillon |  |  | completed |  |  | 0 | 3 | 3 | 0 | 0
BF-1238 | [SCO] Deployment and test support PI-1-6 | Story | 3 | Closed | 1 | Papillon |  |  | completed |  |  | 1 | 0 | 1 | 0 | 0
BF-1235 | [ADAPTER] Create integration tests against Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | completed | 3 |  | 3 | 0 | 3 | 0 | 0
BF-1224 | [SCO] Update assco-rp-purchase-service to use at least version 3.6.0 of rp-purchase | Story | 3 | Closed | 3 | Papillon |  |  | completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1101 | [SCO] Add support for NFC based customer cards | Story | 3 | Closed | 8 | Papillon |  |  | completed |  |  | 8 | 0 | 8 | 0 | 0
BF-971 | [ADAPTER] Provide return information for multi-receipt cases | Story | 3 | Closed | 8 | Papillon |  |  | completed | 1 |  | 1 | 0 | 1 | 0 | 0
BF-802 | [ADAPTER] Update MapStruct Version used for the combined services | Story | 3 | Closed | 3 | Papillon |  |  | completed |  |  | 3 | 0 | 3 | 0 | 0
BF-625 | [SCO] Print only UK national lottery tickets, if the customer opted out of receiving paper receipts | Story | 3 | Closed | 2 | Papillon |  |  | completed |  |  | 0 | 2 | 2 | 0 | 0
BF-511 | [ADAPTER] Extend Butterfly adapter documentation with a general description of the adapter | Story | 3 | Ready | 5 | Papillon |  |  | not completed |  |  | 0 | 5 | 0 | 0 | 5
BF-507 | [ADAPTER] Add ability to send sale void receipts to Yocuda | Story | 3 | In Development | 5 | Papillon |  |  | not completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
BF-1252 | Payment Blocked and Transaction not Sent to Yocuda when scanning multiple Customers in SCO | Bug | 3 | In Acceptance | 0.5 | Papillon | yes |  | completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-1293 | Payment with EFT (and Voucher) on SCO does not forward the e-Receipt to Youcda | Bug | 3 | In Acceptance | 3 | Papillon | yes |  | completed |  |  | 0 | 3 | 3 | 0 | 0
BF-1359 | Error on GetSerializedReceiptByNumber endpoint | Bug | 3 | In Acceptance | 2 | Papillon | yes |  | completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1264 | SCO - Receipt Header is printed out with raw values | Bug | 2 | In Development | 5 | Papillon | yes |  | removed from sprint |  |  | 0 | 5 | 5 | 0 | 0
BF-1318 | [ADAPTER] Add the option to provide returnPositionProperties on position level and forward this information to Yocuda | Story | 3 | In Development | 3 | Papillon | yes |  | not completed |  | 1 | 0 | 3 | 2 | 0 | 1
BF-1314 | [SCO] Integrate POS core version 3.1.36 | Story | 3 | Closed | 2 | Papillon | yes |  | completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1316 | [ADAPTER][SCO] Create and test installation artifacts for system integration test at ALDI (due 16.04.25 EOB) | Story | 3 | In Test | 5 | Papillon | yes |  | not completed |  | 2 | 0 | 5 | 3 | 0 | 2
BF-1317 | [SCO] Add customer card capturing method parameterization | Story | 3 | In Development | 3 | Papillon | yes | pulled up one day before the end of the sprint | not completed |  | 3 | 0 | 3 | 0 | 0 | 3
NPSCO-19994 | SCO - Receipt Header is printed out with raw values | Bug | 3 | In Test | 5 | Papillon | yes | from development side done but forgot to move the status | completed |  | 0 | 0 | 5 | 5 | 0 | 0
ANP-26012 * | ROUND_TAX_AMOUNT tax rounding method not working as expected | Bug | 3 | In Development | 3 | Synergy | yes |  | not completed | 3 |  | 0 | 3 | 0 | 0 | 3

## Sprint_1_5 (hidden)
Sprint 2025_1-5, 19.03.2025 - 01.04.2025, Status at Sprint Completion
|  | Team Summary |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 18 | 15 | 77 | 6 | 72 | 11 | 0 | 83 |  | 77 | 6 | 72 | 0 | 11 | 93.51%
|  | Payment | 10 | 6 | 24 | 6 | 13 | 17 | 0 | 30 |  | 13 | 6 | 13 | 0 | 6 | 100%
|  | Sales | 9 | 8 | 29 | 7 | 31 | 5 | 0 | 36 |  | 29 | 7 | 35 | 0 | 1 | 120.7%
|  | Vlinder | 14 | 12 | 50 | 3 | 37 | 16 | 0 | 53 |  | 44 | 3 | 42 | 0 | 5 | 95.45%
|  | TTT | 13 | 10 | 38 | 2 | 28 | 12 | 0 | 40 |  | 38 | 2 | 34 | 0 | 6 | 89.47%
|  | TNT | 13 | 12 | 35 | 13 | 46 | 2 | 0 | 48 |  | 27 | 9 | 35 | 0 | 1 | 129.6%
|  | TFS | 12 | 11 | 32 | 6 | 35 | 3 | 0 | 38 |  | 29 | 6 | 32 | 0 | 3 | 110.3%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 14 | 12 | 28 | 13 | 36 | 5 | 0 | 41 |  | 26 | 13 | 36 | 0 | 3 | 138.5%
|  | Papillon | 24 | 17 | 46 | 38 | 55.5 | 26 | 1 | 84 |  | 28 | 38 | 53 | 0 | 13 | 189.3%
|  | Total | 89 | 74 | 285 | 43 | 262 | 66 | 0 | 328 |  | 257 | 39 | 263 | 0 | 33 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 92 | 359 | 35 | 94 | 127 | 453 | 127 | 453 | 0 | 0 | 127 | 453
|  | Completed | 77 | 286 | 26 | 67.5 | 103 | 353.5 | 103 | 353.5 | 0 | 0 | 103 | 353.5
|  | Not Completed | 15 | 73 | 7 | 24 | 22 | 97 | 22 | 97 | 0 | 0 | 22 | 97
|  | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-25918 | BasicCardTransactionData table shows cardExpirationDate of e.g. 59884-10-31 | Bug | 2 | closed | 3 | Payment |  | M | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23202 | Payment of transactions by other voucher (CODE + 30, option 5) related to deposit articles | Bug | 2 | closed | 3 | Payment |  | M | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-21583 | Refactor Multilane State | Story | 3 | in development | 8 | Payment |  | PD | Not Completed | 2 | 2 | 2 | 0 | 0 | 0 | 2
ANP-25381 | Implement Remedy Feature for ANP-25351 | Story | 2 | in development | 3 | Payment |  | PD | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-24918 | Add Cancel Tag to Transaction Data | Story | 3 | closed | 2 | Payment |  | PD; practically finished | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-25731 | [CHOP] Status changes for card payments lead to scanning errors | Bug | 2 | closed | 3 | Payment |  | M; duplicate | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23958 | [IT Ejournal] Error during Ejournal entry creation with EPSON Fiscal Printer | Bug | 3 | blocked | 3 | Payment | yes | M | Not Completed |  | 0 | 0 | 3 | 3 | 0 | 0
ANP-25543 | [CHOP] EFT dayend only works after first cashier login | Bug | 2 | in development | 3 | Payment | yes | M | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-23495 | support Australia regarding CDC | Task | 3 | closed | 1 | Payment |  | PD; completed by definition; retroactively estimated | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25464 | Pick Stories for Version 4.7.5 | Story | 3 | closed | 1 | Payment |  | RT | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24609 | Hu Middleware: Branch configuration | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25389 | HU DRS: Separate Tax Handling for RVM Vouchers | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25584 | tills throw "Ausnahmefehler" after the time limit of "shutdown in 5 minutes" is reached | Bug | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25707 * | 1.25E - UAT ITA ¦ Swapped numbers in receipt metadata block on all receipts | Bug | 2 | Closed | 5 | Synergy | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-24781 | Collect all Logfiles: Testing | Story | 3 | Closed | 3 | Synergy |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-25387 | HU DRS: Implement Local validation of the voucher | Story | 3 | In Review | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25624 * | Make Hu middleware config. with CFRM | Story | 3 | Closed | 5 | Synergy | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-25625 | Update current worklow: codes | Story | 3 | In Review | 3 | Synergy |  |  | Not completed |  | 2 | 3 | 0 | 1 | 0 | 2
ANP-25631 | Update current worklow+service: personalize | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25634 | Update current worklow: prestart | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25751 | HU DRS: Automate Applying Vouchers to Transactions | Story | 3 | In Development | 2 | Synergy |  |  | Not completed |  | 1 | 2 | 0 | 1 | 0 | 1
ANP-25780 | Sonar Challenge PI1-5 | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25781 | SetUp HU in the Test Lab | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19448 | Add missed SSL context initialization after Spring migration | Bug | 1 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17577 | [5] Publish application events to MQTT | Story | 3 | closed | 5 | TNT |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-17562 | [6] Consume events from MQTT, store and forward them | Story | 3 | closed | 8 | TNT |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-19495 | [7] Add the MIA to deployment and combined service | Story | 3 | closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18299 | Some totals fields have to be exported in sales receipts | Story | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18310 | Export cashier and attendant information correctly | Story | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18803 | [Test] Adjust tax rate to 6 decimal places | Story | 3 | In Development | 2 | TNT | yes |  | Not Completed |  | 1 | 0 | 2 | 1 | 0 | 1
NPSCO-19483 | Test SCO Sprint 417 | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19484 | Build Sprint Release 417 | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19324 | CH SCO cannot be initialized, gets stuck in "Waiting for POS connection" | Bug | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19379 | 1.25E SCO Pilots - EM: "scale is not connected" | Bug | 2 | closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18311 | Export sourceContainer and targetContainer in receipts | Story | 3 | Closed | 5 | TNT | yes |  | Completed | 1 |  | 0 | 1 | 1 | 0 | 0
NPSCO-19628 | [CH] Incorrect Translations | Bug | 2 | Closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-15480 | (US-only) Credit payment is printed as "Debit card" in the payment line of printed receipt (all versions) | Bug | 3 | In Development | 3 | TFS |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
NPSCO-19095 | Errors in sale export validation because of addition of [objectType] to objects | Bug | 3 | In Development | 5 | TFS |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-19319 | [ITA] Lottery Code not exported to the RT Server | Bug | 2 | In Development | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19180 | [Bug] Login failure after Power Off | Bug | 2 | In Development | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19176 | Receipt over 1000.00 drops last digit on pre-subtotal when promotion is applied | Bug | 3 | In Development | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19449 | Disable Split Payment for EGC in ITA | Bug | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19139 | EGC payment sometimes not aligned with other payment types | Bug | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19140 | [AUS] EGC partial payment is displayed as Card Payment on the virtual receipt | Bug | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19102 | [ITA] Stuck in the transaction after broken fiscalisation and egc | Bug | 3 | In Development | 3 | TFS | yes |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
NPSCO-19453 | Onboarding Paulo Moura Guedes | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19485 | Test Task 4.17.0 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19496 | Release Build 4.21.0 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25951 * | [SPIKE] 1.25E; IT; Instant lottery QR code is missing on receipt | Story | 2 | In Development | 3 | Synergy | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19629 | MSI for 418 (for PI presentation) | Story | 3 | Closed | 1 | TTT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19455 | Scanned Grapes (9317948011236) causing intervention for price on SCO | Bug | 2 | In Development | 5 | TTT |  |  | Not Completed |  | 1 | 5 | 0 | 4 | 0 | 1
NPSCO-19103 | Exit gate barcode | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18885 | Adapt master data lookup for PIN Printing articles in FTH | Story | 3 | In Development | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19076 | Test data from provider | Story | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18379 | Change sales limit for EGCs in US | Task | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19339 | Add FR language for Till report | Story | 3 | In Development | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-19408 | Wrong value in isResyncAllowed | Bug | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17958 | Integrate CHO's MQTT service | Story | 3 | In Development | 5 | TTT |  |  | Not Completed |  | 4 | 5 | 0 | 1 | 0 | 4
NPSCO-19468 | Show six-pack button only when UoM 'PK' is maintained for that article | Story | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18819 | simplify teststart | Story | 3 | Ready | 2 | TTT |  |  | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
NPSCO-19172 | Release Test 417 [M] | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19668 | Test Spring boot fix (NPSCO-19352) | Task | 3 | Closed | 1 | TTT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25603 | 1.25E UAT ITA ¦ wrong wording via code75 on till | Bug | 2 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25997 | [Analysis] DE March 2025 Till reboots | Story | 3 | In Development | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-22554 | [ITA] 5+Code on MCO of SCO receipt leads to till freeze | Bug | 2 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25736 | Build till sharing test artefacts for BO | Story | 3 | In Acceptance | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-24755 | Evaluate capabilities of the receipt layouter component in context of print on demand and receipt shooting | Story | 3 | In Development | 5 | Sales |  |  | Not Completed |  | 1 | 5 | 0 | 4 | 0 | 1
ANP-25159 | Harmonize POS service layer for gift cards and PIN Printing | Story | 3 | In Development | 13 | Sales |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-25038 | Maven install command fails | Bug | 3 | In Development | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25782 | Pick Stories to 4.7 maintenance branch for NEWPOSS 4.7.5 | Story | 3 | Closed | 1 | Sales |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25592 | Remove obsolete Pick-Up-related code | Story | 3 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25685 | Build MCO part of NEWPOSS release 3.18.10 | Story | 2 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25722 * | Merge feature branch for BF-1032 | Story | 3 | Closed | 1 | Vlinder | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25724 | Fix Data Processing Blinker | Story | 3 | Closed | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25842 | BF-1183 Build MSI | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25989 * | BF-1214 Adjust dummy data | Story | 3 | Closed | 2 | Vlinder | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-24906 | BF-774 EFT terminal lines | Story | 3 | In Development | 5 | Vlinder |  |  | Completed | 5 |  | 5 | 0 | 5 | 0 | 0
ANP-24907 | BF-775 double item lines | Story | 3 | In Development | 8 | Vlinder |  | SP adjustment from 5 to 8 | Not Completed | 5 | 3 | 5 | 0 | 2 | 0 | 3
ANP-25193 | BF-834 Aggregation Pt.4 | Story | 3 | In Development | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25474 | BF-134 Return Info Mapping | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25605 | BF-73 [MCO] Customer ID - Identify customer ID via EFT device with NFC during ringing - 2-tap-solution | Story | 3 | In Development | 8 | Vlinder |  |  | Not Completed | 5 | 2 | 5 | 0 | 3 | 0 | 2
ANP-25670 | Build MCO part of NEWPOSS release 4.7.5 | Story | 3 | Blocked | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25747 | BF-1162 Support Tests | Story | 3 | In Development | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25777 | BF-1071 New Logos | Story | 3 | In Development | 2 | Vlinder |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25376 | Build MCO part of NEWPOSS release 4.8.0 (PI1.5) | Story | 3 | Closed | 1 | Vlinder |  | Taken out of sprint after some work was already done. | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25607 | [QA][Tr-Stores-IIT-Legacy testroom] TILL does not always update to NP 4.7.3.1 from lower versions during Ivanti update path tests for Releases 4.1C2/1.26D | Bug | 1 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5944 | Adjust to NEWPOSS log file (path) changes | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6133 | Release Sprint 2025_PI1-4 Artifacts | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6202 | Run CIS Benchmark for 2025_PI1 | Story | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-6289 * | [HU] update incident 25.03 | Bug | 1 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-6307 | MI ¦ CHOP Scale - store was unable to trade on 2/3 tills due to error message: Waage inaktiv | Bug | 2 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24318 | EFT: Double debiting of card payments | Bug | 2 | In Development | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
BF-792 | Implement support for ValueAddedServices for P400 EFTs | Story | 3 | In Review | 13 | Engineering |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
CHO-5573 | [5PT] Analyze Hardware information for C2 scale | Story | 3 | In Development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-5575 | [3PT] Analyze hardware information for integrated Datalogic scales | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5837 | Provide device information for CCV Pad Next to CMDB | Story | 3 | In Acceptance | 20 | Engineering |  |  | Completed |  |  | 20 | 0 | 20 | 0 | 0
CHO-5878 | [3PD] Analyze hardware information for Verifone M424 EFTs | Story | 3 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5886 | [3PD] Analyze hardware information for VGA displays | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6201 | Fix testlab CCV Pads | Bug | 3 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6224 | TLRD Task | Task | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6225 | Release Sprint 2025_PI1-5 Artifacts | Story | 3 | Blocked | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6278 * | Remove Application Status from Performance Overview | Story | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-6294 * | Insufficient permissions to run cmdb.py by discovery_stores user | Bug | 2 | In Review | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-19352 | Double instantiation bug | Bug | 3 | Closed | 13 | Papillon |  | reestimated from 5 to 13 SP due to the needed QA measures | completed | 3 |  | 3 | 0 | 3 | 0 | 0
BF-1182 | [ADAPTER] Mapping of article identifiers in financial transactions is not corect | Bug | 3 | Closed | 2 | Papillon | yes |  | completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1164 | [SCO] Release tests PI-1-5 | Story | 3 | Closed | 3 | Papillon |  |  | completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1158 | [SCO] Deployment and test support PI-1-5 | Story | 3 | Closed | 1 | Papillon |  |  | completed |  |  | 1 | 0 | 1 | 0 | 0
BF-1156 | BF-458 - Adapter - Attributes sent to Yocuda with expected mapping is not correct for SCO | Bug | 2 | Closed | 2 | Papillon | yes |  | Won't Do |  |  | 0 | 2 | 2 | 0 | 0
BF-1112 | [ADAPTER] Implement GetSerializedReceiptByNumber endpoint | Story | 3 | Closed | 2 | Papillon |  |  | completed |  |  | 2 | 0 | 2 | 0 | 0
BF-1094 | [ADAPTER][SCO] Update receipt repository API in MCO and SCO combined service | Story | 3 | Closed | 5 | Papillon | yes |  | completed |  |  | 0 | 5 | 5 | 0 | 0
BF-1021 | [SCO] Amend customer card capturing workflow | Story | 3 | Closed | 3 | Papillon |  |  | completed | 1 |  | 1 | 0 | 1 | 0 | 0
BF-971 | [ADAPTER] Provide return information for multi-receipt cases | Story | 3 | In Development | 8 | Papillon |  |  | not completed |  | 1 | 8 | 0 | 7 | 0 | 1
BF-868 | [ADAPTER] Provide basic return information to checkout for preliminary refund functionality | Story | 3 | Closed | 5 | Papillon |  |  | completed | 1 |  | 1 | 0 | 1 | 0 | 0
BF-509 | [ADAPTER] Improve error handling during provision of customer information from CEE | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-507 | [ADAPTER] Add ability to send sale void receipts to Yocuda | Story | 3 | In Development | 5 | Papillon |  |  | not completed |  | 2 | 5 | 0 | 3 | 0 | 2
BF-506 | [ADAPTER] Add ability to send refund receipts to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
BF-1218 | [SCO] Prepare support for NFC based customer cards | Story | 3 | Closed | 5 | Papillon | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
BF-1101 | [SCO] Add support for NFC based customer cards | Story | 3 | In Development | 8 | Papillon | yes |  | not completed |  | 5 | 0 | 8 | 3 | 0 | 5
BF-1216 | BF-714 - SCO - Re-Identifying different Customers adds promotions instead of replacing | Bug | 2 | Closed | 0.5 | Papillon | yes |  | Won't Do |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-1160 | [SCO] Improve error handling for failed requests to CEE | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1236 | [ADAPTER] Butterfly Adapter cannot forward receipts with CASH payments to Yocuda | Story | 2 | Closed | 0.5 | Papillon | yes |  | Completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-1240 | [SCO][ADAPTER] Update Butterfly adapter in combined service PI-1-5 |  | 3 | Closed | 0.5 | Papillon | yes |  | completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-1103 | [ADAPTER] Do not forward unsuccessful payments to Yocuda |  | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1235 | [ADAPTER] Create integration tests against Yocuda | Story | 3 | In Development | 3 | Papillon | yes |  | not completed |  |  | 0 | 3 | 0 | 0 | 3
BF-625 | [SCO] Print only UK national lottery tickets, if the customer opted out of receiving paper receipts | Story | 3 | In Development | 2 | Papillon | yes | pulled up on sprint change day | not completed |  |  | 0 | 2 | 0 | 0 | 2
BF-1094 | [ADAPTER][SCO] Update receipt repository API in MCO and SCO combined service | Story | 3 | Closed | 5 | Papillon | yes |  | completed |  |  | 0 | 5 | 5 | 0 | 0
BF-1261 | [SCO] Customer ID is not shown immediately on the virtual receipt after successful scan with scanner | Bug | 2 | Closed | 0.5 | Papillon | yes |  | completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_1_4 (hidden)
Sprint 2025_1-3, 19.02.2025 - 04.03.2025, Status at Sprint Completion
|  | Team Summary |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 16 | 8 | 58 | 6 | 27 | 37 | 0 | 64 | 46.55% | 58 | 6 | 27 | 0 | 37 | 46.55%
|  | Payment | 12 | 6 | 26 | 11 | 13 | 16 | 8 | 37 | 50% | 16 | 11 | 14 | 8 | 5 | 87.5%
|  | Sales | 10 | 10 | 52 | 4 | 56 | 0 | 0 | 56 | 107.7% | 52 | 4 | 56 | 0 | 0 | 107.7%
|  | Vlinder | 13 | 9 | 36 | 21 | 38 | 19 | 0 | 57 | 105.6% | 26 | 21 | 33 | 0 | 14 | 126.9%
|  | TTT | 12 | 9 | 36 | 6 | 33 | 9 | 0 | 42 | 91.67% | 36 | 6 | 38 | 0 | 4 | 105.6%
|  | TNT | 12 | 9 | 35 | 4 | 23 | 16 | 0 | 39 | 65.71% | 29 | 4 | 27 | 0 | 6 | 93.1%
|  | TFS | 12 | 10 | 34 | 8 | 34 | 8 | 0 | 42 | 100% | 30 | 8 | 33 | 0 | 5 | 110%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 10 | 7 | 32 | 8 | 29 | 11 | 0 | 40 | 90.62% | 27 | 8 | 26 | 0 | 9 | 96.3%
|  | Papillon | 23 | 18 | 38 | 27.5 | 44.5 | 16 | 1 | 65.5 | 117.1% | 38 | 27.5 | 44.5 | 5 | 16 | 117.1%
|  | Total | 87 | 61 | 277 | 60 | 224 | 105 | 8 | 337 | 80.87% | 247 | 60 | 228 | 8 | 71 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 83 | 347 | 37 | 95.5 | 120 | 442.5 | 120 | 442.5 | 0 | 0 | 120 | 442.5
|  | Completed | 58 | 240 | 28 | 57.5 | 86 | 297.5 | 86 | 297.5 | 0 | 0 | 86 | 297.5
|  | Not Completed | 24 | 104 | 7 | 28 | 31 | 132 | 31 | 132 | 0 | 0 | 31 | 132
|  | Removed | 1 | 3 | 2 | 10 | 3 | 13 | 3 | 13 | 0 | 0 | 3 | 13
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-25046 | Use till-compound-service image instead of cep-adapter-service image for deployment to POS PC | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25118 | Create RPM package to deploy and start the Butterfly Adapter as a service on MCO tills | Story | 3 | Closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25607 * | [QA][Tr-Stores-IIT-Legacy testroom] TILL does not always update to NP 4.7.3.1 from lower versions during Ivanti update path tests for Releases 4.1C2/1.26D | Bug | 1 | Open | 3 | Engineering | yes | reopened by Aldi | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
BF-793 | Update P400 UK EFT terminal firmware | Task | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-5833 | Push RPM releases to ALDI gitlab | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6090 | Videos on the SCO no longer work with the current CHO release | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6164 * | POS01 frozen and does not react any more (during installation) | Bug | 2 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24318 | EFT: Double debiting of card payments | Bug | 2 | In Development | 8 | Engineering |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-25045 | Add butterfly-adapter/combined RPM to release | Story | 3 | Blocked | 2 | Engineering |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
BF-792 | Implement support for ValueAddedServices for P400 EFTs | Story | 3 | In Development | 8 | Engineering |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
CHO-5837 | Provide device information for CCV Pad Next to CMDB | Story | 3 | In Development | 8 | Engineering |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
CHO-5886 | [3PD] Analyze hardware information for VGA displays | Story | 3 | Ready | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6063 | [US] Update process from SCO version 3.18.4 to SCO 4.14.0 does not work | Bug | 3 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-6133 | Release Sprint 2025_PI1-4 Artifacts | Story | 3 | In Development | 2 | Engineering |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-6145 | TLRD Tasks | Task | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18264 | Refactor CheckMK storedata script | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-331 | [SCO] Add Butterfly information to transaction data sent to the back office | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-336 | [SCO] Provide the option to overwrite an already scanned customer loyalty ID | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-577 | [ADAPTER] Switch to newest Yocuda API version for transmission of transaction data | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-624 | [SCO] Display Reminder Pop-Up When Aldi Pass Is Not Scanned | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-969 | [ADAPTER] Add the option to request return information based on the receipt_number | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-995 | [SCO] Voided Deposit refund are showing on the PDF and Receipt | Bug | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-1009 | [ADAPTER] Mapping of store_reference not always working | Bug | 3 | Closed | 1 | Papillon |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
BF-1010 | [SCO] Fix documentation with regard to changed receipt printing behaviour for void positions in UK | Story | 3 | Closed | 1 | Papillon |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
BF-1032 | [ADAPTER] Migrate Adapter to use dedicated DB schema and allow usage of single EntityManager in combined context | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-1033 | Onboarding Helmut | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-1047 | [ADAPTER] Store name is not mapped to Yocuda | Bug | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-1062 * | Test Task Release | Task | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-1072 * | [ADAPTER] Remove region name from receipt PDF name | Story | 3 | Closed | 1 | Papillon | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
BF-1073 * | [SCO] Remove region name from receipt data sent to the Butterfly | Story | 3 | Closed | 1 | Papillon | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
BF-1074 * | [ADAPTER] Amend mapping of article identifiers in financial transactions | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1075 * | [SCO] Amend article identifiers sent to Butterfly adapter for financial transactions | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-1078 * | [ADAPTER] Get rid of the own gRPC deadline configuration and use the RP library | Story | 3 | Closed | 0.5 | Papillon | yes |  | Completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-1120 * | [SCO] Deployment and test support PI-1-4 | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-506 * | [ADAPTER] Add ability to send refund receipts to Yocuda | Story | 3 | In Development | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
BF-868 | [ADAPTER] Provide basic return information to checkout for preliminary refund functionality | Story | 3 | In Development | 5 | Papillon |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
BF-1021 * | [SCO] Amend customer card capturing workflow | Story | 3 | In Development | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-19352 * | Double instantiation bug | Bug | 3 | In Development | 5 | Papillon | yes |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
BF-1094 * | [ADAPTER][SCO] Update receipt repository API in MCO and SCO combined service | Story | 3 | Ready | 5 | Papillon | yes |  | Removed |  |  | 0 | 5 | 0 | 5 | 0
ANP-23202 | Payment of transactions by other voucher (CODE + 30, option 5) related to deposit articles | Bug | 2 | in development | 3 | Payment |  | M | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-24330 | POS3 - CHOP - NCR 7199 PinPrinting not correct | Bug | 3 | blocked | 3 | Payment |  | M | Removed | 3 |  | 3 | 0 | 0 | 3 | 0
ANP-25604 | MI ¦ CHOP Scale - store was unable to trade on 2/3 tills due to error message: Waage inaktiv | Bug | 2 | blocked | 5 | Payment | yes | M | Removed |  |  | 0 | 5 | 0 | 5 | 0
ANP-21583 | Refactor Multilane State | Story | 3 | in development | 8 | Payment |  | D | Not Completed | 2 | 2 | 2 | 0 | 0 | 0 | 2
ANP-23610 | [Integrity Tests] SVS & etc/Medion for Sale of Internal and External EGC | Story | 3 | closed | 5 | Payment |  | R&T | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-25381 | Implement Remedy Feature for ANP-25351 | Story | 2 | in development | 3 | Payment |  | D | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
ANP-24918 | Add Cancel Tag to Transaction Data | Story | 3 | in development | 2 | Payment |  | D | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
ANP-25588 | Analyse Prio 3 Bug ANP-25541 | Story | 2 | closed | 2 | Payment | yes | M | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25485 | Analyse Prio 3 Bug ANP-23958 | Story | 3 | closed | 2 | Payment | yes | M | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25410 | provide support for CHOP UAT in austria (off-site) | Task | 3 | closed | 2 | Payment |  | R&T; retroactively estimated | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25590 | investigate on historical double entries, see ANP-25036 | Task | 3 | closed | 1 | Payment | yes | M; retroactively estimated | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25719 | Standards & Trainings | Story | 3 | closed | 1 | Payment | yes | M; completed by definition at end of sprint | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25713 | Hold first Dev onboarding workshop | Task | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25451 | POS 3 Preallocated receipt by SM prevents ACO update | Bug | 2 | In Development | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25434 | Remove obsolete US offline login logic | Story | 3 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25399 | Empty ACO Masterdata updates cause unnecessary processing at the till | Story | 2 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25360 | Providing till lock fallback during balancing impediments | Story | 3 | In Acceptance | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25154 | Till Boot time takes almost one hour | Bug | 3 | Closed | 1 | Sales |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24909 | Tills are in Bootloop when encryption is activated | Bug | 2 | Closed | 20 | Sales |  |  | Completed |  |  | 20 | 0 | 20 | 0 | 0
ANP-24508 | Adaptation of till locking process | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24507 | Disable Pick-up functionality (94+CODE) for US | Story | 3 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-20481 | Adaption of the compacting-mechanism | Story | 2 | Closed | 8 | Sales |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-24687 | Adjust tax rate to 6 decimal places: testing | Story | 2 | Closed | 8 | Synergy |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-25633 | Update current worklow: postlogout | Story | 3 | Closed | 3 | Synergy | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25714 | Sonar Challenge. Fixing all issues in NEWPOSSMessageProcessorMock. | Bug | 3 | Closed | 1 | Synergy | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-24060 | CPD Tax Fields srip.TotalInputTax and srip.EffectiveTaxAmount do not match for MCO | Bug | 3 | Blocked | 3 | Synergy |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-24770 | Collect all Logfiles: Development | Story | 3 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24781 | Collect all Logfiles: Testing | Story | 3 | In progress | 3 | Synergy |  |  | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
ANP-25137 | [SPIKE] HU DRS: requirements and current implementation analysis | Story | 3 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25375 | Build MCO part of NEWPOSS release 4.7.4 | Story | 3 | Closed | 2 | Synergy | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25403 | (HU) Wastage log - items are not visible on wastage receipt,’Unexpected error’ message on till | Bug | 3 | Blocked | 5 | Synergy |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-25578 | Sonar Challenge PI1-4 | Story | 3 | Closed | 2 | Synergy | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18702 | Enable payment restrictions and cleanup permitted means of payment after purchase spring migration | Story | 5 | closed | 5 | TFS |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-15480 | (US-only) Credit payment is printed as "Debit card" in the payment line of printed receipt (all versions) | Bug | 3 | blocked | 3 | TFS |  | waiting for Aldi | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-19179 | Customers overcharged on SCO - Not Fixed | Bug | 2 | closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18906 | [UK] AldiVoucher doesnt work after spring migration | Bug | 3 | closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19093 | Unclear Customer Intervention for empty ePay Gift Cards | Bug | 3 | closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19095 | Errors in sale export validation because of addition of [objectType] to objects | Bug | 3 | in development | 5 | TFS |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
NPSCO-19138 | [ITA] Disable Split/ Partial Payment for Card Payments in ITA | Bug | 3 | closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19209 | Test Task EGC | Task | 3 | closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19210 | Test Task for 4.16.0 | Task | 3 | closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19192 | Onboarding Paulo Moura Guedes | Task | 3 | closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19385 | Cherry Pick Maintenance Release 3.18.5 | Story | 3 | closed | 5 | TFS | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-19413 | Test Task 3.18.5 | Task | 3 | in development | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19200 | SCO - Legal Requirement- SCO virtual receipt is showing 3 decimal places instead of just 2 for weighted items | Bug | 2 | IN DEVELOPMENT | 3 | TNT |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-17561 | [3] Specifiy application events | Story | 3 | CLOSED | 5 | TNT |  |  | Completed | 4 |  | 4 | 0 | 4 | 0 | 0
NPSCO-17577 | [5] Publish application events to MQTT | Story | 3 | IN DEVELOPMENT | 5 | TNT |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
NPSCO-17562 | [6] Consume events from MQTT, store and forward them | Story | 3 | IN DEVELOPMENT | 8 | TNT |  |  | Not Completed |  | 3 | 8 | 0 | 5 | 0 | 3
NPSCO-18298 | Export deposits as depositData instead of linkedPositions in sales receipts | Story | 3 | CLOSED | 5 | TNT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-18299 | Some totals fields have to be exported in sales receipts | Story | 3 | IN DEVELOPMENT | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18310 | Export cashier and attendant information correctly | Story | 3 | IN DEVELOPMENT | 3 | TNT |  |  | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
NPSCO-19207 | Test Sprint Release 416 | Task | 3 | CLOSED | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17524 | Align logging patterns of logback for all services | Story | 3 | CLOSED | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19205 | Build Sprint Release 416 | Task | 3 | CLOSED | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-19410 | Cherry Pick Story for 3.18.5 | Story | 3 | IN DEVELOPMENT | 1 | TNT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19360 | Build SCO fix 3.18.5 | Task | 3 | OPEN | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-19388 | Cherry pick for Maintenance Release 3.18.5 | Task | 3 | Closed | 1 | TTT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19177 | Federal regulation US- SCO printed receipt needs to have the correct unit of measure (G) for tare weight values | Bug | 2 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19083 | SCO Reboots | Bug | 2 | Closed | 5 | TTT | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-19157 | [EGC] typedValue exception | Bug | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17387 | The Article Lookup (when Item not found) fails during the Gift Card Check | Bug | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19170 | [Spike] Integrate CHO`s MQTT service | Task | 3 | In Progress | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19103 | Exit gate barcode | Story | 3 | In Test | 3 | TTT |  |  | Not Completed |  | 0 | 3 | 0 | 3 | 0 | 0
NPSCO-18884 | Creating technical concept of workflows for EGC and PIN printing | Story | 3 | In Development | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18885 | Adapt master data lookup for PIN Printing articles in FTH | Story | 3 | In Development | 3 | TTT |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
NPSCO-18693 | Generate useful and correct graphs from the PS-analyzer results | Story | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-19076 | Test data from provider | Story | 3 | In Development | 3 | TTT |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
NPSCO-19171 | Release Test 416 [M] | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24951 | BF-233 Aggregation Pt.1 | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-25582 * | BF-1079 Build MSI | Story | 3 | Closed | 2 | Vlinder | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25671 * | Standards & Trainings | Story | 3 | Closed | 1 | Vlinder | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-24906 | BF-774 EFT terminal lines | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed | 5 | 5 | 5 | 0 | 0 | 0 | 5
ANP-24907 * | BF-775 double item lines | Story | 3 | In Development | 5 | Vlinder | yes |  | Not Completed |  | 3 | 0 | 5 | 2 | 0 | 3
ANP-25191 | BF-832 Aggregation Pt.2 | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25225 | BF-849 CFRM | Story | 3 | Closed | 8 | Vlinder |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-25474 | BF-134 Return Info Mapping | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25476 | BF-1060 Check receipt export | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25594 * | BF-1043 [MCO] Customer ID - Changes on Notification on VGA display about status of identification | Story | 3 | Closed | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25605 * | BF-73 [MCO] Customer ID - Identify customer ID via EFT device with NFC during ringing - 2-tap-solution | Story | 3 | In Development | 8 | Vlinder | yes |  | Not Completed |  | 5 | 0 | 8 | 3 | 0 | 5
ANP-25702 * | BF-1130 Support Tests | Story | 3 | Closed | 1 | Vlinder | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25724 * | Fix Data Processing Blinker | Story | 3 | In Development | 1 | Vlinder | yes |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_1_3 (hidden)
Sprint 2025_1-3, 19.02.2025 - 04.03.2025, Status at Sprint Completion
|  | Team Summary |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 28 | 20 | 74 | 10 | 54 | 24 | 6 | 84 | 72.97% | 74 | 10 | 54 | 6 | 24 | 72.97%
|  | Payment | 13 | 7 | 34 | 3 | 16 | 21 | 0 | 37 | 47.06% | 21 | 3 | 13 | 0 | 11 | 61.9%
|  | Sales | 15 | 11 | 37 | 18 | 34 | 21 | 0 | 55 | 91.89% | 37 | 18 | 34 | 0 | 21 | 91.89%
|  | Vlinder | 9 | 6 | 44 | 0 | 26 | 18 | 0 | 44 | 59.09% | 41 | 0 | 33 | 0 | 8 | 80.49%
|  | TTT | 15 | 11 | 41 | 0 | 29 | 12 | 0 | 41 | 70.73% | 41 | 0 | 29 | 0 | 12 | 70.73%
|  | TNT | 15 | 10 | 36 | 13 | 27 | 22 | 0 | 49 | 75% | 36 | 13 | 34 | 0 | 15 | 94.44%
|  | TFS | 11 | 9 | 25 | 8 | 25 | 8 | 0 | 33 | 100% | 23 | 8 | 27 | 0 | 4 | 117.4%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 6 | 4 | 19 | 8 | 16 | 11 | 0 | 27 | 84.21% | 19 | 8 | 21 | 0 | 6 | 110.5%
|  | Papillon | 28 | 22 | 35 | 52 | 61 | 18 | 1 | 87 | 174.3% | 35 | 52 | 61 | 8 | 18 | 174.3%
|  | Total | 106 | 74 | 291 | 52 | 211 | 126 | 6 | 343 | 72.51% | 273 | 52 | 224 | 6 | 95 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 100 | 347 | 40 | 114 | 140 | 461 | 138 | 457 | 2 | 4 | 140 | 461
|  | Completed | 73 | 225 | 27 | 65 | 100 | 290 | 99 | 288 | 1 | 2 | 100 | 290
|  | Not Completed | 25 | 116 | 12 | 41 | 37 | 157 | 36 | 155 | 1 | 2 | 37 | 157
|  | Removed | 2 | 6 | 1 | 8 | 3 | 14 | 3 | 14 | 0 | 0 | 3 | 14
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-23202 | Payment of transactions by other voucher (CODE + 30, option 5) related to deposit articles | Bug | 2 | in development | 3 | Payment |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
ANP-25036 | All POS - Wrong Currency: Euro instead of Franken | Bug | 2 | closed | 3 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-24330 | POS3 - CHOP - NCR 7199 PinPrinting not correct | Bug | 3 | in development | 3 | Payment |  |  | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
ANP-23037 | Terminal Assignment Wizard - IP Address-based - Pre-fill Prompt from Till_State | Story | 3 | closed | 3 | Payment |  | spilled over with virtually zero | Completed | 0 |  | 0 | 0 | 0 | 0 | 0
ANP-25142 | Post-release Tasks for NEWPOSS release 4.7.2 | Story | 3 | closed | 2 | Payment |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-21583 | Refactor Multilane State | Story | 3 | in development | 8 | Payment |  |  | Not Completed | 1 | 2 | 1 | 0 | -1 | 0 | 2
ANP-23610 | [Integrity Tests] SVS & etc/Medion for Sale of Internal and External EGC | Story | 3 | in development | 5 | Payment |  |  | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
ANP-24850 | simulated till freezes at paying 'Failed to send cashdrawer event to listener NulPointerException | Bug | 3 | closed | 5 | Payment |  | status at team review | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25171 | support for conceptual clarifications | Task | 3 | in progress | 1 | Payment |  | estimated retroactively, closed at end of sprint by definition | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25209 | take a look at SEND_FAILED topic | Task | 3 | closed | 1 | Payment |  | estimated retroactively | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25364 | Pick Stories for Version 4.7.3 | Story | 3 | closed | 1 | Payment | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25465 | Analyse Prio 1 Bug ANP-25423 | Story | 1 | Ready | 2 | Payment | yes |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
ANP-25410 | provide support for CHOP UAT in austria (off-site) | Task | 3 | Ready | - | Payment | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-17524 | Align logging patterns of logback for all services | Story | 3 | In Development | 1 | TNT |  |  | Not Completed |  | 1 | 1 | 0 | 0 | 0 | 1
NPSCO-18576 | [2][Spike] (Celonis) Create Celonis test and demo system | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18220 | Implement CFRM Script for the Bizerba C2 POS scale | Task | 3 | CLOSED | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18573 | Build Maintenance Release 3.18.4 | Task | 3 | CLOSED | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18574 | Test Maintenance Release 3.18.4 | Task | 3 | Closed | 1 | TNT |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-18907 | Build Sprint Release 415 | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18892 | [FI CH] Customer Intervention to be adapted based on Language selected (develop) | Story | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17561 | [3] Specifiy application events | Story | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-19205 | Build Sprint Release 416 | Task | 3 | CLOSED | 1 | TNT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-19200 | SCO - Legal Requirement- SCO virtual receipt is showing 3 decimal places instead of just 2 for weighted items | Bug | 1 | in development | 3 | TNT | yes |  | Not Completed |  | 2 | 0 | 3 | 1 | 0 | 2
NPSCO-18689 | [4] Create the monitored item adapter API | Story | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17577 | [5] Publish application events to MQTT | Story | 3 | Ready | 5 | TNT | yes |  | Not Completed |  | 4 | 0 | 5 | 1 | 0 | 4
NPSCO-16394 | Integrate Purchase Service into single JVM deployment | Story | 3 | In Development | 8 | TNT |  |  | Not Completed |  | 7 | 8 | 0 | 1 | 0 | 7
NPSCO-18298 | Export deposits as depositData instead of linkedPositions in sales receipts | Story | 3 | In Development | 5 | TNT |  |  | Not Completed |  | 1 | 5 | 0 | 4 | 0 | 1
NPSCO-19091 | Test Release 4.15 | Task | 3 | Closed | 1 | TNT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-15442 | Receipt Archive is empty after a very short time | Bug | 2 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18454 | SCO - No coupon notices or collection notices on SCO or ATS when coupon is scanned before items. | Bug | 3 | In Test | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18888 | Translations for every country (Till report) | Story | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18690 | Additional condition for BO resync | Story | 3 | In Development | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18641 | Pin Printing can be deactivated via Parameter | Story | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18642 | add support for ringing PIN printing items | Story | 3 | In Development | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18884 | Creating technical concept of workflows for EGC and PIN printing | Story | 3 | In Development | 5 | TTT |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-18887 | [Spike] Analyze use of MCO libraries (Medion/ETC) | Task | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18693 | Generate useful and correct graphs from the PS-analyzer results | Story | 3 | In Development | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-18379 | Change sales limit for EGCs in US | Task | 3 | In Progress | 1 | TTT |  |  | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
NPSCO-17387 | The Article Lookup (when Item not found) fails during the Gift Card Check | Bug | 3 | In Development | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17537 | Invalid EGC header-text in Ringing Mode | Bug | 3 | In Test | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18890 | Handover EGC Payment | Task | 3 | In Progress | 1 | TTT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18925 | Release Test 415 [M] | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18926 | Release Test 415 [K] | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15739 | [SCO Pentest] l4: Web Server Version Exposed | Story | 3 | Closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-16457 | [ITA] Adjust receipt layout for EGC payment | Bug | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16584 | Receipt cannot be printed in Payment with EGC | Bug | 3 | Closed | 3 | TFS |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-17588 | Disable gRPC reflection for purchase | Story | 3 | Closed | 2 | TFS |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18911 | Test Task for 3.18.4 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15480 | (US-only) Credit payment is printed as "Debit card" in the payment line of printed receipt (all versions) | Bug | 3 | In Development | 3 | TFS | yes |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
NPSCO-16261 | Handle partial/split EGC payments in the transaction after shutdown | Story | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16390 | Voiding of an EGC and Payment with another EGC results in no Taxes being paid | Bug | 3 | Closed | 2 | TFS | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18235 | 477-005 had a double charge on 12/01 with no terminal error showing on the receipt. | Bug | 2 | Closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18702 | Enable payment restrictions and cleanup permitted means of payment after purchase spring migration | Story | 3 | In Development | 5 | TFS |  |  | Not Completed | 5 | 1 | 5 | 0 | 4 | 0 | 1
NPSCO-19146 | Test Task EGC | Task | 3 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-23977 | BF-467 Prevent scan URID | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-24564 | BF-178 Weight articles | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24905 | BF-736 Merge ANP-23975 | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24952 | BF-797 Assessment discount bug | Bug | 3 | Closed | 3 | Vlinder |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-25185 | BF-844 Scan before ringing | Story | 3 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24476 | BF-534 re-scanning | Story | 3 | In Development | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24906 | BF-774 EFT terminal lines | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed |  | 5 | 5 | 0 | 0 | 0 | 5
ANP-24951 | BF-233 Aggregation Pt.1 | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-25225 | BF-849 CFRM | Story | 3 | In Development | 8 | Vlinder |  |  | Not Completed |  | 1 | 8 | 0 | 7 | 0 | 1
BF-549 | [ADAPTER][SCO] Bind Butterfly functionalities to CFRM parameter | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-770 | [SCO] Do not forward voided positions to Butterfly adapter | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-773 | [ADAPTER] Persist only receipts in the Butterfly adapter for that a use case exists in subsequent systems | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-809 | Onboarding of new colleague (Fatema) | Story | 3 | Closed | - | Papillon |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
BF-838 * | [SCO] Implement outbox pattern for messages to the butterfly Adapter | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-853 | [ADAPTER] Create combined service for MCO | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-866 | [ADAPTER] Support sub-commodity group number information for articles in receipts sent to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-867 | [SCO] Support sub-commodity group information for articles in receipts sent to the Butterfly adapter | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-878 * | [SCO] Send core receipt information to Butterfly adapter | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-881 | [ADAPTER] Send effective price and value of articles and financial transactions via butterfly adapter to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-882 | [SCO] Send effective price and value of articles and financial transactions to Butterfly adapter | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-883 * | [SCO] Amend store name mapping for receipt data sent to the Butterfly | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-884 * | [ADAPTER] Amend receipt PDF name generation | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-889 * | [ADAPTER] The product_code extension property must have a type | Bug | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-895 | [ADAPTER] EGC item is lost in the request to Yocuda | Bug | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-896 | [SCO] No PDF is generated if receipt contains one EGC and one voided EGC | Bug | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-898 | [ADAPTER] Analyze and clarify use of type information in properties | Story | 3 | Closed | 1 | Papillon |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
BF-899 | [SCO] It's not possible to add retrieved customer information to the receipt | Bug | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-921 * | [ADAPTER] Update protobuf object mapping tests and remove use of Instancio framework | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-926 * | [SCO] Long loading times when scanning a customer ID after short break | Bug | 2 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-931 * | [SCO] Transmit commodity group and sub commodity group as number | Bug | 3 | Closed | 1 | Papillon | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
BF-953 * | [ADAPTER] Don't retry processing unknown/unprocessable messages indefinitely | Story | 3 | Closed | 5 | Papillon | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
BF-331 * | [SCO] Add Butterfly information to transaction data sent to the back office | Story | 3 | In Development | 5 | Papillon | yes |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
BF-577 * | [ADAPTER] Switch to newest Yocuda API version for transmission of transaction data | Story | 3 | In Development | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
BF-868 * | [ADAPTER] Provide basic return information to checkout for preliminary refund functionality | Story | 3 | In Development | 5 | Papillon | yes |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
BF-969 * | [ADAPTER] Add the option to request return information based on the receipt_number | Story | 3 | In Development | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
BF-995 * | [SCO] Voided Deposit refund are showing on the PDF and Receipt | Bug | 3 | In Development | 2 | Papillon | yes |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
BF-935 * | [SCO] Update assco-rp-purchase-service to use at least version 3.4 of rp-purchase | Story | 3 | Blocked | 8 | Papillon | yes |  | Removed |  |  | 0 | 8 | 0 | 8 | 0
ANP-25372 | [Spike]Scan for occurences of Masterdata update thread waiting | Story | 3 | Closed | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25358 | Build MCO part of NEWPOSS release 3.18.9 | Story | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25341 | Fix SonarQube findings after merge of ANP-24589 | Task | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25184 | [SPIKE] Evaluate Wrong Price Report from 032-040 Friesenheim market | Story | 3 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25145 | [Analysis] Analyse current PIN Printing implementation to support functionality migration to EGC - Part 2 | Story | 3 | Closed | 8 | Sales |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-25139 | [SPIKE] Analyse activation of till sharing (20+CODE) for US | Story | 3 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25130 | [SPIKE] Evaluate Wrong Price Report from 023-034 Neuenbürg market | Story | 3 | In Development | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25049 | Build MCO part of NEWPOSS release 4.7.3 | Story | 3 | Closed | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-25037 | Enable till sharing functionality (20+CODE) for US | Story | 3 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24940 | [QA] PIN Printing item is no longer sellable on till after update 1.25D1 -> 1.26B | Bug | 1 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24909 | Tills are in Bootloop when encryption is activated | Bug | 2 | Closed | 8 | Sales |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-24892 | Product Block did not work on 25th of Januar for 826704 & 810998 in multiple stores | Bug | 3 | In Development | 3 | Sales |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-24507 | Disable Pick-up functionality (94+CODE) for US | Story | 3 | In Development | 5 | Sales | yes |  | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
ANP-22964 | In TCS-3922 at Step 16's Step 14, the CSH file values are not increased by, but they are exactly the amount of the expected increase. | Bug | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-20481 | Adaption of the compacting-mechanism | Story | 3 | In Development | 5 | Sales |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-25278 | [Legal] AU: MCO POS are not displaying NMI verification details when doing a 98 code (after Rocky Linux migration) | Bug | 2 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-3928 | Regularly execute VACUUM to free up disk space | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5173 | TLS Client authentication fails with CSR script | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5574 | [3PD] Analyze hardware information for integrated NCR scales | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5836 | Provide device information for TIM API EFT devices to CMDB | Story | 3 | Closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-5838 | [3PD] Analyze hardware information for Quest EFTs | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5887 | [3PD] Analyze hardware information for Epson TM-T88 printers | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5894 | Update GEBIT_CHO_TOKEN for gitlab | Task | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5922 | [3PD] Analyze hardware information for 2x20 displays | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5952 | Bizerba-C2 configuration directories have the wrong owner and group after installation from scratch | Bug | 1 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5964 | Implement volumes as persistent storage for mosquitto and postgres container | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6010 | Investigate installation issues in US | Task | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-6015 | Set up NFC test passes on iOS and Google test devices | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6029 * | CHO system configuration playbook not run after update | Bug | 1 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25045 | Add butterfly-adapter/combined RPM to release | Story | 3 | Blocked | 2 | Engineering |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
ANP-25118 | Create RPM package to deploy and start the Butterfly Adapter as a service on MCO tills | Story | 3 | In Development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
BF-792 | Implement support for ValueAddedServices for P400 EFTs | Story | 3 | In Development | 8 | Engineering |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
BF-793 | Update P400 UK EFT terminal firmware | Task | 3 | Blocked | 1 | Engineering |  |  | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
CHO-4293 * | Evaluate supply of SCO-DN hardware device information | Story | 3 | In Development | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-5833 | Push RPM releases to ALDI gitlab | Story | 3 | In Development | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5837 | Provide device information for CCV Pad Next to CMDB | Story | 3 | In Development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-6002 | Release Sprint 2025_PI1-3 Artifacts | Story | 3 | Blocked | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-6014 | TLRD Tasks | Task | 3 | In Progress | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-6017 * | Mirroring repositories fails | Bug | 3 | In Acceptance | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
CHO-6031 * | Satisfy requirements for combined-services adapter on mco | Story | 3 | In Development | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-6045 * | Multilane virtual keyboard test setup | Task | 3 | In Progress | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-5647 | [3PD] Create concept to simplify dependencies between CHO MSIs | Story | 3 | Ready | 3 | Engineering |  |  | Removed |  |  | 3 | 0 | 0 | 3 | 0
CHO-5886 | [3PD] Analyze hardware information for VGA displays | Story | 3 | Ready | 3 | Engineering |  |  | Removed |  |  | 3 | 0 | 0 | 3 | 0
ANP-15539 | Extract receipt logic from RetrieveReceiptController | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24360 | Replace SNMP monitoring with the Till heartbeat for Backoffice pending balancing scenarios | Story | 2 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25048 | SI signature certificate cannot be loaded as Base64 string | Bug | 2 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-25071 | [SPIKE] Till PC does not respond to user interaction | Story | 3 | Closed | 5 | Synergy | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-24060 | CPD Tax Fields srip.TotalInputTax and srip.EffectiveTaxAmount do not match for MCO | Bug | 3 | In Development | 3 | Synergy | yes | Incidents and Problems bug | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-24687 | Adjust tax rate to 6 decimal places: testing | Story | 2 | In Development | 8 | Synergy |  |  | Not Completed |  | 3 | 8 | 0 | 5 | 0 | 3
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_1_2 (hidden)
Sprint 2025_1-2, 05.02.2025 - 18.02.2025, Status at Sprint Completion
|  | Team Summary |  |  |  | v v v Use exactly these statuses v v v
|  |  | Issue Count |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS])
|  | Team | Sprint Scope | Completed | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned
| > > > > Use exactly these team names! > > > > | Engineering | 25 | 17 | 48 | 5 | 38 | 15 | 0 | 53 | 79.17% | 48 | 5 | 38 | 0 | 15 | 79.17%
|  | Payment | 22 | 15 | 28 | 19 | 30 | 12 | 5 | 47 | 107.1% | 13 | 19 | 21 | 5 | 6 | 161.5%
|  | Sales | 13 | 11 | 54 | 4 | 45 | 8 | 5 | 58 | 83.33% | 54 | 4 | 45 | 5 | 8 | 83.33%
|  | Vlinder | 14 | 11 | 38 | 5 | 35 | 8 | 0 | 43 | 92.11% | 26 | 5 | 26 | 0 | 5 | 100%
|  | TTT | 14 | 9 | 35 | 6 | 26 | 15 | 0 | 41 | 74.29% | 35 | 6 | 26 | 0 | 15 | 74.29%
|  | TNT | 17 | 16 | 45 | 5 | 47 | 3 | 0 | 50 | 104.4% | 45 | 5 | 49 | 0 | 1 | 108.9%
|  | TFS | 8 | 6 | 40 | 0 | 29 | 11 | 0 | 40 | 72.5% | 27 | 0 | 16 | 0 | 11 | 59.26%
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Synergy | 10 | 7 | 31 | 9 | 29 | 11 | 0 | 40 | 93.55% | 31 | 9 | 31 | 0 | 9 | 100%
|  | Papillon | 21 | 15 | 37 | 19.5 | 41.5 | 15 | 1 | 56.5 | 112.2% | 37 | 19.5 | 41.5 | 0 | 15 | 112.2%
|  | Total | 113 | 85 | 288 | 44 | 250 | 72 | 10 | 332 | 86.81% | 248 | 44 | 221 | 10 | 61 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 110 | 390 | 34 | 78.5 | 144 | 468.5 | 124 | 428.5 | 20 | 40 | 144 | 468.5
|  | Completed | 86 | 306 | 21 | 44.5 | 107 | 350.5 | 92 | 320.5 | 15 | 30 | 107 | 350.5
|  | Not Completed | 23 | 79 | 10 | 29 | 33 | 108 | 28 | 98 | 5 | 10 | 33 | 108
|  | Removed | 1 | 5 | 3 | 5 | 4 | 10 | 4 | 10 | 0 | 0 | 4 | 10
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-25060 | [CHOP] Receipts are being printed at wrong pinter during card payment | Bug | 2 | closed | 3 | Payment | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25035 | [CHOP] Printers do no reconnect to the till after being removed | Bug | 2 | closed | 3 | Payment | yes | not reproducible anymore | Removed |  |  | 0 | 3 | 0 | 3 | 0
ANP-23202 | Payment of transactions by other voucher (CODE + 30, option 5) related to deposit articles | Bug | 2 | in development | 3 | Payment |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
ANP-24943 | create "nightly build" V3 for austrian and swiss multilane testing | Task | 2 | closed | - | Payment |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-25003 | record video | Task | 3 | closed | - | Payment | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24949 | Pick ANP-24583 to Release 4.7.2 | Story | 3 | closed | 1 | Payment |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24977 | Pick ANP-23694 to Release 4.7.2 | Story | 3 | closed | 1 | Payment |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-25067 | Pick ANP-23037 to Release 4.7.2 | Story | 3 | closed | 1 | Payment | yes |  | Removed |  |  | 0 | 1 | 0 | 1 | 0
ANP-25075 | Pick ANP-25060 to Release 4.7.2 | Story | 3 | closed | 1 | Payment | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25091 | Pick ANP-25035 to Release 4.7.2 | Story | 3 | closed | 1 | Payment | yes |  | Removed |  |  | 0 | 1 | 0 | 1 | 0
ANP-24950 | Build MCO part of NEWPOSS release 4.7.2 | Story | 3 | closed | 2 | Payment |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-18160 | CFRM Configuration Guide | Story | 3 | closed | 3 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-19414 | Create Integrity Tests and Manual Tests - AT BASICS | Story | 3 | closed | 5 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-19941 | Create Integrity Tests and Manual Tests - CH BASICS | Story | 3 | closed | 5 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-23694 | Create Integrity Tests and Manual Tests - AT TAW | Story | 3 | closed | 5 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-23037 | Terminal Assignment Wizard - IP Address-based - Pre-fill Prompt from Till_State | Story | 3 | in development | 3 | Payment |  | spilled over with virtually zero | Not Completed | 2 | 0 | 2 | 0 | 2 | 0 | 0
ANP-25043 | IP assignment with no address for lane 1 leads to exception error on CHOP till | Bug | 3 | closed | 3 | Payment | yes | bug fixed and merged | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-25036 | All POS - Wrong Currency: Euro instead of Franken | Bug | 2 | in review | 3 | Payment | yes |  | Not Completed |  | 1 | 0 | 3 | 2 | 0 | 1
ANP-24330 | POS3 - CHOP - NCR 7199 PinPrinting not correct | Bug | 3 | in development | 3 | Payment | yes |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-24485 | find out whether there was a change in printing the second sale receipt in case of EFT/EGC after total | Task | 3 | closed | - | Payment |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-25105 | Pick NO-ISSUE: Fix time setup in JUnit test PluReportServiceImplTest | Story | 3 | closed | 1 | Payment | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-25108 | support for conceptual clarifications | Task | 3 | closed | - | Payment | yes | closed by definition at sprint end | Completed |  |  | 0 | 0 | - | 0 | 0
NPSCO-15442 | Receipt Archive is empty after a very short time | Bug | 2 | In Development | 3 | TTT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-18699 | Forward FinancialTransactionType to Provider for all calls | Task | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18690 | Additional condition for BO resync | Story | 3 | In Development | 2 | TTT |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
NPSCO-18640 | Master data for PinPrinting article | Story | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18641 | Pin Printing can be deactivated via Parameter | Story | 3 | In Development | 2 | TTT |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
NPSCO-16515 | [TEST] finalise test cases and test for EGC error handling | Task | 3 | In Progress | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18642 | add support for ringing PIN printing items | Story | 3 | In Development | 5 | TTT |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-18692 | Check the performance values | Story | 3 | In Development | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18712 | [Analysis Spike] Scannable Price Reduction (SPR) [0.5PT] | Task | 3 | In Progress | 1 | TTT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18698 | Handover EGC Payment (on call) | Task | 3 | In Progress | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18703 | Release Test 414 [M] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18454 | SCO - No coupon notices or collection notices on SCO or ATS when coupon is scanned before items. | Bug | 3 | In Development | 3 | TTT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-18704 | Maintenance Release Test 3.18.4 [K] | Task | 3 | Open | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18706 | Maintenance Release Test 3.18.4 [M] | Task | 3 | Open | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18705 | Cherry Pick NPSCO-18035 for Mainentance 3.18.4 |  | 3 | Closed | 2 | TFS |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18627 | [Analysis] Stabilization of the EFT Payment Process: Measures to Prevent Double Charges at SCOs |  | 3 | Closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18707 | Test Task 4.14.0 |  | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16393 | Update Purchase Service after Spring Migration RP |  | 3 | Closed | 13 | TFS |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
NPSCO-18702 | Enable payment restrictions and cleanup permitted means of payment after purchase spring migration |  | 3 | In Development | 8 | TFS |  |  | Not Completed |  | 8 | 8 | 0 | 0 | 0 | 8
NPSCO-18039 | Handling of voided EGC payments |  | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15737 | [SCO Pentest] l2: Mosquitto: SCO Information Exposed |  | 3 | Closed | 3 | TFS |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
NPSCO-16584 | Receipt cannot be printed in Payment with EGC |  | 3 | In Development | 3 | TFS |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
[12 empty] | 0 | 0 | 0 | 0 | 0
NPSCO-17013 | [15] Merge Spring migration after all tests are done | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18018 | Create parent pom of assco-pos-app-adapter-local-component-tests | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18181 | EFT payments cant be processed | Bug | 2 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18626 | [FI CH] Customer Intervention to be adapted based on Language selected | Story | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18645 | [1][Spike] Create Monitored Item Adapter using CEP Adapter as blueprint | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18572 | Cherry Pick Story for CH 3.18.4 | Story | 3 | In Development | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18055 | [B] Simplify class hierarchy for component test boot strap | Task | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18534 | Release build 414 | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18297 | Export objectType in all receipts | Story | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17524 | Align logging patterns of logback for all services | Story | 3 | In Development | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18576 | [2][Spike] (Celonis) Create Celonis test and demo system | Task | 3 | In Progress | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18686 | Till unusable after closing printer lid after fixing printer issue in payment mode | Bug | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17709 | [SCO CH] Test VSS Bugfix Provide configured (CFRM) language for region to TPI Scan | Story | 3 | Closed | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18574 | Test Maintenance Release 3.18.4 | Task | 3 | In Progress | 3 | TNT |  |  | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
NPSCO-18573 | Build Maintenance Release 3.18.4 | Task | 3 | Open | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18790 | Test Release 4.14 | Task | 3 | Closed | 1 | TNT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-18830 | Integrate the new CHO Fix for Bizerba C2 | Task | 3 | Closed | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-23847 | Implementation for Add FiscalNullStartReceipt step during CSR process | Story | 2 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23979 | Testing for Add FiscalNullStartReceipt step during CSR process | Story | 2 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24769 | Collect all Logfiles: Discovery,Planning and Documentation | Story | 3 | Closed | 3 | Synergy | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24938 | Adjust tax rate to 6 decimal places: change business models | Story | 2 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-15539 | Extract receipt logic from RetrieveReceiptController | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-24360 | Replace SNMP monitoring with the Till heartbeat for Backoffice pending balancing scenarios | Story | 2 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24574 | Adjust tax rate to 6 decimal places: implementation | Story | 2 | In Development | 5 | Synergy |  |  | Not Completed |  | 3 | 5 | 0 | 2 | 0 | 3
ANP-24687 | Adjust tax rate to 6 decimal places: testing | Story | 2 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25047 | [QA] Simulated Till GUI does not show the Receipt Printer section on AHEAD ITALY stores | Bug | 2 | Blocked | 3 | Synergy | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-25127 | [Legal] AU: MCO POS are not displaying NMI verification details when doing a 98 code | Bug | 2 | In Development | 3 | Synergy | yes |  | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-25103 | Move spotless:check goal execution to jenkins profile | Story | 2 | Closed | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-25084 | [QA] HU; 1.26C; Tills don't automatically update again | Bug | 1 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-25070 | Support by the setup of Test system for Pin Printing | Task | 3 | Closed | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-24997 | POS - All tills are not able to trade | Bug | 1 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24934 | [Analysis] Analyse current PIN Printing implementation to support functionality migration to EGC - Part 1 | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24909 | Tills are in Bootloop when encryption is activated | Bug | 2 | In Development | 8 | Sales |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-24865 | Ensure triggering of full masterdata resync only after all data has been fully updated by SSR | Story | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24828 | All Tills - EM : Data sychronize .. when logging out | Bug | 2 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24589 | Add ActivityStackInspector to the MCO till simulator | Story | 3 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24529 | Create automated integration test coverage for multilane scanner status handling | Story | 3 | In Development | 13 | Sales |  | will most likely be finished | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-24176 | 774-081, 774-078: product block for 67602 released on the 5th December 17:17 but not applied on morning of 6th | Bug | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-11615 | Improve depiction of linked service articles on receipts | Story | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24854 | Update SonarCube connection in Developer IDEs | Story | 3 | Ready | 5 | Sales |  |  | Removed |  |  | 5 | 0 | 0 | 5 | 0
CHO-3157 | Provide Postgresql container on MCO tills | Story | 3 | Closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-4599 | Implement CheckMK checks that monitor additional devices on a multilane till | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-4767 | Signature check for dn-aldi-vss-rocky.repo in SCO scratch installations | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5177 | Move cho-base and its functionality to cho-ansible, cho-kickstart | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5662 | Testlab hardware completion for HWLM | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5876 | [3PD] Analyze hardware information for P400 EFTs via OPI | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5880 | [3PD] Analyze hardware information for Lane 5000 EFTs via OSPI | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5882 | [3PD] Analyze hardware information for Lane 5000 (IT) EFTs | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5885 | [3PD] Analyze hardware information for the Mettler Toledo Ariva-B D8 scale | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5888 | [3PD] Analyze hardware information for BBox + NCR 7197 | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5889 | [3PD] Analyze hardware information for the DN P1200 printer | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5951 * | Help Team Vlinder with the implementation of the Bizerba C2 Scale | Task | 3 | Closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-25118 | Create RPM package to deploy and start the Butterfly Adapter as a service on MCO tills | Story | 3 | In Development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
BF-793 | Update P400 UK EFT terminal firmware | Task | 3 | In Progress | - | Engineering |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
CHO-3928 | Regularly execute VACUUM to free up disk space | Story | 3 | Ready | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5173 * | TLS Client authentication fails with CSR script | Bug | 3 | In Review | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5582 | Automatically aggregate Changelog for CHO artifacts | Story | 3 | In Test | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5833 | Include RPM-releases in gitlab-mirroring | Story | 3 | Ready | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5836 | Provide device information for TIM API EFT devices to CMDB | Story | 3 | In Review | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5837 | Provide device information for CCV Pad Next to CMDB | Story | 3 | In Review | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5878 | [3PD] Analyze hardware information for Verifone M424 EFTs | Story | 3 | Blocked | - | Engineering |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
CHO-5894 | Update GEBIT_CHO_TOKEN for gitlab | Task | 3 | Open | - | Engineering |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
CHO-5900 | Release Sprint 2025_PI1-2 Artifacts | Story | 3 | Blocked | 2 | Engineering |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-5909 | TLRD Tasks | Task | 3 | In Progress | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5952 * | Bizerba-C2 configuration directories have the wrong owner and group after installation from scratch | Bug | 1 | Blocked | 2 | Engineering | yes |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
BF-699 | [SCO] Send receipt type and status information to Butterfly adapter | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-718 | [ADAPTER] Add specific type values for Butterfly related discounts | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-719 | [SCO] Provide identifier for Butterfly coupons and promotions | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-734 | [ADAPTER] Add till number to receipts sent to Yocuda | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-740 | [SCO] Send EGC articles to Butterfly adapter | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-741 | [SCO] Provide the option to remove anonymous coupons | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-772 | [ADAPTER] Receive and forward receipt type and status information to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-780 * | [ADAPTER] Document checkMK monitoring information provided by Butterfly adapter | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-788 | [SCO] Amend mapping of discount extension properties for sale receipts sent to the Butterfly adapter | Bug | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-789 | [ADAPTER][SPIKE] Analyze current Butterfly adapter implementation with regard to extension property handling and provide suggestions to improve its quality | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-798 * | [SCO] Remove artificial void positions from SCO receipt | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-839 * | [SCO] Provide generic_article_item_id extension as string | Bug | 3 | Closed | 0.5 | Papillon | yes |  | Completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-841 * | [ADAPTER][SCO] Create release for onsite test at ALDI (18.02.25) | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-842 * | [ADAPTER] store_reference includes till number | Bug | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-870 * | [SCO] It is not possible to scan customers with promotions | Bug | 3 | Closed | 1 | Papillon | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
BF-549 | [ADAPTER][SCO] Bind Butterfly functionalities to CFRM parameter | Story | 3 | In Development | 3 | Papillon |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
BF-770 | [SCO] Do not forward voided positions to Butterfly adapter | Story | 3 | In Development | 3 | Papillon |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
BF-773 * | [ADAPTER] Persist only receipts in the Butterfly adapter for that a use case exists in subsequent systems | Story | 3 | In Acceptance | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
BF-809 | Onboarding of new colleague (Fatema) | Story | 3 | Ready | - | Papillon |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
BF-866 * | [ADAPTER] Support sub-commodity group number information for articles in receipts sent to Yocuda | Story | 3 | In Development | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
BF-881 * | [ADAPTER] Send effective price and value of articles and financial transactions via butterfly adapter to Yocuda | Story | 3 | In Development | 3 | Papillon | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-21303 * | [MCO] NEWPOSS Implementation of Bizerba C2 POS Scale (CS300 successor model) | Story | 3 | Closed | 5 | Vlinder | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-23587 | BF-402 Im- and export | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-24045 | BF-573 Testing Part 1 | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-24191 | Merge Implementations for new Scales | Task | 3 | Closed | - | Vlinder |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24475 | BF-563 PDF purging | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24565 | BF-36 Auto-refund | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-24566 | Build MCO part of release 3.18.8 | Story | 3 | Closed | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24612 | Build MCO part of NEWPOSS release 4.7.1 | Story | 3 | Closed | 1 | Vlinder |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24700 | BF-739 Performance | Task | 3 | Closed | - | Vlinder |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24820 | BF Test Support | Task | 3 | Closed | - | Vlinder |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24910 | BF-64 show ID status | Story | 3 | Closed | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23977 | BF-467 Prevent scan URID | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed | 2 | 2 | 2 | 0 | 0 | 0 | 2
ANP-24111 | Release Builds for all Butterfly Libs | Task | 3 | Open | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24952 | BF-797 Assessment discount bug | Bug | 3 | In Development | 3 | Vlinder |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_1_1 (hidden)
Sprint 2025_1-1, 22.01.2025 - 04.02.2025, Status at Sprint Completion
|  | Team Summary |  |  |  | v v v Use exactly these statuses v v v
|  |  |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS]) | [5 empty] | Issue Count
|  | Team | Issue Count | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | Completed
| > > > > Use exactly these team names! > > > > | Engineering | 33 | 53 | 38 | 75 | 16 | 0 | 91 | 141.5% | 53 | 38 | 75 | 0 | 16 | 141.5% | 28
|  | Payment | 13 | 27 | 9 | 10 | 26 | 0 | 36 | 37.04% | 11 | 9 | 9 | 0 | 11 | 81.82% | 6
|  | Sales | 15 | 34 | 20 | 37 | 17 | 0 | 54 | 108.8% | 34 | 20 | 37 | 0 | 17 | 108.8% | 9
|  | Vlinder | 15 | 49 | 0 | 27 | 22 | 0 | 49 | 55.1% | 38 | 0 | 28 | 0 | 10 | 73.68% | 5
|  | TTT | 13 | 32 | 5 | 29 | 3 | 5 | 37 | 90.62% | 32 | 5 | 29 | 5 | 3 | 90.62% | 11
|  | TNT | 21 | 48 | 8 | 37 | 19 | 0 | 56 | 77.08% | 48 | 8 | 39 | 0 | 17 | 81.25% | 15
|  | TFS | 12 | 23 | 10 | 22 | 11 | 0 | 33 | 95.65% | 18 | 10 | 25 | 0 | 3 | 138.9% | 10
|  | 0-Noise | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Synergy | 9 | 37 | 4 | 17 | 13 | 11 | 41 | 45.95% | 32 | 4 | 24 | 6 | 6 | 75% | 5
|  | Papillon | 15 | 36 | 12 | 23 | 22 | 3 | 48 | 63.89% | 36 | 12 | 23 | 3 | 22 | 63.89% | 7
|  | Total | 122 | 266 | 90 | 237 | 114 | 5 | 356 | 89.1% | 234 | 90 | 242 | 5 | 77 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 103 | 357 | 43 | 118 | 146 | 475 | 131 | 445 | 15 | 30 | 146 | 475
|  | Completed | 68 | 224 | 28 | 69 | 96 | 293 | 88 | 277 | 8 | 16 | 96 | 293
|  | Not Completed | 32 | 117 | 14 | 46 | 46 | 163 | 39 | 149 | 7 | 14 | 46 | 163
|  | Removed | 3 | 16 | 1 | 3 | 4 | 19 | 4 | 19 | 0 | 0 | 4 | 19
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-24753 | Update mco-storedata collection time interval to once every minute | Story | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-5056 | Migrate bizerba cs300 software display for SCO | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5156 | Provide documentation for CMDB data retrieval | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5162 | Pipeline of Integration builds should not fail if the feature branch is a number which is not found in jira | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5163 | Organise the rights for our gitlab project correctly | Task | 3 | Closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5228 | Provide How-to articles for hardware monitoring | Story | 3 | Closed | 20 | Engineering |  |  | Completed |  |  | 20 | 0 | 20 | 0 | 0
CHO-5229 | Provide How-to articles for CMDB data provision | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5230 | [5PT] Hardware information for CS300 scale | Story | 3 | Closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5294 | [10PT] Serial ID for TIM-API EFT devices | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5295 | [10PT] Serial ID for CMDB for CCV Pad Next EFT device | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5325 | Provision of SLO certificates by ALDI | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5336 | Extend logging of old CSR process | Story | 3 | Closed | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
CHO-5458 | Update iPXE Boot Firmware to the latest version | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5506 | Hardware clock time is set incorrectly | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5507 | Improve debug-info shortcut. | Story | 3 | Closed | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
CHO-5523 | [SCO FI CH] TIM API EFT not working | Bug | 2 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5524 | Perform and document configuration of country settings on C2 scale | Task | 3 | Closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5526 | Create shortcut to trigger an installation from scratch | Story | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-5527 | Add cho local checks and collector script to CHO release | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5528 | Backport NHPI-reconfiguration to release 1.25E | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5576 | Document hardware information availability for CMDB | Story | 3 | Closed | 5 | Engineering | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
CHO-5578 | Document GSD performance summary shortcut | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5579 | Provide documentation for cho-local-checks in Confluence | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5601 | Unrecognized argument in cho-local-checks | Bug | 3 | Closed | 1 | Engineering | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
CHO-5634 | TIM API - Implement support for UNATTENDED flag for SCOs | Story | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5660 | Performance summary stops at CHO step | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-3157 | Provide Postgresql container for Butterfly adapter on MCO tills | Story | 3 | In Development | 8 | Engineering | yes |  | Not Completed |  |  | 0 | 8 | 0 | 0 | 8
CHO-5115 | Remove containers from cho-ansible (even if the build is aborted) | Bug | 3 | In Development | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-5177 | Move cho-base and its functionality to cho-ansible | Story | 3 | In Development | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-5563 | Release Sprint 2025_PI1-1 Artefacts | Story | 3 | Blocked | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5580 | TLRD Tasks | Task | 3 | In Progress | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
NPSCO-18264 | Refactor CheckMK storedata script | Story | 3 | In Acceptance | 2 | Engineering |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-5573 | [5PT] Hardware information for C2 scale | Story | 3 | Blocked | - | Engineering | yes | requires delivery from Bizerba | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
BF-338 | [SCO] [Identification] capture customer ID in ringing mode with correct return code DN | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-571 | [SCO][ADAPTER] Integrate Butterfly adapter to single JVM deployment | Story | 3 | Closed | 8 | Papillon |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
BF-623 | [ADAPTER] Send receipts with EGC articles from butterfly adapter to Yocuda | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-674 | [SCO] Send warranty articles to Butterfly adapter | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-724 | [SCO] Log the necessary times for requesting capturing and applying a customer id on the POS Adapter | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-732 | [ADAPTER] Log the necessary times for retrieving and forwarding of customer information at the Butterfly Adapter | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-787 | [ADAPTER] Amend supported fields for forwarding discount information to Butterfly adapter | Bug | 3 | Closed | 1 | Papillon | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
BF-718 | [ADAPTER] Add specific type values for Butterfly related discounts | Story | 3 | Blocked | 3 | Papillon |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
BF-719 | [SCO] Provide identifier for Butterfly coupons and promotions | Story | 3 | Blocked | 5 | Papillon |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
BF-734 | [ADAPTER] Add till number to receipts sent to Yocuda | Story | 3 | In Development | 2 | Papillon | yes |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
BF-740 | [SCO] Send EGC articles to Butterfly adapter | Story | 3 | In Development | 5 | Papillon |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
BF-741 | [SCO] Provide the option to remove anonymous coupons | Story | 3 | Blocked | 5 | Papillon |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
BF-743 | Onboarding of new colleague (Lennart) | Story | 3 | Ready | - | Papillon |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
BF-788 | [SCO] Amend mapping of discount extension properties for sale receipts sent to the Butterfly adapter | Bug | 3 | In Review | 2 | Papillon | yes |  | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
BF-770 | [SCO] Do not forward voided positions to Butterfly adapter | Story | 3 | Ready | 3 | Papillon | yes |  | Removed |  |  | 0 | 3 | 0 | 3 | 0
ANP-24583 | Printer detection not reliable on CHOP MCO after changing printer protocol to NHPI | Bug | 2 | closed | 3 | Payment |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-22753 | The Scanner unit at the Till play alert sound during a card payment | Bug | 2 | closed | 3 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-24318 | EFT: Double debiting of card payments | Bug | 2 | in development | 5 | Payment | yes |  | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
ANP-18160 | CFRM Configuration Guide | Story | 3 | in development | 3 | Payment |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
ANP-19414 | Create Integrity Tests and Manual Tests - AT BASICS | Story | 3 | in development | 5 | Payment |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
ANP-19941 | Create Integrity Tests and Manual Tests - CH BASICS | Story | 3 | in development | 5 | Payment |  |  | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-23694 | Create Integrity Tests and Manual Tests - AT TAW | Story | 3 | in development | 5 | Payment |  |  | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-24846 | Pick ANP-22753 to Release 4.7.1 | Story | 3 | closed | 1 | Payment | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-23695 | Create Integrity Tests and Manual Tests - CH BASICS+ | Story | 3 | closed | 3 | Payment |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-23037 | Terminal Assignment Wizard - IP Address-based - Pre-fill Prompt from Till_State | Story | 3 | in development | 3 | Payment | yes |  | Not Completed |  | 2 | 0 | 3 | 1 | 0 | 2
ANP-24655 | [BOSS Interface] evaluate effects of port change | Task | 3 | closed | - | Payment |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24686 | clarify next steps for setting up test hardware for CHOP CH | Task | 3 | closed | - | Payment |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24485 | find out whether there was a change in printing the second sale receipt in case of EFT/EGC after total | Task | 3 | in progress | - | Payment | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24865 | Ensure triggering of full masterdata resync only after all data has been fully updated by SSR | Story | 3 | In Development | 3 | Sales | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-24774 | Fix CheckMK monitoring service | Story | 3 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24749 | Till is not able to finish the import masterdata when encryption is activated | Bug | 2 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24619 | Creation of analysis tasks regarding PI-1 topics | Task | 3 | In Progress |  | Sales |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24617 | Auto MCO Rebooting after ACO Interface Received Resync Message | Bug | 2 | In Development | 3 | Sales | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-24611 | Fix ClassNotFoundException for ApplicationStateAPI | Bug | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24607 | Fix parameter post release tasks after NEWPOSS 4.7.0 | Story | 2 | Closed | 1 | Sales |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24606 | Add press 'CLEAR' in deactivation error | Story | 3 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24542 | Fix ConfigurationException during startup of simulated till | Story | 3 | In Development | 3 | Sales |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-24529 | Create automated integration test coverage for multilane scanner status handling | Story | 3 | In Development | 5 | Sales |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-24367 | Enable code format checking during maven build | Story | 3 | Closed | 5 | Sales | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-24175 | PC-transaction search transaction missing in system | Bug | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24047 | POS WERW LineItem with "0" Price causing error in backposting | Bug | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23454 | Customer Scanner availability check | Story | 3 | Closed | 13 | Sales |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-11615 | Improve depiction of linked service articles on receipts | Story | 3 | In Development | 3 | Sales | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-24201 | In offline mode, user is unable to log out from a session (started in online mode) | Bug | 2 | Closed | 3 | Synergy |  | zero-noise bug | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24325 | Post Release Tasks for NP Release 4.7.0 | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-24759 * | Welcome onboarding for Sergey and Vladimir | Story | 3 | Closed | 1 | Synergy | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-23847 | Implementation for Add FiscalNullStartReceipt step during CSR process | Story | 2 | In Development | 8 | Synergy |  | only task release left | Not Completed |  | 1 | 8 | 0 | 7 | 0 | 1
ANP-23958 | [IT Ejournal] Error during Ejournal entry creation with EPSON Fiscal Printer | Bug | 3 | Blocked | 3 | Synergy |  | zero-noise bug | Removed |  |  | 3 | 0 | 0 | 3 | 0
ANP-23979 | Testing for Add FiscalNullStartReceipt step during CSR process | Story | 2 | Closed | 5 | Synergy |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-24360 | Replace SNMP monitoring with the Till heartbeat for Backoffice pending balancing scenarios | Story | 2 | Blocked | 8 | Synergy |  | was blocked by BOD team | Removed | 3 |  | 3 | 0 | 0 | 3 | 0
ANP-24608 | HU: Middleware Analysis | Story | 2 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-24168 | Adjust tax rate to 6 decimal places: analysis | Story | 2 | Closed | 3 | Synergy | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18480 | Takeover EGC Payment | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18486 | Kick-Off Knowledge Transfer Celonis to TNT | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18492 | Kick-Off Knowledge Transfer Logging, Tracing and Monitoring to TNT | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15193 | Mount db init scripts for postgres component tests and development | Task | 3 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-15500 | [B] Remove --add-opens when POS adapter is migrated to Spring Boot | Task | 4 | Closed | 1 | TFS | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-15192 | Create scheduler to delete exported receipts | Task | 3 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-16393 | Update Purchase Service after Spring Migration RP | Story | 3 | In Development | 8 | TFS |  |  | Not Completed | 3 | 1 | 3 | 0 | 2 | 0 | 1
NPSCO-15737 | [SCO Pentest] l2: Mosquitto: SCO Information Exposed | Story | 3 | In Development | 3 | TFS |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
NPSCO-10135 | Increase SNMP password complexity | Task | 3 | Closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-15738 | [SCO Pentest] l3: Detailed Error Messages in gRPC Service | Story | 3 | Closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-15736 | [SCO Pentest] m6: Unencrypted Traffic with Store Server | Story | 3 | Closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17566 | [Bug-Analysis] Offline Login fails | Bug | 3 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-11650 | [Test Story] Scale Checksum and Software Version Implementation for Bizerba C2 POS Scale | Story | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18569 | [FI CH] Language Issues | Bug | 2 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17962 | Add taxinformation to export in case of foodstampable items being paid with EBT and other payment card type | Story | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17706 | [ITA] Rounding Logic may be obsolete in TransactionVoidingServiceITAImpl | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18289 | Install production key into Bizerba C2 driver used by SCO | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18179 | Knowledge Transfer for Release Builds between DEV in TNT Team | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18453 | NL UK: Void and Suspend Transaction Messages for Lottery Items Not Displaying Correctly | Bug | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17013 | [15] Merge Spring migration after all tests are done | Task | 3 | In Review | 2 | TNT |  |  | Not Completed |  | 2 | 2 | 0 | 0 | 0 | 2
NPSCO-18378 | [SCO FI CH] Bizerba overlay calculates EUR/kg instead of CHF/kg | Bug | 1 | Closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18487 | Takeover Celonis from TFS | Story | 3 | Open | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18489 | Takeover Optimize Memory from TFS | Story | 3 | Open | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18491 | Takeover Logging, Tracing and Monitoring from TFS | Story | 3 | Open | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17963 | Set taxBase of voided items in export to 0 | Story | 3 | In Development | 3 | TNT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-18504 | Test fiscal country for Spring migration | Task | 3 | In Progress | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18505 | Test US Spring migration | Task | 3 | Open | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18521 | (dublicated by mistake) | Task | 3 | Closed | 0 | TNT |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18018 | Create parent pom of assco-pos-app-adapter-local-component-tests | Task | 3 | In Progress | 3 | TNT |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-18522 | Testing Release 4.13.0 | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18181 | EFT payments cant be processed | Bug | 2 | In Development | 3 | TNT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-18626 | [FI CH] Customer Intervention to be adapted based on Language selected | Story | 3 | In Development | 5 | TNT | yes |  | Not Completed |  | 3 | 0 | 5 | 2 | 0 | 3
NPSCO-18645 | [Spike] Create Monitored Item Adapter using CEP Adapter as blueprint | Task | 3 | Open | 3 | TNT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-16261 | Handle partial/split EGC payments in the transaction after shutdown | Story | 3 | In Test | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17316 | Second split payment with (SVS) EGCs leads to message "insufficent funds" while enough balance is available | Bug | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18448 | Handover EGC Payment | Task | 3 | In Progress | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18428 | Persist Transactiondata/KPIs | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18474 | [AnalyseSpike] Full resync | Task | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18210 | [AnalyseSpike] PIN Printing | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18493 | Load test of the release 413 | Task | 3 | Ready | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18259 | Manually canceled receipts have totalReceiptSum = "null" | Bug | 2 | Concept Design | 5 | TTT |  |  | Removed |  |  | 5 | 0 | 0 | 5 | 0
NPSCO-18563 | Implement till report functionality | Story | 3 | In Development | 5 | TTT | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
NPSCO-17881 | Onboarding Markus Weißeise | Task | 3 | In Progress | None | TTT |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
NPSCO-18138 | Onboarding Anna Terekhina | Task | 3 | In Progress | None | TTT |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
NPSCO-18532 | Release Test 413 [K] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18533 | Release Test 413 [M] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23976 | BF-469 Scan URID | Story | 3 | Closed | 8 | Vlinder |  |  | Completed | 0.5 |  | 0.5 | 0 | 0.5 | 0 | 0
ANP-24042 | BF-572 Validate Promo | Story | 3 | Closed | 3 | Vlinder |  |  | Completed | 0.5 |  | 0.5 | 0 | 0.5 | 0 | 0
ANP-24563 | BF-714 Coupon ID Bug | Bug | 3 | Closed | 3 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-23587 | BF-402 Im- and export | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-23977 | BF-467 Prevent scan URID | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-23978 | BF-63 Asynchronous | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-24045 | BF-573 Testing Part 1 | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed | 5 | 2 | 5 | 0 | 3 | 0 | 2
ANP-24111 | Release Builds for all Butterfly Libs | Task | 3 | Open | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24191 | Merge Implementations for new Scales | Task | 3 | In Progress | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24565 | BF-36 Auto-refund | Story | 3 | In Development | 5 | Vlinder |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-24566 | Build MCO part of release 3.18.8 | Story | 3 | In Development | 1 | Vlinder |  |  | Not Completed |  | 0 | 1 | 0 | 0 | 0 | 1
ANP-24612 | Build MCO part of NEWPOSS release 4.7.1 | Story | 3 | In Development | 1 | Vlinder |  |  | Not Completed |  | 0 | 1 | 0 | 0 | 0 | 1
ANP-24699 | BF-738 Follow-Up PDF creation | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24700 | BF-739 Performance | Task | 3 | In Progress | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24820 * | BF Test Support | Task | 3 | Open | - | Vlinder | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0

## Sprint_4_8 (hidden)
Sprint 4_5, 27.11.2024 - 10.12.2024, Status at Sprint Completion
|  | Team Summary |  |  |  | v v Use these statuses by all means! v v
|  |  |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS]) | [5 empty] | Issue Count
|  | Team | Issue Count | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | Completed
| > > > > Use these team names by all means! > > > > | Engineering | 29 | 65 | 37 | 74 | 28 | 0 | 102 | 113.8% | 65 | 37 | 74 | 0 | 28 | 113.8% | 22
|  | Payment | 6 | 17 | 3 | 9 | 11 | 0 | 20 | 52.94% | 17 | 3 | 9 | 0 | 11 | 52.94% | 3
|  | Sales | 7 | 29 | 3 | 24 | 8 | 0 | 32 | 82.76% | 29 | 3 | 24 | 0 | 8 | 82.76% | 5
|  | Vlinder | 13 | 34 | 14 | 29 | 19 | 0 | 48 | 85.29% | 28 | 14 | 34 | 0 | 8 | 121.4% | 7
|  | TTT | 15 | 49 | 0 | 38 | 11 | 0 | 49 | 77.55% | 42 | 0 | 40 | 0 | 2 | 95.24% | 10
|  | TNT | 19 | 42 | 15 | 52 | 5 | 0 | 57 | 123.8% | 42 | 15 | 52 | 0 | 5 | 123.8% | 17
|  | TFS | 10 | 22 | 4 | 18 | 8 | 0 | 26 | 81.82% | 17 | 4 | 18 | 0 | 3 | 105.9% | 9
|  | 0-Noise | 6 | 27 | 0 | 11 | 16 | 0 | 27 | 40.74% | 27 | 0 | 11 | 0 | 16 | 40.74% | 2
|  | Synergy | 15 | 53 | 1 | 23 | 31 | 0 | 54 | 43.4% | 53 | 1 | 34 | 0 | 20 | 64.15% | 8
|  | Papillon | 12 | 28 | 7 | 24 | 11 | 1 | 35 | 85.71% | 28 | 7 | 32 | 0 | 3 | 114.3% | 10
|  | Total | 105 | 285 | 76 | 255 | 106 | 0 | 361 | 89.47% | 267 | 76 | 262 | 0 | 81 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 101 | 370 | 31 | 92 | 132 | 462 | 126 | 450 | 6 | 12 | 132 | 462
|  | Completed | 70 | 250 | 23 | 56 | 93 | 306 | 91 | 302 | 2 | 4 | 93 | 306
|  | Not Completed | 31 | 120 | 8 | 36 | 39 | 156 | 35 | 148 | 4 | 8 | 39 | 156
|  | Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-24318 EFT: Double debiting of card payments | EFT: Double debiting of card payments | Bug | 2 | Blocked | 3 | 0-Noise |  | Detailed Prodocoll analysis is required. Will be completed in the Pay Team | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24201 | In offline mode, user is unable to log out from a session (started in online mode) | Bug | 2 | In Development | 3 | 0-Noise |  | Only the merge is pending, will be completed in Team Synergy | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-23965 | Voided transactions with gift cards causing "Error During Processing of Till Transactions" | Bug | 2 | closed | 8 | 0-Noise |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-22753 | The Scanner unit at the Till play alert sound during a card payment. | Bug | 2 | In Development | 3 | 0-Noise |  | Only the merge is pending, will be completed in Team Payment | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-19941 | Create Integrity Tests and Manual Tests - CH BASICS | Story | 3 | In Development | 5 | 0-Noise |  | Will be completed in the Pay Team | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-19414 | Create Integrity Tests and Manual Tests - AT BASICS | Story | 3 | In Development | 5 | 0-Noise |  | Will be completed in the Pay Team | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-23190 | Clarify UI/Softwaredisplay layout, size and colors | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23200 | Create localized configurations for Bizerba C2 for each country with corresponding language and decimal separator | Story | 3 | Closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23987 | Fail MCO MSI pipeline if RPM signature is unsuccessful | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24199 | Error during startup of NEWPOSS launch script | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24478 | Collect cho monitoring data for mco-storedata.txt | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-2133 | Deactivate SCO display controls by default | Story | 2 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5133 | Provide script for collection of CMDB data | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5150 | Keep CMDB information across re-installations of the till | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5296 | Implement EFT driver fixes for OPI and CB2P17 drivers in POS Core | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5363 | Application of BIOS settings fails if no configuration file for version is available | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5406 | Bizerba C2 software display cannot be installed on Rocky Linux 9.5 | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5417 | Till user cannot update software display layout for C2 scale | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5423 | Dn Sx mainboards do not boot automatically when user passwords is set | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5427 | Integrate bizerba C2 authentication key | Story | 2 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5444 | Race condition between reboot issued by cho-firstboot and ATS/ASSCO installer | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5513 | NHPI reconfiguration may fail without exit code indicating an error | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-2835 | GSD Performance Incident Summary Shortcut Command Implementation | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5161 | Harden the shortcut role in ansible by deleting shortcut scripts from a false system | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5173 | CSR job does only consider https communication | Bug | 3 | Blocked | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5188 | Release Sprint PI4-7 Artefacts | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5228 | Provide How-to articles for hardware monitoring | Story | 3 | In Development | 20 | Engineering | yes |  | Not Completed |  |  | 0 | 20 | 0 | 0 | 20
CHO-5292 | PARENT - POS Scale issues 2024 Dec. / (NON-Waage Entlasten) after Bizerba Display 4x RPM update | Bug | 2 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5325 | Provision of SLO certificates by ALDI | Story | 3 | Blocked | 2 | Engineering |  | meeting postponed by ALDI | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
CHO-5392 | Store debug-info archive in user directory, not /root/ | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-5475 | TLRD Tasks | Task | 3 | Closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5524 | Perform and document configuration of country settings on C2 scale | Task | 3 | Blocked | - | Engineering | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
CHO-5525 | Support Team Synergy with CSR | Task | 3 | In Progress | - | Engineering | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
CHO-5527 | Add cho local checks and collector script to CHO release | Story | 3 | In Development | 2 | Engineering | yes | implementation done, documentation to do | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
NPSCO-18264 | Refactor CheckMK storedata script | Story | 3 | In Development | 1 | Engineering |  |  | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
BF-306 | [SCO] Skip printing the receipt based on customer choice in app | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-309 | [SCO] Provide queueing mechanism for the communication with Butterfly adapter | Story | 3 | Closed | 1 | Papillon |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
BF-571 | [SCO][ADAPTER] Integrate Butterfly adapter to single JVM deployment | Story | 3 | In Development | 8 | Papillon |  |  | Not Completed |  | 2 | 8 | 0 | 6 | 0 | 2
BF-619 | [ADAPTER] Configure MQTT session parameters | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-620 | [ADAPTER] Send receipts with warranty articles from butterfly adapter to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-626 | [ADAPTER] Switch Yocuda request authentication from JWT to bearer token | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-654 | [ADAPTER][SCO] Create release for onsite test at ALDI | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-674 | [SCO] Send warranty articles to Butterfly adapter | Story | 3 | In Development | 3 | Papillon |  |  | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
BF-675 | [SCO] Amend store opening hours mapping | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-703 | [ADAPTER][SCO] Support deployment in ALDI test lab | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-704 | [SCO] Sometimes after installation from scratch the POS adapter has to be restarted to enable PDF receipt generation | Bug | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-705 | [ADAPTER][SCO] Update certificate trust store of butterfly adapter's container to include the public key of the ALDI root certificate | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-18160 | CFRM Configuration | Story | 3 | In Development | 3 | Payment |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-23018 | Testing of Terminal Assignment Concept | Story | 3 | Closed | 3 | Payment |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23694 | Create Integrity Tests and Manual Tests - AT TAW | Story | 3 | In Development | 5 | Payment |  | based on team forecast | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-23695 | Create Integrity Tests and Manual Tests - CH BASICS+ | Story | 3 | In Development | 3 | Payment |  | based on team forecast | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-24398 | [SPIKE] Clarify Requirements for HU Social Voucher | Story | 3 | Closed | 3 | Payment |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24495 | [CHOP AT] EFTs do not initialise after being allocated to the till via the wizard | Bug | 3 | Closed | 3 | Payment | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24542 | Analyse ConfigurationException during startup of simulated till | Task | 3 | Open |  | Sales | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24541 | Analyse ClassNotFoundException for ApplicationStateAPI | Task | 3 | Closed |  | Sales | yes |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-23454 | Customer Scanner availability check | Story | 3 | In Development | 8 | Sales |  |  | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-22866 | Trigger reconfiguration via POS Keyboard | Story | 2 | Closed | 13 | Sales |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-19967 | Add press 'CLEAR' in activation error | Story | 3 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-18979 | Provide checkMK monitoring values related to master data polling and processing | Story | 2 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-13550 | Adapt ReceiptPositions layout rows to check whether they are executed for an item receipt position | Story | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23684 | RVM voucher can not be redeemed in case of an offline scenario at the till | Bug | 2 | Closed | 1 | Synergy |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-23992 | Add a null check and redundant check remove | Story | 3 | Closed | 1 | Synergy |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-24506 * | Build MCO part of release 3.18.7 | Story | 3 | Closed | 2 | Synergy |  | est.changed | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-12711 | Fix exceptions during automated tests | Story | 3 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-14099 | Improve implementation of Tax Refund | Story | 3 | Blocked | 3 | Synergy |  |  | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
ANP-15539 | Extract receipt logic from RetrieveReceiptController | Story | 3 | Blocked | 2 | Synergy |  | est.changed | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
ANP-22307 | Replace deprecated constant BASKET_DISCOUNT_ROUNDING_FRACTION | Story | 3 | Blocked | 3 | Synergy |  | needs to be merged together with the corresponding BOD (and potentially SCO) stories. | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
ANP-23847 | Implementation for Add FiscalNullStartReceipt step during CSR process | Story | 2 | In Development | 8 | Synergy |  | est.changed | Not Completed |  | 8 | 8 | 0 | 0 | 0 | 8
ANP-23979 | Testing for Add FiscalNullStartReceipt step during CSR process | Story | 2 | Open | 5 | Synergy |  |  | Not Completed |  | 5 | 5 | 0 | 0 | 0 | 5
ANP-24320 | Build MCO part of NEWPOSS release 4.7.0 | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24325 | Post Release Tasks for NP Release 4.7.0 | Story | 3 | In Development | 2 | Synergy |  |  | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
ANP-24357 | HU middleware - Investigation story | Story | 2 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-24360 | Replace SNMP monitoring with the Till heartbeat for Backoffice pending balancing scenarios | Story | 2 | In Development | 8 | Synergy |  | est.changed | Not Completed |  | 2 | 8 | 0 | 6 | 0 | 2
ANP-24410 | Build MCO part of NEWPOSS release 4.4.2 | Story | 3 | Closed | 2 | Synergy |  | est.changed | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-24439 | Build MCO part of release 3.18.6 | Story | 3 | Closed | 1 | Synergy | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-16393 | Update Purchase Service after Spring Migration RP | Story | 3 | In Development | 8 | TFS |  |  | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-17300 | Tax middleware timeouts are being ignored by SCO | Bug | 2 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16415 | [ITA] Attendant intervention for printer has to be confirmed four times and prevents the start of a new transaction | Bug | 3 | Closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17076 | Adjust fiscal adapter workaround script to use CHO installation method | Story | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15056 | [SPIKE] Analyse Autoupdate Script failure | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17198 | Infra: Archived Log files are being saved in the wrong folder | Bug | 3 | Closed | 1 | TFS |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18023 | Onboarding Philipp Sackel | Task | 3 | Closed |  | TFS |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18294 | Test Task 4.12.0 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17371 | Fix folder permissions of Combined Services | Task | 3 | Closed | 2 | TFS | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-17024 | Admin User does not have to see the combined services logs | Bug | 3 | Closed | 2 | TFS | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-11650 | [Test Story] Scale Checksum and Software Version Implementation for Bizerba C2 POS Scale | Story | 3 | Ready | 3 | TNT |  |  | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-17012 | [14] Test English country before merge Spring migration | Task | 3 | In Progress | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16632 | [12] Present Implementation in CoP Dev | Task | 3 | In Progress | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16037 | [SCO DE AHEAD] Remove precondition "number of ean/upc assigned to variants of beverage itemID in reusable bottles" to display the selection screen | Story | 3 | In Development | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17533 | [Infinity] DRS/RVM causing balancing issues on SCOs. | Bug | 2 | In Development | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17723 | [Analyse Spike] NPSCO-17530 Harmonisation of ACO Transaction Data for SCOs | Task | 3 | In Review | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17962 | Add taxinformation to export in case of foodstampable items being paid with EBT and other payment card type | Story | 3 | In Development | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18177 | Create the group cs300sd and add the user assco-inf to this group | Story | 3 | In Review | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18217 | Suspend transaction action not working as expected | Bug | 3 | In Review | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18218 | POS adapter log doesn't exist anymore | Bug | 3 | In Review | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18219 | No payload or ejournal created after hard reset | Bug | 3 | In Review | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18223 | Sometimes close lane fails with error 'UNAVAILABLE: io exception' | Bug | 3 | In Development | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18225 | POS adpater log is flooded with fiscalization messages [ITA,DE] | Bug | 3 | In Development | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18333 | Testing Release 4.12.0 | Task | 3 | In Progress | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-18232 | UK: Transaction Command Rejected When Adding Items to Receipt | Bug | 3 | Closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18234 | No customer intervention when Inactivity Timer for card payment SCOs is active. Attendant intervention shown right away | Bug | 3 | Closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-17706 | [ITA] Rounding Logic may be obsolete in TransactionVoidingServiceITAImpl | Task | 3 | In Progress | 2 | TNT | yes |  | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
NPSCO-18413 | Coupon names are not resolved on the receipt | Bug | 3 | Closed | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18439 | Setup docker images for Rocky Linux based VSS International R27.4 and R28 | Task | 3 | In Progress | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18127 | Release Build 4.12.0 | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17729 | Java-Based gRPC Client for testing POS Transactions | Story | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16190 | [11] Test fiscal country for Spring migration | Task | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17011 | [13] Test US before merge Spring migration | Task | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-18290 | Test Task for Spring Migration | Task | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16261 | Handle partial/split EGC payments in the transaction after shutdown | Story | 3 | In Test | 3 | TTT |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
NPSCO-18175 | BO SP SCOs showing offline on cashier widget after update- No EM | Bug | 2 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16518 | [UK,AUS] Scanned EGC in RINGING is on the receipt before selection of action | Bug | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17316 | Second partial payment with (SVS) EGCs leads to message "insufficent funds" while enough balance is available | Bug | 3 | In Development | 3 | TTT |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
NPSCO-18259 | Manually canceled receipts have totalReceiptSum = "null" | Bug | 2 | Blocked | 5 | TTT |  |  | Not Completed | 0 | 5 | 0 | 0 | 0 | 0 | 0
NPSCO-17881 | Onboarding Markus Weißeise | Task | 3 | In Progress | None | TTT |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18138 | Onboarding Anna Terekhina | Task | 3 | In Progress | None | TTT |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18334 | Test Release 4.12.0 [M] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18335 | Test Release 4.12.0 [C] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18366 | Release Build 4.13.0 | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-24484 * | Revert cherry-pick on maintenance branch 4.4 | Task | 3 | Closed | - | Vlinder | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-23242 | BF-135 Mapping | Story | 3 | Closed | 8 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-23975 | BF-389 Test coverage | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 5 |  | 5 | 0 | 5 | 0 | 0
ANP-23976 | BF-469 Scan URID | Story | 3 | In Development | 8 | Vlinder |  |  | Not Completed |  | 0.5 | 8 | 0 | 7.5 | 0 | 0.5
ANP-24042 | BF-572 Validate Promo | Story | 3 | In Development | 3 | Vlinder |  |  | Not Completed | 3 | 0.5 | 3 | 0 | 2.5 | 0 | 0.5
ANP-24045 * | BF-573 Testing Part 1 | Story | 3 | In Development | 5 | Vlinder | yes |  | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
ANP-24088 | BF-569 Test | Story | 3 | Closed | 5 | Vlinder |  |  | Completed | 5 |  | 5 | 0 | 5 | 0 | 0
ANP-24111 | Release Builds for all Butterfly Libs | Task | 3 | Open | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24191 | Merge Implementations for new Scales | Task | 3 | In Progress | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24445 | BF-238 PDF creation | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24486 * | BF-697 MSI | Story | 3 | Closed | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24511 * | ITA refund receipt is missing payment and discount positions | Bug | 1 | Closed | 3 | Vlinder | yes | rejected | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24563 * | BF-714 Coupon ID Bug | Bug | 3 | In Development | 3 | Vlinder | yes |  | Not Completed |  | 2 | 0 | 3 | 1 | 0 | 2
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0

## Sprint_4_6 (hidden)
Sprint 4_5, 27.11.2024 - 10.12.2024, Status at Sprint Completion
|  | Team Summary |  |  |  | v v Bitte unbedingt diese Status verwenden! v v v
|  |  |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS]) | [5 empty] | Issue Count
|  | Team | Issue Count | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | Completed
| > > > > Bitte unbedingt diese Team-Namen verwenden! > > > > > | Engineering | 22 | 46 | 19 | 37 | 28 | 0 | 65 | 80.43% | 46 | 19 | 37 | 0 | 28 | 80.43% | 15
|  | Payment | 11 | 17 | 3 | 20 | 0 | 0 | 20 | 117.6% | 11 | 3 | 14 | 0 | 0 | 127.3% | 11
|  | Sales | 14 | 26 | 15 | 33 | 8 | 0 | 41 | 126.9% | 22 | 15 | 34 | 0 | 3 | 154.5% | 13
|  | Vlinder | 13 | 39 | 4 | 18 | 25 | 0 | 43 | 46.15% | 31 | 4 | 18 | 0 | 17 | 58.06% | 5
|  | TTT | 25 | 63 | 14 | 51 | 26 | 0 | 77 | 80.95% | 50 | 9 | 56 | 0 | 3 | 112% | 18
|  | TNT | 18 | 47 | 16 | 38 | 25 | 0 | 63 | 80.85% | 47 | 16 | 38 | 0 | 25 | 80.85% | 12
|  | TFS | 16 | 27 | 11 | 30 | 8 | 0 | 38 | 111.1% | 27 | 11 | 32 | 0 | 6 | 118.5% | 14
|  | 0-Noise | 9 | 29 | 24 | 32 | 21 | 0 | 53 | 110.3% | 29 | 24 | 37 | 0 | 16 | 127.6% | 5
|  | Synergy | 14 | 71 | 2 | 30 | 43 | 0 | 73 | 42.25% | 71 | 2 | 58 | 0 | 15 | 81.69% | 7
|  | Papillon | 20 | 24.5 | 31.5 | 37 | 17 | 1 | 56 | 151% | 20.5 | 31.5 | 37 | 2 | 13 | 180.5% | 15
|  | Total | 128 | 294 | 106 | 259 | 141 | 0 | 400 | 88.1% | 263 | 101 | 266 | 0 | 98 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 110 | 399.5 | 52 | 147.5 | 162 | 547 | 153 | 529 | 9 | 18 | 162 | 547
|  | Completed | 81 | 263.5 | 34 | 80.5 | 115 | 344 | 106 | 326 | 9 | 18 | 115 | 344
|  | Not Completed | 28 | 134 | 18 | 67 | 46 | 201 | 46 | 201 | 0 | 0 | 46 | 201
|  | Removed | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 0 | 1 | 2
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-17528 | Remove the unnecessary test reference to till-receiptsearch-impl | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-15108 | Use country-specific amount and weight formatting for Weighing Report | Bug | 3 | Closed | 5 | 0-Noise |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-22666 | Refactor CSR Tests and LTC | Story | 3 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23450 | [SPIKE] Investigation - Check whether InitialBackupRestoreStatusKVStoragePOSServiceImpl can be used or deleted | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-19414 | Create Integrity Tests and Manual Tests - AT BASICS | Story | 3 | In Development | 5 | 0-Noise | yes | Execution of Multilane Integrity Tests offer some additional unexpected complexity. Therefore the Issue was not completed | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
ANP-19512 | Set up test hardware | story | 3 | closed | 3 | Payment |  |  | Completed | 1 | 0 | 1 | 0 | 1 | 0 | 0
ANP-19941 | Create Integrity Tests and Manual Tests - CH BASICS | Story | 3 | In Development | 5 | 0-Noise | yes | Execution of Multilane Integrity Tests offer some additional unexpected complexity. Therefore the Issue was not completed | Not Completed |  | 5 | 0 | 5 | 0 | 0 | 5
ANP-20258 | [Spike] Enable Code format checking for till-dev | Story | 3 | Closed | 5 | Sales |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-21725 | Update ArchUnit library usage in MCO | Story | 3 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23721 | Onboarding Hanna | Task | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-22433 | Refactor VerifyPriceController | Story | 3 | Closed | 8 | 0-Noise |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-22494 | [ITA] Instant Lottery Code not printed on receipt | Bug |  | In Development | 3 | Vlinder |  |  | Not Completed | 1 |  | 1 | 0 | 0 | 0 | 1
ANP-24032 | [SPIKE] middleware for fiscalisation hungary | Story | 2 | Closed | 8 | Synergy |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-22884 | Fix MasterdataProvisioningPOSService OSGi configuration | Story | 3 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23002 | Unite all EGC Training mode tests at one position | Story | 3 | Closed | - | Sales | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-23181 | Create Multilane IP assignment extension setting | story | 3 | closed | 3 | Payment |  |  | Completed | 2 | 0 | 2 | 0 | 2 | 0 | 0
ANP-23190 | Clarify UI/Softwaredisplay layout, size and colors | Story | 3 | In Development | 3 | Engineering |  | awaiting input from ALDI | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-23197 | Printing of printer, scanner and terminal assignments on software and bundle version receipt | story | 3 | closed | 2 | Payment |  |  | Completed | 1 | 0 | 1 | 0 | 1 | 0 | 0
ANP-23200 | Create localized configurations for Bizerba C2 for each country with corresponding language and decimal separator | Story | 3 | Blocked | 8 | Engineering |  | awaiting input from ALDI | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
ANP-23217 | Provide device information in devices.xml for multilane proxy | Story | 3 | Closed | 13 | 0-Noise |  |  | Completed |  |  | 13 | 0 | 13 | 0 | 0
ANP-23242 | BF-135 Mapping | Story |  | In Development | 8 | Vlinder |  |  | Not Completed | 2 |  | 2 | 0 | 0 | 0 | 2
ANP-23344 | Enable FiscalizationPerformCheck for Austria | story | 3 | closed | 3 | Payment |  |  | Completed | 1 | 0 | 1 | 0 | 1 | 0 | 0
ANP-24033 | [SPIKE] US Till Sharing | Story | 3 | Closed | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23454 | Customer Scanner availability check | Story | 3 | In Development | 8 | Sales |  |  | Not Completed |  | 3 | 8 | 0 | 5 | 0 | 3
ANP-23670 | Set Multilane IP assignment extension setting for CH | story | 3 | closed | 1 | Payment |  |  | Completed | 1 | 0 | 1 | 0 | 1 | 0 | 0
ANP-24186 | WAW Test Lab onboarding | Story | 3 | Closed | 2 | Synergy | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-23693 | Update checkmk agent in NEWPOSS | Story | 3 | In Acceptance | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-22307 | Replace deprecated constant BASKET_DISCOUNT_ROUNDING_FRACTION | Story | 3 | In Review | 5 | Synergy |  | reestimated on retro, higher efforts | Not Completed | 5 | 2 | 5 | 0 | 3 | 0 | 2
ANP-23810 | [US Tax] Water tax not reflecting on suspend/retrieve receipts | Bug | 4 | Blocked | 3 | 0-Noise |  | Despite huge efforts it was not possible to reproduce the issue. It will be subject of futher refinements and be pulled in a later sprint | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23684 | RVM voucher can not be redeemed in case of an offline scenario at the till | Bug | 2 | In Review | 10 | Synergy |  | reestimated on retro, higher efforts | Not Completed | 10 | 1 | 10 | 0 | 9 | 0 | 1
ANP-23896 | Terminal Assignment Wizard - IP Address-based - Range Violation Error Beep | story | 3 | closed | 2 | Payment |  |  | Completed |  | 0 | 2 | 0 | 2 | 0 | 0
ANP-23897 | Terminal Assignment Wizard - IP Address-based - Prohibit Double Entries | story | 3 | closed | 3 | Payment |  |  | Completed |  | 0 | 3 | 0 | 3 | 0 | 0
ANP-23898 | Terminal Assignment Wizard - IP Address-based - Empty Prompt with Clear | story | 3 | closed | 2 | Payment | yes |  | Completed |  | 0 | 0 | 2 | 2 | 0 | 0
ANP-23903 | Till is in bootloop when encryption is activated | Bug | 2 | Closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23910 | Translation adjustments for 8+Code (HU, SL, IT) and 18+Code (SL, IT) till reports | Story | 3 | Closed | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-23919 | Fatma Onboarding | Task |  | Closed | 0 | Vlinder |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-23965 | Voided transactions with gift cards causing "Error During Processing of Till Transactions" | Bug | 2 | Blocked | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23973 | create "nightly build" V1 for austrian and swiss multilane testing | task | 3 | closed | - | Payment |  |  | Completed |  | 0 | 0 | 0 | - | 0 | 0
ANP-23975 | BF-389 Test coverage | Story |  | In Development | 5 | Vlinder |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-23847 | Implementation for Add FiscalNullStartReceipt step during CSR process | Story | 2 | In Review | 8 | Synergy |  | reestimated on retro, higher efforts | Not Completed | 8 | 2 | 8 | 0 | 6 | 0 | 2
ANP-23992 | Add a null check for objects of the class where the getClass() method call is used | Story | 3 | In Review | 2 | Synergy |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
ANP-14099 | Improve implementation of Tax Refund | Story | 3 | In Development | 8 | Synergy |  |  | Not Completed | 8 | 3 | 8 | 0 | 5 | 0 | 3
ANP-15539 | Extract receipt logic from RetrieveReceiptController | Story | 3 | In Test | 5 | Synergy |  | reestimated on retro, higher efforts | Not Completed | 5 | 1 | 5 | 0 | 4 | 0 | 1
ANP-24041 | BF-570 new API | Story |  | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24042 | BF-572 Validate Promo | Story |  | In Development | 3 | Vlinder |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-24068 | create "nightly build" V2 for austrian and swiss multilane testing | task | 3 | closed | - | Payment |  |  | Completed |  | 0 | 0 | 0 | - | 0 | 0
ANP-24087 | BF-568 Deploy | Story |  | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-24088 | BF-569 Test | Story |  | In Development | 5 | Vlinder |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-24111 | Release Builds for all Butterfly Libs | Task |  | Open | 0 | Vlinder | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24125 | AT - POS MASTER_DATA_PROVISIONING not running | Bug | 2 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24156 | Display correct text for selection possibilities in display when 85+CODE is used | story | 3 | closed | 1 | Payment | yes |  | Completed |  | 0 | 0 | 1 | 1 | 0 | 0
ANP-23979 | Testing for Add FiscalNullStartReceipt step during CSR process | Story | 2 | In Development | 5 | Synergy |  |  | Not Completed | 5 | 5 | 5 | 0 | 0 | 0 | 5
ANP-24191 | Merge Implementations for new Scales | Task |  | In Progress | 0 | Vlinder | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-24201 | In offline mode, user is unable to log out from a session (started in online mode) | Bug | 2 | In Development | 3 | 0-Noise | yes | We could not complete the tests for this issue and will complete them in the next sprint | Not Completed |  | 3 | 0 | 3 | 0 | 0 | 3
ANP-24205 | Build MCO part of release 4.6.0 | Story | 3 | Closed | 3 | Sales | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24209 | Post Release Tasks for NP Release 4.6.0 | Story | 3 | Closed | 2 | Sales | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-24247 | Build Empty Release 3.13.11 | Story |  | In Development | 1 | Vlinder | yes |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
ANP-24249 | Print fiscal lottery code as QR-Code instead of Datamatrix | Story | 2 | Closed | 5 | Sales | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-24252 | Multi-Use_Deposit: RVM vouchers created on the 31.12. during a leap year are denied with 'RVM Bon abgelaufen' | Bug |  | Closed | 3 | Vlinder | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-24255 | Release 3.18.5 | Story | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-24307 | [QA] Till did not update automatically after updating from Release 3.1B(NP version: 3.13.10.1) to Release 3.1B1 (NP version: 3.13.11.1) | Bug | 1 | Closed | - | Sales | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-24309 | Release 3.13.12 | Story | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
BF-306 | [SCO] Skip printing the receipt based on customer choice in app | Story | 3 | In Development | 5 | Papillon | yes |  | Not Completed |  | 1 | 0 | 5 | 4 | 0 | 1
BF-330 | [SCO] Print additional free text for identified customer | Story | 3 | Closed | 5 | Papillon | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
BF-394 | [ADAPTER] Send receipts with variant articles from butterfly adapter to Yocuda | Story | 3 | Closed | 3 | Papillon | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
BF-414 | [SCO] Amend mapping of unique sale receipt ID | Story | 3 | Closed | 5 | Papillon |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
BF-442 | [SCO] Extend the transmission of sale receipts to the Butterfly adapter with the option to send discount information | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-444 | [SCO] Amend depiction of promotion data in SCO purchase transaction | Story | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-548 | [ADAPTER] Amend custom properties in payment details in mapping to Yocuda | Story | 3 | Closed | 1 | Papillon |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
BF-552 | [ADAPTER][SCO] Deploy SCO with butterfly adapter on SCO hardware and test connection to CEE and Yocuda | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-553 | [SCO] Switch to LMS API version 0.6 for customer loyalty information requests to Butterfly adapter | Story | 3 | Closed | 1 | Papillon |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
BF-558 | [ADAPTER] Replace generic receipt PDF name with combination of location, date and time of purchase | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-577 | [ADAPTER] Switch to newest Yocuda API version for transmission of transaction data | Story | 3 | Removed from sprint | 2 | Papillon |  | Removed due to blocker from Yocuda | Removed |  |  | 2 | 0 | 0 | 2 | 0
BF-579 | [SCO][SPIKE] Evaluate possible options to activate/deactivate the Butterfly adapter of a SCO based on CFRM parameter settings | Story / Spike | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-581 | [SCO][SPIKE] Explore how to provide a queueing/retry mechanism for the communication with Butterfly adapter | Story / Spike | 3 | Closed | 2 | Papillon |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-582 | [SCO] Provide stand alone Butterfly adapter deployment | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-588 | [ADAPTER] Switch to LMS API version 0.6 for customer loyalty information requests sent to Butterfly adapter | Story | 3 | Closed | 0.5 | Papillon |  |  | Completed |  |  | 0.5 | 0 | 0.5 | 0 | 0
BF-614 | [ADAPTER] Enable Kubernetes capabilities | Story | 3 | Closed | 0.5 | Papillon | yes |  | Completed |  |  | 0 | 0.5 | 0.5 | 0 | 0
BF-617 | [ADAPTER] Amend transmitted receipt information, so that PDF name and file extension are preserved | Story | 3 | Closed | 2 | Papillon | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-654 | [ADAPTER][SCO] Create release for onsite test at ALDI | Story | 3 | In Development | 2 | Papillon | yes | pulled intro sprint on tuesday (last day of the sprint, because otherwise DEVs would run out of work; therefore is no notable progress and the remaining storypoints equal the original estimation | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
BF-626 | [ADAPTER] Switch Yocuda request authentication from JWT to bearer token | Story | 3 | In Development | 2 | Papillon | yes | pulled intro sprint on tuesday (last day of the sprint, because otherwise DEVs would run out of work; therefore is no notable progress and the remaining storypoints equal the original estimation | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
BF-571 | [SCO][ADAPTER] Integrate Butterfly adapter to single JVM deployment | Story | 3 | In Development | 8 | Papillon | yes | pulled intro sprint on tuesday (last day of the sprint, because otherwise DEVs would run out of work; therefore is no notable progress and the remaining storypoints equal the original estimation | Not Completed |  | 8 | 0 | 8 | 0 | 0 | 8
CHO-2835 | GSD Performance Incident Summary Shortcut Command Implementation | Story | 3 | In Development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-5030 | Provide CHO monitoring data for CheckMk | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5034 | Refactor CHO check format | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5133 | Provide script for collection of CMDB data | Story | 3 | In Test | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5141 | [10PT] Provide tooling to gather information about displays | Story | 3 | Closed | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5150 | Keep CMDB information across re-installations of the till | Story | 3 | Blocked | 3 | Engineering |  | awaiting updated documentation from Bizerba | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5158 | Provide documentation for hardware monitoring | Story | 3 | Closed | 3 | Engineering |  | meeting with ALDI set to 20th of January | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5159 | SCO: Remedy pen-test findings for Beetle M3 Rx boards | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5173 | CSR job does only consider https communication | Bug | 3 | Blocked | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-5174 | Provide documentation for the message broker | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5188 | Release Sprint PI4-6 Artefacts | Story | 3 | Blocked | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5263 | TLRD Tasks | Task | 3 | In Progress | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5292 | PARENT - POS Scale issues 2024 Dec. / (NON-Waage Entlasten) after Bizerba Display 4x RPM update | Bug | 2 | Blocked | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-5325 | Provision of SLO certificates by ALDI | Story | 3 | In Development | 2 | Engineering | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
CHO-5330 | New SSH Keys & distribution script for all till-users | Story | 1 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5331 | Change Store region does not work because of differences in data structures | Bug | 1 | Blocked | 3 | Engineering | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
CHO-5342 | Build hot-fix for changed ssh-keys and user passwords | Story | 1 | In Acceptance | 8 | Engineering | yes |  | Completed |  |  | 0 | 8 | 8 | 0 | 0
CHO-5388 | Support SCO placeholder | Task | 3 | Closed | - | Engineering | yes | support for NPSCO-18265 | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5393 | Support Aldi in setting up Italian test system with fiscal adapter | Task | 3 | In Progress | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
NPSCO-11650 | [Test Story] Scale Checksum and Software Version Implementation for Bizerba C2 POS Scale | Story | 3 | Ready | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16037 | [SCO DE AHEAD] Remove precondition "number of ean/upc assigned to variants of beverage itemID in reusable bottles" to display the selection screen | Story | 3 | In Development | 3 | TNT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17005 | Refactor StatusApplicationService so that the latest transaction ID is no longer maintained twice | Task | 3 | closed | 3 | TTT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-16225 | [NL UK] Add Fault Reference code in error message | Story | 3 | Closed | 2 | TFS |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17240 | SCO 3 - transaction command rejected | Bug | 2 | closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16393 | Update Purchase Service after Spring Migration RP | Story | 3 | In Development | 5 | TFS |  |  | Not Completed | 5 | 3 | 5 | 0 | 2 | 0 | 3
NPSCO-16524 | Update BEV System documentation by including Bizerba C2 | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-16616 | [7] Build MSI, deploy it on a TestLab SCO, execute a developer test and fix findings | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16618 | Delete all Lagom/Akka/Typesafe strings from code base | Task | 3 | In Progress | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17699 | Knowledge Transfer for EGC-EPAY | Task | 3 | closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17738 | Maintenance Release 3.10.10 | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17012 | [14] Test English country before merge Spring migration | Task | 3 | In Progress | 5 | TNT |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17235 | [Incident Taskforce] Trigger device re-initialisation when printer connection not lost | Story | 2 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17739 | Maintenance Release 3.13.6 | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17300 | Tax middleware timeouts are being ignored by SCO | Bug | 2 | In Development | 3 | TFS |  |  | Not Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-17523 | Implement logging on service edges with timing information | Story | 3 | Closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17533 | [Infinity] DRS/RVM causing balancing issues on SCOs. | Bug | 2 | In Development | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-17740 | Test Maintenance Release 3.10.10 [C] | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17741 | Test Maintenance Release 3.10.10 [M] | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17723 | [Analyse Spike] NPSCO-17530 Harmonisation of ACO Transaction Data for SCOs | Task | 3 | In Progress | 3 | TNT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17742 | Test Maintenance Release 3.13.6 [C] | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17743 | Test Maintenance Release 3.13.6 [M] | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17746 | Release Build 4.10.0 | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18015 | Test Maintenance Release 3.18.2 [C] | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18016 | Test Maintenance Release 3.18.2 [M] | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17700 | Knowledge Transfer to Release and update documentation | Story | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17728 | Measure and document RAM usage and JVM metrics(RAM?) of the till | Story | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18250 | Hotfix Build 3.10.11 | Task | 3 | Closed | 3 | TTT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18251 | Hotfix Build 3.18.3 | Task | 3 | Closed | 3 | TTT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18128 | Test Release 4.10.0 [M] | Task | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17747 | Test Task 3.10.10 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17748 | Test Task 3.13.6 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17785 | Test Task 3.18.2 | Task | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18056 | Estimation Demands | Task | 3 | Closed | 0 | TTT |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-17962 | Add taxinformation to export in case of foodstampable items being paid with EBT and other payment card type | Story | 3 | In Development | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16190 | [11] Test fiscal country for Spring migration | Task | 3 | In Progress | 5 | TTT |  |  | Not Completed | 0 | 5 | 0 | 0 | 0 | 0 | 0
NPSCO-18026 | Testing Maintenance Release 3.13.6 | Task | 3 | Closed | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-18035 | gsd and nit users does not have access to read SCO db | Bug | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18050 | Maintenance Release 3.18.2 Test Part II | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18051 | Testing Release 4.10.0 | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18052 | Maintenance Release 3.10.10 Test | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-18113 | Test Task 4.10.0 | Task | 3 | Closed |  | TFS |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18181 | EFT payments cant be processed | Bug | 2 | In Development | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-18216 | Spring Migration - Issues found before merge | Bug | 3 | Open | 8 | TNT | yes |  | Not Completed |  |  | 0 | 8 | 0 | 0 | 8
NPSCO-18227 | Test Task for Spring Migration | Task | 3 | Closed | 1 | TFS | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-18233 | SCO - Unable to Complete Transactions When Tax Middleware Service is Down - US | Bug | 1 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18253 | Cherry Pick Hotfix Release 3.10.11 | Task | 3 | Closed | 1 | TFS | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-18255 | Cherry Pick Hotfix Release 3.18.3 | Task | 3 | Closed | 1 | TFS | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-18265 | SCO - Unable to Complete Interventions from ATS | Bug | 1 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-18267 | Cherry Pick Hotfix Release 3.18.3 | Task | 3 | Closed | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-18285 | Test Task 3.10.11 | Task | 3 | Closed | 1 | TFS | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-18287 | Test Task 3.18.3 | Task | 3 | Closed | 1 | TFS | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-7353 | Integrate Bizerba C2 POS Scale driver | Story | 3 | In Development | 8 | TNT |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
NPSCO-16261 | Handle partial/split EGC payments in the transaction after shutdown | Story | 3 | open | 3 | TTT |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
NPSCO-17011 | [13] Test US before merge Spring migration | Task | 3 | In Progress | 5 | TTT |  |  | Not Completed | 0 | 5 | 0 | 0 | 0 | 0 | 0
NPSCO-17729 | Java-Based gRPC Client for testing POS Transactions | Story | 3 | In Development | 5 | TTT |  |  | Not Completed | 4 | 1 | 4 | 0 | 3 | 0 | 1
NPSCO-17881 | Onboarding Markus Weißeise | Task | 3 | In Progress | 0 | TTT |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18290 | Test Task for Spring Migration | Task | 3 | In Progress | 5 | TTT | yes |  | Not Completed | 0 | 5 | 0 | 0 | 0 | 0 | 0
NPSCO-18127 | Release Build 4.12.0 | Task | 3 | In Progress | 3 | TTT |  |  | Not Completed | 2 | 1 | 2 | 0 | 1 | 0 | 1
ANP-23496 | [4.0A][AT] Active 'tim-terminal-p400' parameter causes Simulated Till to be perpetually stuck at step 'TERMINAL INITIALIZATION' | Bug | 3 | Blocked | 3 | 0-Noise | yes | Our analysis came to the conclusion that the software works as designed but we expect the description is not as precise as we would have needed it. Therefore the issue is subject of futher refinements and may pe pulled to a later sprint | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-23965 | Voided transactions with gift cards causing "Error During Processing of Till Transactions" | Bug | 2 | Blocked | 8 | 0-Noise | yes | Despite huge efforts it was not possible to reproduce the issue. Because of the priority of this issue we will keep it in the next sprint backlog and try to progress as much as possible | Not Completed |  | 3 | 0 | 8 | 5 | 0 | 3

## Sprint_4_5 (hidden)
Sprint 4_5, 27.11.2024 - 10.12.2024, Status at Sprint Completion
|  | Team Summary |  |  |  | v v Bitte unbedingt diese Status verwenden! v v v
|  |  |  | Story Points Sum | [6 empty] | Story Points Sum (Spill-over sensitive [SOS] and Carry-over sensitive [COS]) | [5 empty] | Issue Count
|  | Team | Issue Count | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | Completed
| > > > > Bitte unbedingt diese Team-Namen verwenden! > > > > > | Engineering | 23 | 57 | 6 | 59 | 4 | 0 | 63 | 103.5% | 57 | 6 | 59 | 0 | 4 | 103.5% | 21
|  | Payment | 9 | 13 | 11 | 12 | 12 | 0 | 24 | 92.31% | 10 | 10 | 11 | 0 | 9 | 110% | 4
|  | Sales | 12 | 39 | 19 | 50 | 8 | 0 | 58 | 128.2% | 39 | 19 | 50 | 0 | 8 | 128.2% | 11
|  | Vlinder | 13 | 51 | 0 | 40 | 11 | 0 | 51 | 78.43% | 40 | 0 | 29 | 0 | 11 | 72.5% | 9
|  | TTT | 28 | 76 | 3 | 36 | 40 | 3 | 79 | 47.37% | 76 | 3 | 36 | 3 | 40 | 47.37% | 11
|  | TNT | 18 | 40 | 11 | 35 | 13 | 3 | 51 | 87.5% | 40 | 11 | 34 | 3 | 14 | 85% | 12
|  | TFS | 15 | 46 | 8 | 30 | 24 | 0 | 54 | 65.22% | 46 | 8 | 30 | 0 | 24 | 65.22% | 9
|  | 0-Noise | 10 | 34 | 8 | 16 | 26 | 0 | 42 | 47.06% | 6 | 8 | 11 | 0 | 3 | 183.3% | 7
|  | Synergy | 12 | 29 | 6 | 23 | 12 | 0 | 35 | 79.31% | 29 | 6 | 24 | 0 | 11 | 82.76% | 9
|  | Papillon | 11 | 28 | 2 | 17 | 10 | 0 | 30 | 60.71% | 22 | 2 | 19 | 0 | 5 | 86.36% | 7
|  | Total | 128 | 356 | 66 | 278 | 138 | 6 | 422 | 78.09% | 314 | 65 | 260 | 6 | 113 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 120 | 425 | 31 | 76 | 151 | 501 | 144 | 487 | 7 | 14 | 151 | 501
|  | Completed | 81 | 282 | 19 | 46 | 100 | 328 | 95 | 318 | 5 | 10 | 100 | 328
|  | Not Completed | 36 | 134 | 12 | 30 | 48 | 164 | 46 | 160 | 2 | 4 | 48 | 164
|  | Removed | 2 | 6 | 0 | 0 | 2 | 6 | 2 | 6 | 0 | 0 | 2 | 6
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
ANP-23700 | [IRL] Card payment throws Wrong Terminal State error on SimTill | Bug | 3 | Closed | 3 | 0-Noise | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-22892 | reg 1,2, and 3 - PC freezing constantly | Bug | 2 | Closed | 3 | 0-Noise | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-20270 | AUS End of Day: Bank not found in configuration | Bug | 4 | Blocked | 5 | 0-Noise |  | We encountered additional challenges when merging the issue on the NP Application Test repository that could not be resolved until the end of the Sprint. | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-15108 | Use country-specific amount and weight formatting for Weighing Report | Bug | 3 | In Development | 5 | 0-Noise |  | Unfortunately this Story will spill over to PI4-6. Once the coding and testing was successful we had issues with the NP Application tests. | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-23778 | Revert ANP-22433 from master | Story | 3 | Closed | 1 | 0-Noise |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-23217 | Provide device information in devices.xml for multilane proxy | Story | 3 | In Development | 13 | 0-Noise |  | Unfortunately this Story will also spill over to Sprint PI4-6. We did not anticipate the need for an additional CHOP configuration and we encountered challenges during testing that made the completion within PI4-5 impossible. | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-23193 | Redesigned / deleted / disabled for OfflineDetectionRunnableTest | Story | 3 | Closed | 1 | 0-Noise | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-22433 | Refactor VerifyPriceController | Story | 3 | In Development | 8 | 0-Noise |  | Unfortunatly this Story will also spill over to PI4-6. | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
ANP-19527 | Remove secret from monitoring | Story | 3 | Closed | 2 | 0-Noise |  |  | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
ANP-23960 | Support to stabalize master build | Story | 3 | Closed | 1 | 0-Noise | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-22907 | Remove cho-updater invocation from NEWPOSS post-install scripts | Story | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-23717 | Newposs updater does not remove packages when required during update | Bug | 3 | In Development | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-23917 | Fix newposs-client signature during jenkins build | Task | 1 | Closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-1520 | Decide to whom the certificates of fiscalization in Austria and Slovenia belong and move them accordingly | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4293 | Evaluate supply of SCO-DN hardware device information | Story | 3 | Blocked | 1 | Engineering |  | Depends on input from DN | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
CHO-4519 | Increase the root user's password length to 64 characters (MIT0013124) | Story | 2 | In Test | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-4737 | Define a CMDB interface | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-4852 | Analyse and handle usb device with kernel 3-8.1.2 | Story | 3 | In Development | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-4915 | Release Sprint PI4-5 Artefacts | Story | 3 | Blocked | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-4955 | CDT Client reports Local IP address does not match certificate if till client is offline | Bug | 2 | Blocked | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4957 | Provide documentation for NHPI printer reconfiguration | Story | 3 | Closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-4965 | Pick ANP-20185 and ANP-22214 changes for Release 1.25D | Story | 3 | Closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-4966 | kickstart_postinstall_restore.log missing after installation | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5007 | Upgrade Base OS to Rocky 9.5 | Story | 3 | In Test | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5011 | SCO touch-displays do not respond to input | Bug | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5019 | Implement container log management | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-5020 | Fix permission warnings from mosquitto logs | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5028 | A scratch installation, SCO shortcuts zip-till-logs and debug-info save all .log files under /var/log/assco | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-5056 | Migrate bizerba cs300 software display for SCO | Story | 3 | Ready | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-5076 | Supply a list of devices that can state their serial number | Story | 3 | Closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-5077 | TLRD Tasks | Task | 3 | In Progress | - | Engineering |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5090 | Explicitly managing bizerba CS300 file permissions conflicts with bizerba C2 rpm installation | Bug | 3 | Closed | 3 | Engineering | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
CHO-7 | Check and delete expired slo certificates if there are no dependencies | Story | 3 | Closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
2 | [SCO] Provide API endpoint for layout sale receipts as PDF | Story | 3 | Closed | 2 | Papillon |  | After spillover: Merge and tests are still left to do. Remaining estimate is 1 SP. Main driver of unexpected effort was analysis regarding the thread safety. | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
BF-396 | [ADAPTER] Send receipts with receipt discount information from butterfly adapter to Yocuda | Story | 3 | In Acceptance | 3 | Papillon |  |  |  | 1 |  | 1 | 0 | 1 | 0 | 0
BF-307 | [SCO] Export simple sale receipt to Butterfly adapter | Story | 3 | Closed | 5 | Papillon |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
BF-410 | [ADAPTER] Improve Butterfly adapter configuration | Story | 3 | Closed | 2 | Papillon |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
BF-414 | [SCO] Amend mapping of unique sale receipt ID | Story | 3 | In Development | 5 | Papillon |  | will be a spillover | Not Completed |  | 1 | 5 | 0 | 4 | 0 | 1
BF-446 | [ADAPTER] Replace GrpcAdvice by ServerInterceptor | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-442 | [SCO] Extend the transmission of sale receipts to the Butterfly adapter with the option to send discount information | Story | 3 | In Development | 3 | Papillon |  | will be a spillover | Not Completed |  | 2 | 3 | 0 | 1 | 0 | 2
BF-457 | [ADAPTER] Retrieve a customer's loyalty information from CEE | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-458 | [ADAPTER] Align attributes sent to Yocuda with expected mapping | Story | 3 | In Development | 2 | Papillon | yes |  | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
BF-559 | [ADAPTER][SCO][SPIKE] Clarify what is needed for establishing a connection from checkouts to CEE and Yocuda from the Gebit test lab and notify people responsible if needed | Story / Spike | 3 | Closed | 2 | Papillon |  | Fixed with ticket ITH-1795 | Completed |  |  | 2 | 0 | 2 | 0 | 0
BF-440 | Onboarding Nicolai | Task | 3 | Closed | - | Papillon |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-23889 | [CHOP] Card payment fails, because PinPrinting activation fails for non-PinPrinting articles | bug | 1 | in development | 5 | Payment | yes | no fix necessary | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-23181 | Create Multilane IP assignment extension setting | story | 3 | in review | 3 | Payment |  |  | Not Completed | 1 |  | 1 | 0 | 0 | 0 | 1
ANP-23670 | Set Multilane IP assignment extension setting for CH | story | 3 | in review | 1 | Payment |  | small issue with integrity tests required temporary status revert | Not Completed | 1 |  | 1 | 0 | 0 | 0 | 1
ANP-19512 | Set up test hardware | story | 3 | in development | 3 | Payment |  |  | Not Completed | 2 |  | 2 | 0 | 0 | 0 | 2
ANP-23344 | Enable FiscalizationPerformCheck for Austria | story | 3 | in development | 3 | Payment |  | likely complete by end of sprint | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
ANP-18159 | [Preliminary Tests] SVS & etc/Medion for Sale of Internal and External EGC | story | 3 | closed | 3 | Payment |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23350 | Post Release Tasks for NP Release 4.5.0 | story | 3 | closed | 2 | Payment | yes |  | Completed | 1 |  | 0 | 1 | 1 | 0 | 0
ANP-18173 | Translations to IT & FR | story | 3 | closed | 2 | Payment | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
ANP-23197 | Printing of printer, scanner and terminal assignments on software and bundle version receipt | story | 3 | in development | 2 | Payment | yes | Implementation accepted by PO | Not Completed |  |  | 0 | 2 | 0 | 0 | 2
ANP-23769 | ANP-20895 check 801-036 different prices on POS | Bug | 2 | In Development | 3 | Sales | yes | Merge pending | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-22995 | In TCS-3454 at Step 8, void of earlier EGC activation receipt is not successful. Till displays 'Void not possible'. | Bug | 3 | Closed | 3 | Sales |  | Merge pending | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23677 | US - Voided transactions containing LINKED ITEMS are not processed in transactiondataqueue table | Bug | 2 | In Development | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-20250 | Technical change: Source for Receipt Layout from Compas to local resource for receipt shooting layouted receipts | Story | 3 | In Development | 20 | Sales |  | Tests currently running | Completed |  |  | 20 | 0 | 20 | 0 | 0
ANP-23187 | Enable configuration of cashier name and number on cashier display at the MCO | Story | 3 | Closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23497 | Build Maintenance Release 3.18.4 | Story | 3 | In Development | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23671 | Adjust confirmation workflow for MCO restart after triggered resynch | Story | 3 | Blocked | 3 | Sales |  | Tests need to run after code freeze lift + merge | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23436 | [SPIKE] Analyze the checkMK monitoring values used for the deprecated Replication Interface related to master data polling and processing | Story | 3 | In Development | 5 | Sales | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-23454 | Customer Scanner availability check | Story | 3 | In Development | 8 | Sales | yes |  | Not Completed |  |  | 0 | 8 | 0 | 0 | 8
ANP-23895 | Build MCO part of NEWPOSS release 3.10.17 | Story | 3 | In Development | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-23904 | Analyse need of Integrity test for ANP-22666 | Task | 3 | Closed | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-23894 | Review ANP-22433 | Task | 3 | In Development | 1 | Sales | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-15469 * | Allow inner classes in case of functional interfaces in ArchUnit rules | Story | 3 | Closed | 5 | Synergy | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
ANP-23684 | RVM voucher can not be redeemed in case of an offline scenario at the till | Bug | 2 | In Development | 5 | Synergy |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-17917 | Check and solve instanceof handling at equals methods | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-23572 | [SPIKE] - Automate the Parameter Post Release Tasks | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-23628 | [SPIKE] - Investigate the possibility of splitting API from scale satellite implementation | Story | 3 | Closed | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-23720 | Cover HeadlessPOSClientApplication with unit tests | Story | 3 | Closed | 3 | Synergy |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23957 * | Stabilize till-dev master builds | Story | 3 | Closed | 1 | Synergy | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-14529 | [SPIKE] automate the update to new version in till/till-application-tests | Story | 3 | In Development | 2 | Synergy |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-16465 | Remove and fix private references in exported OSGi classes | Story | 3 | Ready | 1 | Synergy |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
ANP-22666 | Refactor CSR Tests and LTC | Story | 3 | In Development | 5 | Synergy |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-23533 | Concept for MCO: FiscalNullStartReceipt creation during CSR | Task | 3 | In Progress | 5 | Synergy |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23721 | Onboarding Hanna | Task | 3 | In Progress | 2 | Synergy |  |  | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
NPSCO-16711 | Adapt pricing and purchase service to keep prices for same articles constant on a receipt | Story | 2 | In Development | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17361 | Evaluate different approaches for observability | Task | 3 | Closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17712 | Improve memory setting for systems with 16 GB RAM | Story | 3 | In Development | 2 | TFS |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17713 | Integrate new EFT driver in SCO (Pepper removal) - UK | Story | 2 | Blocked | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17717 | [US + AUS] Update fails from 3.13.4 to SCO-Client 3.13.5 (postgres migration/update is failing) | Bug | 1 | Closed | 3 | TFS | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-17745 | Test Task 4.9.0 | Task | 3 | In Progress | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17749 | Cherry Picking Maintenance Release 3.10.10 | Task | 3 | In Progress | 3 | TFS |  | will be a spillover | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17750 | Cherry Picking Maintenance Release 3.13.6 | Task | 3 | closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17751 | Cherry Picking Maintenance Release 3.18.2 | Task | 3 | Open | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-11856 | [SPIKE] Setup and use the Bizerba C2 POS Scale driver 64 bit version [4 Days] | Task | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16619 | [9] Remove code from package assco-pos-app-adap‎ter-local-testsupport | Task | 3 | In Progress | 1 | TNT | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
NPSCO-16620 | [10] Document changes to POS that were necessary to get it running with Spring Boot | Task | 3 | In Review | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17241 | SCO Legacy & AHEAD - CPD TaxableAmount field incorrect for Partial EBT and Voided line items | Bug | 2 | In Development | 3 | TNT |  |  | Completed | 3 | 3 | 3 | 0 | 0 | 0 | 3
NPSCO-17297 | Onboarding Jörg Enkel | Task | 3 | Closed |  | TNT |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-17380 | Testing Maintenance Release 3.18.2 | Task | 3 | In Progress | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17455 | Fix UK and baseline component tests | Task | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17540 | [US] SCO-adapter exports taxSums although tax middleware is offline | Bug | 2 | In Development | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17711 | Cancel button in weighing process leads to an exception | Bug | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17722 | Knowledge transfer release building and update release documentation | Task | 3 | Ready | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17725 | Testing Release 4.9.0 | Task | 3 | Closed | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17726 | Support Maintenance Release 3.10.10 and 3.13.6 | Task | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16393 | Update Purchase Service after Spring Migration RP | Story | 3 | In Development | 5 | TFS |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17300 | Tax middleware timeouts are being ignored by SCO | bug | 2 | In Development | 3 | TFS |  | will be finalized at the sprint end | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17523 | Implement logging on service edges with timing information | Story | 5 | in development | 5 | TFS | yes | will be a spillover | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
NPSCO-17747 | Test Task 3.10.10 | Task | 3 | Open | 5 | TFS |  | will be a spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17748 | Test Task 3.13.6 | Task | 3 | Open | 5 | TFS |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17785 | Test Task 3.18.2 | Task | 3 | Open | 1 | TFS |  |  | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
NPSCO-16616 | [7] Build MSI, deploy it on a TestLab SCO, execute a developer test and fix findings | Task | 3 | In Progress | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-16949 | [SCO] POS printer don't respond after update with boot error | Bug | 2 | In Development | 3 | TNT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17235 | [Incident Taskforce] Trigger device re-initialisation when printer connection not lost | Story | 2 | In Development | 3 | TNT | yes | Will solve problems for NPSCO-16949 | Not Completed | 3 | 1 | 0 | 3 | 2 | 0 | 1
NPSCO-18026 | Testing Maintenance Release 3.13.6 | Task | 3 | In Progress | 1 | TNT | yes |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
NPSCO-18050 | Maintenance Release 3.18.2 Test Part II | Task | 3 | In Progress | 3 | TNT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-17376 | Maintenance Release Build 3.18.2 | Task | 3 | In Progress | 3 | TNT |  |  | Removed |  |  | 3 | 0 | 0 | 3 | 0
NPSCO-16369 | Errorhandling of failing Article lookup during EGC payment | Story | 3 | Closed | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-16483 | Different representation of the EGC card number in the Receipt and Activation Receipt | Bug | 3 | in Test | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16516 | Voided EGC payment still on printed receipt | Bug | 3 | in Test | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17294 | SupportNOW - SCO - Wrong Price | Bug | 1 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17318 | Update Release documentation | Task | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17330 | Fix SonarQube issues in FTH | Task | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17515 | Release Build 4.9.0 | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17714 | Create plan for test tool | Task | 3 | In Progress | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17735 | Change the IDE tooling | Task | 3 | In Progress | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17736 | Test Release 4.9.0 [C] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17737 | Test Release 4.9.0 [M] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16261 | Handle partial/split EGC payments in the transaction after shutdown | Story | 3 | Blocked | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-16390 | Voiding of an EGC and Payment with another EGC results in no Taxes being paid | Bug | 3 | Blocked | 3 | TTT |  | Blocked regarding release tests | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17240 | SCO 3 - transaction command rejected | Bug | 2 | Open | 5 | TTT |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17699 | Knowledge Transfer for EGC-EPAY | Task | 3 | In Progress | 2 | TTT |  |  | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
NPSCO-17700 | Knowledge Transfer to Release and update documentation | Task | 3 | In Progress | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17738 | Maintenance Release 3.10.10 | Task | 3 | Ready | 3 | TTT |  | New delivery date: 16.12 | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17739 | Maintenance Release 3.13.6 | Task | 3 | In Progress | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17740 | Test Maintenance Release 3.10.10 [C] | Task | 3 | Ready | 3 | TTT |  | New delivery date: 16.13 | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17741 | Test Maintenance Release 3.10.10 [M] | Task | 3 | Ready | 3 | TTT |  | New delivery date: 16.14 | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17742 | Test Maintenance Release 3.13.6 [C] | Task | 3 | In Progress | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17743 | Test Maintenance Release 3.13.6 [M] | Task | 3 | In Progress | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17746 | Release Build 4.10.0 | Task | 3 | Ready | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17881 | Onboarding Markus Weißeise | Task | 3 | In Progress |  | TTT | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18013 | Pre-Test newest Purchase Version with OPS changes | Task | 3 | Ready | 3 | TTT | yes |  | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-18015 | Test Maintenance Release 3.18.2 [C] | Task | 3 | In Progress |  | TTT | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-18016 | Test Maintenance Release 3.18.2 [M] | Task | 3 | In Progress |  | TTT | yes |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-17316 | Second partial payment with (SVS) EGCs leads to message "insufficent funds" while enough balance is available | bug | 3 | Ready | 3 | TTT |  |  | Removed |  |  | 3 | 0 | 0 | 3 | 0
ANP-23144 | BF-388 Jenkins | Story | 3 | Closed | 8 | Vlinder |  |  | Completed | 2 |  | 2 | 0 | 2 | 0 | 0
ANP-23192 | Extend error message for cashier with error 10045 "scale sentry"/"Shrink Monitoring" | Story | 3 | In Development | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23242 | BF-135 Mapping | Story | 3 | In Development | 8 | Vlinder |  |  | Completed | 8 |  | 8 | 0 | 8 | 0 | 0
ANP-23245 | BF-55 Promo | Story | 3 | In Development | 8 | Vlinder |  |  | Completed | 3 |  | 3 | 0 | 3 | 0 | 0
ANP-23584 | BF-404 Identify | Story | 3 | Closed | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23585 | BF-405 PDF Spike | Story | 3 | In Development | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23586 | BF-44 Adapter local | Story | 3 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23590 | Support with testing IT Fiscal Server MCO/SCO | Task | 3 | Closed | - | Vlinder |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-23629 | IT Fiscal Printer not printing Datamatrix codes | Task | 3 | Closed | - | Vlinder |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-21712 | [SPIKE] Mettler Toledo module installation | Story | 3 | In Development | 8 | Vlinder |  |  | Not Completed | 8 | 8 | 8 | 0 | 0 | 0 | 8
ANP-22494 | [ITA] Instant Lottery Code not printed on receipt | Bug | 2 | In Development | 3 | Vlinder |  |  | Not Completed | 3 |  | 3 | 0 | 0 | 0 | 3
ANP-23919 * | Fatma Onboarding | Task | 3 | In Progress | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
ANP-23967 * | Support Mettler Toledo testing in Aldi Testlab | Task | 3 | In Progress | - | Vlinder |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0

## Sprint_4_4 (hidden)
Sprint 4_4, 13.11.2024 - 26.11.2024, Status at Sprint Completion
Team Summary
|  |  |  | Story Points Sum | [6 empty] | Spill-over sensitive (SOS) and Carry-over sensitive (COS) | [5 empty] | Issue Count
| Bitte unbedingt die Team-Namen aus der Team Summary verwenden! ------> | Team | Issue Count | Initially Planned | Pulled after Start | Completed | Not Completed | Removed | Total |  | Initially Planned | Pulled after Start | Completed | Removed | Not Completed | Completed vs. Initially Planned | Completed
|  | Engineering | 24 | 79 | 6 | 70 | 13 | 2 | 85 | 88.61% | 79 | 6 | 70 | 2 | 13 | 88.61% | 18
|  | Payment | 9 | 21 | 1 | 5 | 14 | 3 | 22 | 23.81% | 13 | 1 | 7 | 3 | 4 | 53.85% | 4
|  | Sales | 9 | 56 | 5 | 23 | 38 | 0 | 61 | 41.07% | 56 | 5 | 23 | 0 | 38 | 41.07% | 5
|  | Vlinder | 12 | 59 | 1 | 33 | 27 | 0 | 60 | 55.93% | 59 | 1 | 50 | 0 | 10 | 84.75% | 7
|  | TTT | 19 | 56 | 6 | 29 | 33 | 0 | 62 | 51.79% | 56 | 6 | 29 | 0 | 33 | 51.79% | 9
|  | TNT | 21 | 50 | 10 | 41 | 19 | 0 | 60 | 82% | 50 | 10 | 41 | 0 | 19 | 82% | 16
|  | TFS | 12 | 40 | 7 | 16 | 31 | 0 | 47 | 40% | 40 | 7 | 16 | 0 | 31 | 40% | 5
|  | 0-Noise | 10 | 38 | 5 | 17 | 26 | 0 | 43 | 44.74% | 38 | 5 | 17 | 0 | 26 | 44.74% | 5
|  | Synergy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Papillon | 8 | 21 | 2 | 13 | 10 | 0 | 23 | 61.9% | 21 | 2 | 16 | 0 | 7 | 76.19% | 5
|  | Total | 116 | 399 | 41 | 234 | 201 | 5 | 440 | 58.65% | 391 | 41 | 253 | 5 | 174 | ---
Category Summary
|  |  | Planned |  | Pulled after Start |  | Total |  | Estimated (Jira Story Points = #) |  | Not Estimated (Jira Story Points = -) |  | Total
|  |  | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP | Count | SP
|  | Scope | 105 | 430 | 19 | 47 | 124 | 477 | 117 | 463 | 7 | 14 | 124 | 477
|  | Completed | 63 | 232 | 11 | 27 | 74 | 259 | 68 | 247 | 6 | 12 | 74 | 259
|  | Not Completed | 40 | 193 | 8 | 20 | 48 | 213 | 47 | 211 | 1 | 2 | 48 | 213
|  | Removed | 2 | 5 | 0 | 0 | 2 | 5 | 2 | 5 | 0 | 0 | 2 | 5
[11 empty] | Flat Rate for "-" Story Points | 2
Key | Summary | Issue Type | Priority | Jira Status | Jira Story Points | Team | Pulled after Start | Notes | Status | Carry-over | Spill-over | SP Initially Planned (COS) | SP Pulled after Start (COS) | SP Completed (COS & SOS) | SP Removed (COS & SOS) | SP Not Completed (COS & SOS)
[ANP-21583] | Refactor Multilane State | Story | 3 | in development | 8 | Payment |  | Integrity Tests sind massenhaft rot; technische Schuld hat sich sehr groß herausgestellt | Not Completed | 1 | 1 | 1 | 0 | 0 | 0 | 1
[ANP-21635] | Disimplement Rebooking of Payments with failed signature check - Extension deprecation | Story | 3 | closed | 2 | Payment |  | wird im Laufe des Tage (26.11.) gemerged | Completed | 1 |  | 1 | 0 | 1 | 0 | 0
[ANP-23181] | Create Multilane IP assignment extension setting | Story | 3 | in development | 3 | Payment |  | wahrscheinlich morgen (27.) erst fertig | Not Completed | 3 | 1 | 3 | 0 | 2 | 0 | 1
[ANP-23497] | Build Maintenance Release 3.18.4 | Story | 3 | open | 3 | Payment |  |  | Removed |  |  | 3 | 0 | 0 | 3 | 0
[ANP-23346] | Build Release 4.5.0 | Story | 3 | closed | 3 | Payment |  | wird im Laufe des Tage (26.11.) gemerged | Completed |  |  | 3 | 0 | 3 | 0 | 0
[ANP-23350] | Post Release Tasks for NP Release 4.5.0 | Story | 3 | in development | 2 | Payment |  | hängt am BO | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
[ANP-22916] | get messages related to payment in conjunction with article tender restrictions | Task | 3 | closed | - | Payment |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
[ANP-23057] | lay the foundation for integrity testing multilane AT | Task | 3 | closed | - | Payment |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
[ANP-23670] | Set Multilane IP assignment extension setting for CH | Story | 3 | in development | 1 | Payment | yes | wahrscheinlich morgen (27.) erst fertig | Not Completed |  | 1 | 0 | 1 | 0 | 0 | 1
ANP-14075 | Start UK lottery services only in UK | Story | 2 | blocked | 5 | Sales |  |  | Not Completed | 5 |  | 5 | 0 | 0 | 0 | 5
ANP-11593 | Amend count of articles with linked service articles on VGA display and receipt | Story | 3 | closed | 8 | Sales |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-22950 | Activation of 8+Code (HU, SL, IT) and 18+Code (SL, IT) | Story | 3 | closed | 5 | Sales |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23107 | Till does not sync to CFRM changes. Sync only happens after aldi_compas_mv.db is deleted and the till has been restarted. | Bug | 3 | closed | 3 | Sales |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-20250 | Technical change: Source for Receipt Layout from Compas to local resource for receipt shooting layouted receipts | Story | 3 | in development | 20 | Sales |  |  | Not Completed | 20 |  | 20 | 0 | 0 | 0 | 20
ANP-23008 | Enable testability of UK Systems | Story | 3 | blocked | 8 | Sales |  |  | Not Completed | 8 |  | 8 | 0 | 0 | 0 | 8
ANP-23187 | Enable configuration of cashier name and number on cashier display at the MCO | Story | 3 | in development | 5 | Sales |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
ANP-23195 | Change printed cashier name to cashier number on tax refund receipt | Story | 3 | in development | 2 | Sales |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
ANP-23470 | 3.2B4 & 3.2B5 PECW/PERW items not ringing correctly at ECO's, asking to be weighed when entering item code, cannot scan UPC's | Bug | 1 | in development | 5 | Sales | yes |  | Completed |  |  | 0 | 5 | 5 | 0 | 0
CHO-3253 | Provide Mosquitto-Service | Story | 3 | closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-3436 | Implement update mechanism for containers | Story | 3 | closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-3440 | Define convention on providing persistent storage to containers | Story | 3 | closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4468 | Implement CheckMK checks that monitor devices connected to an MCO till | Story | 3 | closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-4469 | Implement CheckMK checks that monitor devices connected to an SCO till | Story | 3 | closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-4829 | Kickstart postinstall logs are empty | Story | 3 | closed | 2 | Engineering |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
CHO-4863 | Reduce disk consumption of Jenkins-Builds | Story | 3 | closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4937 | Run CIS Benchmark for PI4 | Story | 3 | closed | 1 | Engineering |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
CHO-4972 | Investigate issues with fiscal adapter IT on MCO | Story | 3 | closed | - | Engineering | yes |  | Completed |  |  | 0 | 0 | - | 0 | 0
CHO-5006 | Provide CHO-Platform releases with Bizerba Software Display version 4 | Story | 2 | closed | 5 | Engineering | yes | short-term high-priority addition by AS, potential fix for CHO-4739 | Completed |  |  | 0 | 5 | 5 | 0 | 0
CHO-7 | Check and delete expired slo certificates if there are no dependencies | Story | 3 | in development | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-1520 | Decide to whom the certificates of fiscalization in Austria and Slovenia belong and move them accordingly | Story | 3 | Ready | 3 | Engineering |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
CHO-3254 | Monitoring checks for Mosquitto | Story | 3 | closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-3255 | Ensure Delivery of Messages that arrived before the consumers were started | Story | 3 | closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-3435 | Implement automated security scan for container images | Story | 3 | closed | 5 | Engineering |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
CHO-3437 | Provide connection information to client systems in a secure way | Story | 3 | in acceptance | 3 | Engineering |  | likely to be completed until Nov 26 EOB | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4293 | Evaluate supply of SCO-DN hardware device information | Story | 3 | blocked | 1 | Engineering |  | awaiting feedback from DN | Not Completed |  |  | 1 | 0 | 0 | 0 | 1
CHO-4737 | Define a CMDB interface | Story | 3 | in development | 5 | Engineering |  |  | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
CHO-4739 | AT Scales are randomly not working 3.1A/3.2B | Bug | 1 | closed | 8 | Engineering |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
CHO-4864 | Timesync issues between the till PC and the Store Server. | Story | 1 | closed | 3 | Engineering |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4965 | Pick ANP-20185 and ANP-22214 changes for Release 1.25D | Story | 3 | in development | 1 | Engineering | yes |  | Not Completed |  |  | 0 | 1 | 0 | 0 | 1
CHO-4915 | Release Sprint PI4-4 Artefacts | Story | 3 | blocked | 2 | Engineering |  | release will be built in the next sprint | Removed |  |  | 2 | 0 | 0 | 2 | 0
CHO-4939 | Evaluate software provided by DN | Story | 3 | In Review | 3 | Engineering |  | will be completed until Nov 26 EOB | Completed |  |  | 3 | 0 | 3 | 0 | 0
CHO-4940 | [2PT] TLRD tasks | Story | 3 | In Progress | - | Engineering |  | will be completed until Nov 26 EOB | Completed |  |  | 0 | 0 | - | 0 | 0
NPSCO-17319 | Integrate new EFT driver in SCO (Pepper removal) | Bug | 3 | Closed | 3 | TFS |  | will be completed on sprint end | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16393 | Update Purchase Service after Spring Migration RP | Story | 3 | In Development | 5 | TFS | yes | Spillover | Not Completed |  |  | 0 | 5 | 0 | 0 | 5
NPSCO-17343 | ASSCO updater does not update packages from cho-dependencies repositories | Bug | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17361 | Evaluate different approaches for observability | Task | 3 | In Progress | 5 | TFS |  | Spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17382 | Plan and create stories for Logging, Tracing and Monitoring epic NPSCO-17084 | Task | 3 | Closed | 5 | TFS |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16711 | Adapt pricing and purchase service to keep prices for same articles constant on a receipt | Story | 3 | In Development | 5 | TFS |  | Spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17086 | Fix SonarQube findings (RP-Services and Library config client) | Task | 3 | In Progress | 8 | TFS |  | Spillover | Not Completed |  |  | 8 | 0 | 0 | 0 | 8
NPSCO-16980 | Remove docker desktop dependency | Task | 3 | In Progress | 5 | TFS |  | Spillover -will removed for the next sprint | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17424 | Support Maintenance Release 3.18.2 | Task | 3 | In Progress | 3 | TFS |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-16188 | [NL UK] Change some attendant interventions into customer messages | Story | 3 | closed | 2 | TFS | yes | will be completed on sprint end | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-17420 | Test Task 4.8.0 |  | 3 | Closed | 3 | TFS |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17298 | Onboarding Kai Lippert |  | 3 | In Progress |  | TFS |  |  | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-17367 | SCO-adapter keystore is not updated/reloaded in case certificate is updated | Bug | 2 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17379 | Testing Release 4.8.0 | Task | 3 | Closed | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17376 | Maintenance Release Build 3.18.2 | Task | 3 | Ready | 3 | TNT |  | Spillover | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-15728 | [SCO Pentest] m4: Disable Reflection in gRPC Service | Story | 2 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-16614 | [5] Fix failing jenkins build | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16610 | [2] Wire all beans as Spring @Component that where automatically wired by Guice before starting migration to Spring | Task | 3 | In Progress | 3 | TNT |  | Spillover | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17452 | Fix CH component tests | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17453 | Fix IRL component tests | Task | 3 | Closed | 3 | TNT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17454 | Fix ITA component tests | Task | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17455 | Fix UK and baseline component tests | Task | 3 | In Progress | 5 | TNT |  | Spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17456 | Fix US component tests | Task | 3 | Closed | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-16615 | [6] Get all POS adapter launchers running | Task | 3 | Closed | 2 | TNT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-16949 | [SCO] POS printer don't respond after update with boot error | Bug | 2 | In Development | 3 | TNT | yes | Spillover | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-15469 | [SCO CH][Test] Provide configured (CFRM) language for region to TPiScan | Story | 2 | Closed | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17380 | Testing Maintenance Release 3.18.2 | Task | 3 | Ready | 1 | TNT |  |  | Completed |  |  | 1 | 0 | 1 | 0 | 0
NPSCO-17297 | Onboarding Jörg Enkel | Task | 3 | In Progress | 5 | TNT |  | Spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17463 | Write test concept for pos-adapter spring migration | Task | 3 | In Progress | 5 | TNT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17551 | Support Maintenance Release 3.18.2 | Task | 3 | Closed |  | TNT | yes |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-17451 | Fix AUS component tests | Task | 3 | Closed | 3 | TNT | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
NPSCO-16617 | [8] Close the Gib-Gas-GUI when Bootstrap fails | Task | 3 | In Progress | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-17705 | Setup docker images for Rocky Linux based VSS International R27.1 | Task | 3 | In Progress | 2 | TNT | yes |  | Completed |  |  | 0 | 2 | 2 | 0 | 0
NPSCO-17180 | Release Build 4.8.0 | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17519 | Test Release 4.8.0 [M] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-17520 | Test Release 4.8.0 [C] | Task | 3 | Closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-16998 | Incident - declined payment, in AHEAD Stores the amount is being sent through to CPD but for Legacy Stores 0 amount is being sent through | Bug | 2 | Blocked | 3 | TTT |  | Spillover | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17140 | Check Baseline Criteria for DN-Interface test for QF-Test | Task | 3 | In Progress | 5 | TTT |  | Spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17106 | Action plan for EGC | Task | 3 | closed | 3 | TTT |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
NPSCO-15432 | Remove workaround for unnecessary balance inquiry | Task | 3 | In Progress | 3 | TTT |  |  | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17059 | SCO 9 (reg 15) printer incorrect/bad print formatting. | Bug | 3 | Closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17374 | [AnalyseSpike] Handling Donation DIC menu with DN | Task | 3 | closed | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17318 | Update Release documentation | Task | 3 | In Progress | 5 | TTT |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
NPSCO-17330 | Fix SonarQube issues in FTH | Task | 3 | In Progress | 5 | TTT |  | Spillover | Not Completed |  |  | 5 | 0 | 0 | 0 | 5
NPSCO-17234 | Test EGC Event Voucher | Task | 3 | In Progress | 2 | TTT |  |  | Completed |  |  | 2 | 0 | 2 | 0 | 0
NPSCO-17464 | [TechnicalDebt] Remove Stale branches and Build jobs (annually task) | Task | 3 | Closed |  | TTT |  |  | Completed |  |  | 0 | 0 | 0 | 0 | 0
NPSCO-16261 | Handle partial/split EGC payments in the transaction after shutdown | Story | 3 | In Development | 3 | TTT |  | Spillover | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-16390 | Voiding of an EGC and Payment with another EGC results in no Taxes being paid | Bug | 3 | In Development | 3 | TTT |  | Spillover | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-16369 | Errorhandling of failing Article lookup during EGC payment | Story | 3 | In Development | 2 | TTT |  | Spillover | Not Completed |  |  | 2 | 0 | 0 | 0 | 2
NPSCO-17515 | Release Build 4.9.0 | Task | 3 | Open | 3 | TTT |  | Spillover | Not Completed |  |  | 3 | 0 | 0 | 0 | 3
NPSCO-17294 | SupportNOW - SCO - Wrong Price | Bug | 1 | In Development | 3 | TTT | yes | Spillover | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
NPSCO-16516 | Voided EGC payment still on printed receipt | Bug | 3 | In Development | 3 | TTT | yes | Spillover | Not Completed |  |  | 0 | 3 | 0 | 0 | 3
ANP-23051 | Improve Coverage of RVM Locking in Integrity Tests | Story | 3 | Closed | 3 | Vlinder |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23145 | BF-56 Communication | Story | 3 | Closed | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23604 * | Merge ANP-22501 to 3.18.4 (Store 2014 3.1) | Story | 3 | Closed | 1 | Vlinder | yes |  | Completed |  |  | 0 | 1 | 1 | 0 | 0
ANP-21712 | [SPIKE] Mettler Toledo module installation | Story | 3 | In Development | 8 | Vlinder |  | Spillover | Not Completed |  | 2 | 8 | 0 | 6 | 0 | 2
ANP-22494 | [ITA] Instant Lottery Code not printed on receipt | Bug | 2 | Blocked | 3 | Vlinder |  | Spillover | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3
ANP-23144 | BF-388 Jenkins | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23242 | BF-135 Mapping | Story | 3 | In Development | 8 | Vlinder |  | Spillover | Not Completed |  | 3 | 8 | 0 | 5 | 0 | 3
ANP-23243 | BF-237 Service-API | Story | 3 | In Development | 8 | Vlinder |  |  | Completed |  |  | 8 | 0 | 8 | 0 | 0
ANP-23245 | BF-55 Promo | Story | 3 | In Development | 8 | Vlinder |  | Spillover | Not Completed |  | 2 | 8 | 0 | 6 | 0 | 2
ANP-23476 | Adjustment in abbreviation of tare on receipt in case of multi-use bags | Story | 2 | In Development | 5 | Vlinder |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-23590 | Support with testing IT Fiscal Server MCO/SCO | Task | 3 | In Progress | - | Vlinder |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
ANP-23629 * | IT Fiscal Printer not printing Datamatrix codes | Task | 3 | In Progress | - | Vlinder | yes | Spillover | Not Completed |  |  | 0 | 0 | 0 | 0 | 0
BF-440 | Onboarding Nicolai | Task | 3 | In Progress | - | Papillon |  |  | Completed |  |  | 0 | 0 | - | 0 | 0
BF-412 | [ADAPTER] Send receipts with deposit refund (vouchers) from butterfly adapter to Yocuda | Story | 3 | Closed | 3 | Papillon |  | Spillover | Completed |  | 3 | 3 | 0 | 0 | 0 | 3
BF-410 | [ADAPTER] Improve Butterfly adapter configuration | Story | 3 | In Development | 2 | Papillon | yes | Was actually done at sprint closure. Ticket status was not up to date. | Completed |  |  | 0 | 2 | 2 | 0 | 0
BF-409 | [ADAPTER] Extend Butterfly adapter mock functionalities for CEE communication | Story | 3 | Closed | 5 | Papillon |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
BF-396 | [ADAPTER] Send receipts with receipt discount information from butterfly adapter to Yocuda | Story | 3 | In Development | 3 | Papillon |  |  | Not Completed |  | 1 | 3 | 0 | 2 | 0 | 1
BF-393 | [ADAPTER] Add store information to receipts sent from butterfly adapter to Yocuda | Story | 3 | Closed | 3 | Papillon |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
BF-311 | [SCO] Provide API endpoint for layout sale receipts as PDF | Story | 3 | In Development | 2 | Papillon |  |  | Not Completed |  | 1 | 2 | 0 | 1 | 0 | 1
BF-307 | [SCO] Export simple sale receipt to Butterfly adapter | Story | 3 | In Development | 5 | Papillon |  |  | Not Completed |  | 2 | 5 | 0 | 3 | 0 | 2
ANP-23626 | Retrieve/Suspend on same POS while NEWPOSS offline | Bug | 2 | Blocked | 3 | 0-Noise | yes |  | Completed |  |  | 0 | 3 | 3 | 0 | 0
ANP-23443 | Field DISCOUNTVALUE in ALDIASSESSMENTDISCOUNTVALUE does not contain actual discount percentage for percentage based receipt discounts | Bug | 3 | Closed | 3 | 0-Noise |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23442 | Field COUPONEAN in ALDIASSESSMENTDISCOUNTVALUE is not set | Bug | 3 | Closed | 3 | 0-Noise |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23338 | Add handling of the PersistenceException to the End of day process for Electronic Gift Cards |  | 3 | Closed | 3 | 0-Noise |  |  | Completed |  |  | 3 | 0 | 3 | 0 | 0
ANP-23217 | Provide device information in devices.xml for multilane proxy |  | 3 | In Development | 8 | 0-Noise |  | Spillover | Not Completed |  | 8 | 8 | 0 | 0 | 0 | 8
ANP-22554 | [ITA] 5+Code on MCO of SCO receipt leads to till freeze | Bug | 3 | Blocked | 5 | 0-Noise |  |  | Completed |  |  | 5 | 0 | 5 | 0 | 0
ANP-22433 | Refactor VerifyPriceController |  | 3 | In Development | 8 | 0-Noise |  | Spillover | Not Completed |  | 8 | 8 | 0 | 0 | 0 | 8
ANP-20270 | AUS End of Day: Bank not found in configuration | Bug | 4 | Blocked | 5 | 0-Noise |  | Spillover | Not Completed |  | 5 | 5 | 0 | 0 | 0 | 5
ANP-19527 | Remove secret from monitoring |  | 3 | In Development | 2 | 0-Noise | yes | Spillover | Not Completed |  | 2 | 0 | 2 | 0 | 0 | 2
ANP-15108 | Use country-specific amount and weight formatting for Weighing Report | Bug | 3 | In Development | 3 | 0-Noise |  | Due to challenges with our build system we could not complete the merge for the story on time. The Story will spillover to the next Sprint PI4-5 | Not Completed |  | 3 | 3 | 0 | 0 | 0 | 3